## Bhutan
[8 empty] | Year 1 |  |  |  |  | Year 2
OBJ | SDA | REF | IMP | Level | Activity | Activity Description | Year 1 Total | Y1Q1 | Y1Q2 | Y1Q3 | Y1Q4 | Year 2 Total | Y2Q5 | Y2Q6 | Y2Q7 | Y2Q8 | Year 1 and 2 Total
1. To improve the delivery of HIV related services for MSM and TG across South Asia
1.1 Strengthening of civil society and institutional development
1 | 1.1 | BHU 1.1.1 | NFI | Bhutan | In country training programmes for government/NGO sector providers | Tailor made training programmes will be delivered to enable participants to better develop policy, advocate on behalf of, develop, implement, and monitor and evaluate programmes on MSM, TG, and HIV-related issues. This can also include provider training on STI syndromic management for MSM and HIV counselling. [Est. 20 participants x 4 days, TA participation budgeted.] | 3434 |  |  | X |  | 7005.36 |  | X |  | X | 10439.36
1 | 1.1 | BHU 1.1.2 | NFI | Bhutan | Support a national technical working group on MSM, TG and HIV related issues | This working group will inform the development and implementation of proposals addressing MSM, TG, and HIV-related issues, and will directly support the Bhutan CCM to address these issues. [Est. 15 participants x 1 day, TA participation budgeted.] | 0 |  | X | X | X | 2809.08 | X | X | X | X | 2809.08
1 | 1.1 | BHU 1.1.3 | NFI | Bhutan | Regional exposure trips to visit MSM, TG, and HIV related organizations | These trips will allow various governmental, and non-government stakeholders to visit MSM and TG HIV-related organisations in other South Asian countries so they can gain a better understanding of policy and advocacy, HIV-related service provision, and research and dissemination when addressing MSM, TG, and HIV-related issues. [Est. 3 participants x 7 days, including travel.] | 8700 |  |  |  | X | 17748 |  | X |  | X | 26448
1 | 1.1 | BHU 1.1.4 | NFI |  | Participation in a range of national and regional meetings on HIV and AIDS to advocate on MSM and HIV issues | This will involve participation in and development of activities at a range of events to support advocacy, skills sharing, and coordination of MSM and HIV issues. [Est. 1 participant x 5 days, including travel.] | 4650 |  | X | X | X | 7114.5 | X | X | X | X | 11764.5
1 | 1.1 | BHU 1.1.5 | NFI |  | Participation in regional and global AIDS conferences/meetings (World AIDS Congress, PEPFAR conference, Global Health Conference, ICAAP etc.) | Bhutanese participants will share learning from the implementation of this proposal, develop contacts to further to objects of the proposal, and gain knowledge to inform the implementation of the program. [Est. 4 participants x 7 days, including travel.] | 14700 |  |  |  | X | 14994 |  |  |  | X | 29694
OBJ | SDA | REF | IMP | Level | Activity |  | #REF! | Y1Q1 | Y1Q2 | Y1Q3 | Y1Q4 | #REF! | Y2Q1 | Y2Q2 | Y2Q3 | Y2Q4 | #REF!
1. To improve the delivery of HIV related services for MSM and TG across South Asia
1.2 Behaviour change communication – community outreach
1 | 1.2 | BHU 1.2.1 | NFI | Bhutan | Production of BCC materials in Bhutan | Using models developed by NFI, specific BCC materials in appropriate languages will be adapted and/or deveoped for Bhutan in collaboration/consultation with Bhutan partners (NACP). Costs include production/printing and translation. | 6000 |  | X | X | X | 1530 | X |  |  |  | 7530
OBJ | SDA | REF | IMP | Level | Activity |  | Year 1 Total | Y1Q1 | Y1Q2 | Y1Q3 | Y1Q4 | Year 2 Total | Y2Q1 | Y2Q2 | Y2Q3 | Y2Q4 | Year 1 and 2 Total
2. To improve the policy environment with regards MSM, TG, and HIV relates issues across South Asia
2.1 Policy development
2 | 2.1 | BHU 2.1.1 | NFI | Bhutan | Convene a national consultation meeting on MSM, TG, HIV, and sexual health for the government and NGO sectors | This meeting aims to develop and advocate for good policy, coordinate activity, and develop capacity to implement HIV services for MSM and TG. [Est. 50 participants x 2 days, TA participation budgeted.] | 0 |  |  |  |  | 8827.08 |  | X |  |  | 8827.08