## NFI Secretariat
GFATM Regional Project
NFI Activities
Yrs 1 and 2 (quarterly periods)
NFI Secretariat
Ref | Activity | Comments | Q 1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8
NFI 1.1.1 | Identification of office, equip, furnish and operationalise | May require e-registration for change of address with Companies House | bar: Q 1
NFI 1.1.1 | Establish financial and M&E systems | bar: Q 1
NFI 1.1.1 | Recruit and induct project staff | bar: Q 1
NFI 1.1.1 | Management and operations of Secretariat as SR | bar: Q 1 to Q8
NFI 1.1.1 | Website design and development | Contracted to redesign NFI website - as information and knowledge base | bar: Q 1
NFI 1.1.1 | Production of regular finance and activity reports | brings together reports from Regional Office | bar: Q 1 to Q8
Travel

## BHUTAN
GFATM Regional Project
Activities
Yrs 1 and 2 (quarterly periods)
BHUTAN
Ref | Activity | Comments | Q 1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8
NFI 1.1.2a | Training by TA in Bhutan | Training and capacity building provided by NFI seconded Technical Advisor to Maan AIDS Foundation (India)-1 to 4 day workshops depending on topic, with approximately 20 partcipants each for various stakeholders: subject matter - Year 1:1) male sexualities, gender and health (participatory) to develop an understanding of male sexualities in Bhutan; 2) sensitisation workshop with multi-sectoral stakeholders towards developing an understanding of same sex behaviours, risks and vulnerabilities and rights; Year 2:1) continuation of sensitisation workshops, 2) capacity development on psychosexual issues counselling and community mobilisation |  |  | x | x | x |  | x
NFI 1.1.2a | Site visits by TA | Visits to Bhutan by Technical Advisor including travel within Bhutan to conduct MSM assessments and possibly community mobilisation |  |  | x | x | x | x | x | x
BHU 1.2.1 | Production of BCC materials | BCC resources to be designed in NFI regional office in collaboration with NACP or adapting existing materials: funds cover translation and printing/production of materials in Bhutan | x | x | x |  | x
BHU 1.1.1 | In country training programmes for government/NGO sector providers | Tailor made training programmes will be delivered to enable participants to better develop policy, advocate on behalf of, develop, implement, and monitor and evaluate programmes on MSM, TG, and HIV-related issues. This can also include provider training on STI syndromic management for MSM and HIV counselling 20 participants x 4 days - TA participation budgeted. |  |  | x |  |  | x |  | x
BHU 1.1.2 | Support a national technical working group on MSM, TG and HIV related issues | This working group will inform the development and implementation of proposals addressing MSM, TG, and HIV-related issues, and will directly support the Bhutan PCM to address these issues. 15 participants for 1 day-TA participation budgeted.NFI will provide draft TOR to NACP to adapt and form technical working group - to discuss early start-up quarter 3 and quarter 4. |  |  | x | x | x | x | x | x
BHU 1.1.3 | Regional exposure trips to visit MSM, TG, and HIV related organizations | These trips will allow various governmental, and non-government stakeholders, to visit to MSM and TG HIV-related organisations in other South Asian countries so they can gain a better understanding of policy and advocacy, HIV-related service provision, and research and dissemination when addressing MSM, TG, and HIV-related issues. 3 participants x 7 days including travel. |  |  |  | x |  | x |  | x
BHU 1.1.4 | Participation in a range of national and regional meetings on HIV and AIDS to advocate on MSM and HIV issues | This will involve participation in and development of activities at a range of events to support advocacy, skills sharing, and coordination of MSM and HIV issues. 1 person x 5 days including travel. | x | x | x | x | x | x | x | x
BHU 1.1.5 | Participation in regional and global AIDS conferences/meetings (World AIDS Congress, PEPFAR conference, Global Health Conference, ICAAP etc.) | Bhutanese participants will share learning from the implementation of this proposal, develop contacts to further the objectives of the proposal, and gain knowledge to inform the implementation of the program. Up to 4 participants for 7 days including travel. |  |  |  | x |  |  |  | x
BHU 2.1.1 | Convene a national consultation meeting on MSM, TG, HIV, and sexual health for the government and NGO sectors | This meeting aims to develop and advocate for good policy, coordinate activity, and develop capacity to implement HIV services for MSM and TG. 50 participants x 2 days with TA participation budgeted. | [5 empty] | x