## HIV AIDS_Financial Data
HIV/AIDS FINANCIAL REPORTING FORM
Country |  | Bhutan |  |  | PLEASE REFER TO THE "GUIDANCE FOR COMPLETION OF THE ENHANCED FINANCIAL REPORTING TEMPLATE" DOCUMENT TO ASSIST YOU IN COMPLETING THE TEMPLATE
Grant No. |  | 607-G03-H
PR |  | GNHC
Currency |  | USD
[6 empty] | dd-mm-yyyy |  |  |  | dd-mm-yyyy
|  |  |  | Current Reporting Period | Start Date: | 2009-08-01 |  | Cumulative Reporting Period | Start Date: | 2008-02-01
[5 empty] | End Date: | 2010-01-31 |  |  | End Date: | 2010-01-31
The end date for the current reporting period and cumulative reporting period must be the same
The "TOTAL" rows in Table A, B and C will have a RED background if the amounts in each table do not agree. If the Totals for each Table agrees, these rows will have a YELLOW background.
A- BREAKDOWN* BY EXPENDITURE CATEGORY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | Category |  |  | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
1 | Human Resources |  |  | 7200 | 35712.68 | 28512.68 |  | 46800 | 35826.73 | -10973.27
2 | Technical Assistance |  |  | 8000 | 22790.86 | 14790.86 | There was major re programming of the TA budget through the accelerated plan of action so that’s why there is over shooting of the expenditure | 174100 | 65149.31 | -108950.69 | Although the PR has recruited sevral TA for the project, the budgetary provision kept for hiring of TA for strengthening M&E was not possible as the agreed person refused to turn up due to other engagements
3 | Training |  |  | 69416 | 223073.27 | 153657.27 | No of a significant variance | 664382 | 586492.63 | -77889.37
4 | Health Products and Health Equipment |  |  | 0 | 83194 | 83194 | Most of the health equipments targetted to be procured have not been procured during this period such as the CD machines, Elisa reader, test kits & Vacutianers | 206500 | 84181.52 | -122318.48 | The Huge variance in the procuement of health products is due to the non procurement of CD machine & Elisa reader. The quotation has been floated the budget will be spent in the next quarter.
5 | Medicines and Pharmaceutical Products |  |  | 0 | 759.14 | 759.14 | The ARV drugs & OI drugs amounting to USD 33,000 have not been procured in this reporting cycle | 57500 | 22097.71 | -35402.29 | The supply order for the ARV & OI drugs amounting to Usd 33,000 have been placed but the payments were not made
6 | Procurement and Supply Management Costs |  |  | 0 |  |  |  | 0 | 0
7 | Infrastructure and Other Equipment |  |  | 0 | 7098.86 | 7098.86 |  | 122364 | 108544.03 | -13819.97
8 | Communication Materials |  |  | 33100 | 57448.81 | 24348.81 | Not of a significant variance | 152400 | 96117.4 | -56282.6
9 | Monitoring and Evaluation |  |  | 6000 | 1581.62 | -4418.38 |  | 43000 | 6323.4 | -36676.6
10 | Living Support to Clients/Target Population |  |  | 0 |  |  |  |  | 0
11 | Planning and Administration |  |  | 2700 | 943.36 | -1756.64 | Not of a significant variance | 15400 | 9762.62 | -5637.38
12 | Overheads |  |  | 0 |  |  |  | 20000 |  | -20000
13 | Other |  |  | 0
|  |  | TOTAL | 126416 | 432602.6 | 306186.6 |  | 1502446 | 1014495.35 | -487950.65
B- BREAKDOWN* BY PROGRAM ACTIVITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | Macro-category | Objectives | Service Delivery Area | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
1 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA 1.1: Providing life-skills-based HIV/AIDS education in 140 schools (grade 7 and above) | 10183 | 65152.65 | 54969.65 |  | 135062 | 106970.94 | -28091.06 | The Printing of IEC materials and procurement of AB equipments could not be carried out this reporting period
2 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA 1.2: Providing life-skills-based HIV/AIDS education to 15000 out-of school youth each year through 670 NFE centres and to more than 1000 out-of-school unemployed youth through the department of employment | 13000 | 24437.32 | 11437.32 | Not significant variance | 139582 | 116450.14 | -23131.86 | Not significant variance
3 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA 1.3: Reaching youth through the private sector in 8 towns via 50 hotels, entertainment centres and night clubs | 8000 | 47388.79 | 39388.79 | There was major re programming in the acceleration plan | 67560 | 52965.61 | -14594.39
4 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA 1.4: Establishing youth-friendly health services in 30 hospitals | 3600 | 33884.65 | 30284.65 |  | 48400 | 57922.76 | 9522.76
5 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA 1.5: Intensifying HIV prevention among 10,000 uniformed personnel and their families | 7000 | 28312.6 | 21312.6 |  | 83475 | 52291.3 | -31183.7
6 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA 1.6: Increasing HIV awareness among members of faith-based organizations | 1300 | 20111.02 | 18811.02 |  | 33796 | 32735.22 | -1060.78
7 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA 1.7: Providing services for CSWs, IDUs, and MSMs through NGOs |  | 12813.24 | 12813.24 |  | 40250 | 21744.08 | -18505.92
8 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA 1.8: Expanding testing and counselling services to 2 additional VCT centers, 176 BHUs and 16 army units. | 16813 | 112288.83 | 95475.83 |  | 331389 | 170007.33 | -161381.67
9 | Prevention | To increase access to prevention services for youth and other vulnerable populations | SDA1.9 BCC component and IEC activities | 36100 | 42485.52 | 6385.52 |  | 166490 | 111951.05 | -54538.95
10 | Health Systems Strengthening (HSS) | To increase national capacity in planning, implementation and monitoring HIV activities in the country | SDA 2.1: Strengthening pre-service training at a national institute |  |  |  | The budget for this SDA is confined for the year 1 only | 41050 | 37609.6 | -3440.4 | Not significant variance
11 | Health Systems Strengthening (HSS) | To increase national capacity in planning, implementation and monitoring HIV activities in the country | SDA 2.2: Strengthening national capacity for programme monitoring and evaluation | 9900 | 29180.78 | 19280.78 |  | 213020 | 129161.43 | -83858.57
12 | Health Systems Strengthening (HSS) | To increase national capacity in planning, implementation and monitoring HIV activities in the country | SDA 2.3: Strengthening the management and technical capacity of the NACP | 15000 | 6467.61 | -8532.39 | Not significant variance | 116332 | 80078.86 | -36253.14
13 | Health Systems Strengthening (HSS) | To increase national capacity in planning, implementation and monitoring HIV activities in the country | SDA 2.4: Building the capacity of non-govermental sectors as partner in the national HIV/AIDS response | 5520 | 10079.59 | 4559.59 |  | 36540 | 23268.46 | -13271.54
14 | Care and Support | To increase access to care and support | Treatment: Antiretroviral treatment (ARV) and monitoring |  |  |  | The supply order has been placed but the payments have not been made | 49500 | 21338.57 | -28161.43
| Please Select… |  | Please Select…
TOTAL |  |  |  | 126416 | 432602.6 | 306186.6 |  | 1502446 | 1014495.35 | -487950.65
To add additional rows, right click the row number (Row 39 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
C- BREAKDOWN* BY IMPLEMENTING ENTITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | PR/SR | Name | Type of Implementing Entity | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
1 | PR | Ministry Of Health (MoH) | Ministry of Health (MoH) | 50833 | 204714.7 | 153881.7 | Elisa reader & CD 4 machine not procured, M&E consultant not recruited, KAP survey cound not be completed | 835431 | 503521.49 | -331909.51 | The National AIDS control Programme could not utilize the TA budget of USD 65,000. The health products and equipments such as Elisa reader, CD 4 machines could not be procured. The HIV KAP baseline survey could not be conducted. Budgets available under attending adhoc & GFATM meetings amounting to USD 30,000 COULD NOT BE UTILIZED, ARV drus amounting to USD 33,000 could not be procured
2 | SR | Department of Youth and Sport (MoE) | Other Government | 10183 | 65152.65 | 54969.65 | Due to the acceleration plan and re programming | 135062 | 106970.94 | -28091.06 | The budget unutilized is from the KAP survey, Printing of guidelines and Procurement of AV equipments
3 | SR | Non Formal Education (MoE) | Other Government | 13000 | 7643.98 | -5356.02 | No significant variance | 117582 | 94275.91 | -23306.09 | This budget was not utilized as there was no disbursement from Global Fund to celebrate the World AIDS as celebrated Globally in 1st December. The DR only arrived in February 2010
4 | SR | RoyalInstitute of Health Science | NGO/CBO/Academic | 0 | 0 |  | No budget for RIHS in the second year | 41050 | 37609.6 | -3440.4 | No significant variance
5 | SR | Bhutan Chamber of Commerce Industry | Private Sector | 8000 | 47388.79 | 39388.79 | This over shooting of the expenditure is due to fact that there has been major re pgrgramming in the acceleration plan | 67560 | 52965.61 | -14594.39 | Overall the private sector has not been able to utilize the funds for training of emlpyess of the hotels and bars as they did not have capacity to conduct the training
6 | SR | Dratshang Lhengtshog ( Monastic Body) | FBO | 1300 | 20111.02 | 18811.02 | Due to the acceleration plan and re programming | 33796 | 32735.22 | -1060.78 | No significant variance
7 | SR | Information Communication Bureau (MoH) | Ministry of Health (MoH) | 36100 | 42485.52 | 6385.52 | Major re programming through the acceleration plan | 166490 | 111951.05 | -54538.95 | Most of the IEC activties to be aired or broad casted could not be done. M&E budget was not utilized
8 | SR | Armed Forces ( RBP & RBA) | Other Government | 7000 | 28312.6 | 21312.6 | Not significant variance | 83475 | 52291.3 | -31183.7 | Funds untilized on Printing, KAP survey & sensitization of staffs
9 | SR | Ministry of Labour and Human Resources | Other Government |  | 16793.34 | 16793.34 | This has happended due to the acceleration plan and re programming of the activties | 22000 | 22174.23 | 174.23 | No significant variance
10 | Please Select … |  | Please Select …
| Please Select … |  | Please Select …
|  |  | TOTAL | 126416 | 432602.6 | 306186.6 |  | 1502446 | 1014495.35 | -487950.65
To add additional rows, right click the row number (Row 51 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
* The sum of all three breakdowns should be equal (A- Budget Line-item, B- Program Activity, C- Implementing Entity).
** For the purposes of this report, the SDA Program management and administration should be included in the Supportive Environment Macro Category.
D- ADDITIONAL INFORMATION
Please disclose any relevant information concerning the information in the above tables. Refer to the Guidelines for Completing the Template if required.
Note on A34: Insert Number
Note on A56: Insert Number
Note on B29: This category should only be used as a last resort if there is a type of cost that absolutely cannot be allocated to another cost category
Note on C34: Please remember to include the full name of the objective. If an objective has more than 1 SDA, repeat the objective name on each row for the relevant SDA
Note on D56: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on E30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on E50: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on E68: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on F30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on F50: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on F68: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on G8: Start date for current period cannot be earlier than cumulative period
Note on G30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on G50: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on G68: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on H16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H56: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on I15: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on I33: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I50: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on I55: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I68: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on J30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on J50: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on J68: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on K8: Start date for current period cannot be earlier than cumulative period
Note on K30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on K50: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on K68: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on L16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L56: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.

## Definitions
A- EXPENDITURE CATEGORY
1 | Human Resources | Salaries, wages and related costs (pensions, incentives, supplements, top ups, and other employee benefits, etc.) relating to all employees (including field personnel), and employee recruitment costs.
2 | Technical Assistance (TA) | Costs of all consultants (short or long term) providing technical or management assistance. This includes all costs related to the consultant such as consulting fees, travel and per-diems, field visits and other consultant costs relating to program planning, supervision and administration (including in respect of managing sub-recipient relationships, monitoring and evaluation, and procurement and supply management).
3 | Training | Workshops, meetings, training publications, training-related travel, including training per-diems. Do not include human resources costs related to training which should be included under the Human Resources category.
4 | Health Products and Health Equipment | Health products such as bed nets, condoms, lubricants, diagnostics, reagents, test kits, syringes, spraying materials and other consumables. Health equipment such as microscopes, x-ray machines and testing machines (including the 'Total Cost of Ownership' of this equipment such as reagents, and maintenance costs). Do not include other types of non-health equipment, as these costs should be included under the Infrastructure and Other Equipment category below.
5 | Medicines and Pharmaceutical Products | Cost of antiretroviral therapy, medicines for opportunistic infections, anti-tuberculosis medicines, anti-malarial medicines, and other medicines. Do not include insurance, transportation, storage, distribution or other similar costs, as such costs should be included in Procurement and Supply Management costs below.
6 | Procurement and Supply Management Costs (PSM) | Transportation costs for all purchases (equipment, commodities, products, medicines) including packaging, shipping, insurance and handling. Warehouse, PSM office facilities, and other logistics requirements. Procurement agent fees. Costs for quality assurance (including laboratory testing of samples), and any other costs associated with the purchase, storage and delivery of items. Do not include staff, TA, PSM, Information Technology systems, health products or health equipment costs, as these costs should be included in the categories above.
7 | Infrastructure and Other Equipment | This includes health infrastructure rehabilitation, renovation and enhancement costs. Non-health equipment such as generators and beds. Information technology (IT) systems and software, website creation and development. Office equipment, furniture, audiovisual equipment. Vehicles, motorcycles, bicycles. Related maintenance, spare parts and repair costs.
8 | Communication Materials | Printed material and communication costs associated with program-related campaigns, TV spots, radio programs, advertising, media events, education, dissemination, promotion, promotional items.
9 | Monitoring and Evaluation (M&E) | Data collection, surveys, research, analysis, travel, field supervision visits, and any other costs associated with monitoring and evaluation. Do not include human resources, TA or M&E IT systems costs, as these costs should be included in the categories above.
10 | Living Support to Clients/Target Population | Monetary or in-kind support given to clients and patients e.g.: school fees for orphans, assistance to foster families, transport allowances, patient incentives, grants for revenue-generating activities, food and care packages, costs associated with supporting patients charters for care.
11 | Planning and Administration | Office supplies, travel, field visits and other costs relating to program planning and administration (including in respect of managing sub-recipient relationships). Legal, translation, accounting and auditing costs, bank charges etc. Green Light Committee contributions. Country or Regional Coordinating Mechanism (CCM/RCM) support costs. Do not include human resources costs, as these costs should be included under the Human Resources category above.
12 | Overheads | Overhead costs such as office rent, utilities, internal communication costs (mail, telephone, internet), insurance, fuel, security, cleaning. Management or overhead fees.
13 | Other | Significant costs which do not fall under the above-defined categories. Specify clearly the types of cost in Table D of the Report
B- PROGRAM ACTIVITY
1 | Prevention | Behavioral Change Communication - Mass media Behavioral Change Communication – community outreach Condom distribution Testing and Counseling PMTCT Post-exposure prophylaxis STI diagnosis and treatment Blood safety and universal precaution
2 | Treatment | Antiretroviral treatment and monitoring Prophylaxis and treatment for opportunistic infections
3 | Care and Support | Care and support for the chronically ill Support for orphans and vulnerable children
4 | TB/HIV Collaborative Activities | TB/HIV
5 | Supportive Environment | Policy development including workplace policy Stigma reduction and respect of confidentiality Strengthening of civil society and institutional capacity building Program management and administration
6 | Health Systems Strengthening (HSS) | Service delivery Human resources Community systems strengthening Information system & operational research Infrastructure Procurement and supply management Other - specify
C- IMPLEMENTING ENTITY
- | FBO | Faith-based Organization
- | NGO | Non Governmental Organization. Please note that even if the entity is an NGO but is faith based in any way, it should be included in the FBO category
- | CBO | Community-based Organization. Please note that even if the entity is a CBO but is faith based in any way, it should be included in the FBO category
| Please Select… | Please select…
| FBO | Prevention: BCC - Mass media
| NGO/CBO/Academic | Prevention: BCC - community outreach
| Private Sector | Prevention: Condom distribution
| Ministry of Health (MoH) | Prevention: Testing and Counseling
| Other Government | Prevention: PMTCT
| UNDP | Prevention: Post-exposure prophylaxis (PEP)
| Other Multilateral Organisation | Prevention: STI diagnosis and treatment
Prevention: Blood safety and universal precaution
Treatment: Antiretroviral treatment (ARV) and monitoring
| Please Select… | Treatment: Prophylaxis and treatment for opportunistic infections
| Prevention | Care and support: Care and support for the chronically ill
| Treatment | Care and support: Support for orphans and vulnerable children
| Care and Support | TB/HIV collaborative activities: TB/HIV
| TB/HIV Collaborative Activities | Supportive environment: Policy development including workplace policy
| Supportive Environment | Supportive environment: Strengthening of civil society and institutional capacity building
| Health Systems Strengthening (HSS) | Supportive environment: Stigma reduction in all settings
Supportive environment: Program management and administration
HSS: Service delivery
HSS: Human resources
HSS: Community Systems Strengthening
HSS: Information system & Operational research
HSS: Infrastructure
HSS: Procurement and Supply management
HSS: other - specify

## Annex 1
Annex 1 | Use these worksheets to provide more detailed information on variances if necessary

## Annex 2
Annex 2 | Use these worksheets to provide more detailed information on variances if necessary

## Annex 3
Annex 3 | Use these worksheets to provide more detailed information on variances if necessary