## PR_Cover page
On-going Progress Update and Disbursement Request
Instructions to the Principal Recipient for completing the On-going Progress Update and Disbursement Request
Progress Update
The Progress Update part of this form requires the Principal Recipient (PR) to provide:
- Past expenditure and programmatic performance information for the reporting period just ended
- An update on the progress made towards satisfaction of the conditions precedent (if any) set forth in Annex A to the Grant Agreement applicable
to the period covered by the Progress Update
- A detailed Statement of Sources and Uses of Funds (Cash Flow Statement) for the reporting period just ended
For the Statement of Sources and Uses of Funds, the PR may use its own usual format and expenditure line items as derived from its budgeting and accounting records. The Global Fund does not prescribe specific expenditure line items, but prefers that the PR's reporting format is activity-based, in conformity with the proposal's objectives and service delivery areas. The PR is expected to clearly show actual expenditures as compared to budget for both its own expenditures as well as for disbursements to sub-recipients. The Statement of Sources and Uses of Funds should support the information disclosed in this form in Section 1.C (Program Expenditures) and Section 2.A (Cash Reconciliation for Period Covered by Progress Update).
Disbursement Request
The Disbursement Request part of this form requires the PR to state the cash requirement for meeting on-going program expenditures. The disbursement requested from the Global Fund normally covers the PR's cash requirements for one reporting period, plus one additional quarter as a cash buffer, to ensure the PR has adequate cash on hand for program expenses at all times. The period covered by the Disbursement Request is the period that immediately follows the Reporting Period covered by the Progress Update (as explained above).
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Section 1A (1)
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: |  | Bhutan
Disease: |  | HIV/AIDS
Grant Number: |  | BTN-607-G03-H
Principal Recipient: |  | GROSS NATIONAL Happiness COMMISSION, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01
Currency: |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: |  | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: |  | 3
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | Select
Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  | N/A
TERMS AND ACRONYMS USED IN THIS PROGRESS UPDATE AND DISBURSEMENT REQUEST HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: Programmatic and Financial Progress Update
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
Select
Select
Select
Select
Select
Select
Select
Select
Select
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Intended Yearly Targets | Actual Yearly Results | Reasons for deviation and any other comments
[6 empty] | Value | Year
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | 0.05% | 2006 | N/A | TBD | this will be determined at the 5th year of the project
Impact | HIV prevalence among uniformed personnel |  |  |  |  | 0.20% | 2006 | N/A | TBD | this will be determined at the 5th year of the project
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | TBD | N/A | N/A | TBD | The results will be determined at the end of the KAP survey
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | TBD at the end of 1st year |  | NA | TBD | Targets to be included based on Baseline survey which will be conducted at the end of year 1
Select
Select
Select
Select
Select
Select
Select
Select

## PR_Section 1A (2)
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: |  | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: |  | 3
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Directly Tied? | Level | Baseline (if applicable) |  | Intended Targets to date | Actual Results to date | Reasons for programmatic deviation and any other comments
[8 empty] | Value | Year
1 | Prevention: BCC - community outreach | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | Yes | Select | 0 | 2006 | 0 | 0 | This indicator will be achieved at the end of the 6th Quarter
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education |  |  |  | Yes | Select | 0 | 2006 | 0 | 0 | The department of Youth responsible for fulfilling this indicator has conducted a consultative a work shop for the life skill based material development on HIV/AIDS. They are in the process of hiring a TA to develop the materials.Once the materials are developed the teachers will be trianed
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  | Yes | Select | TBD |  | TBD | 0 | This will be determined through the KAP study. The PMT has evaluated CV for the M&E consultant. Once the consultant is hired the KAP study will be conduted. One of the main ToR for the consultant is to develop the protocols for the KAP study.
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings |  |  |  | Yes | Select | N/A |  | 400 | 0 | The Non formal education division of the ministry of education has already developed life skills based materials on HIV/AIDS for youth NFE learners during the given quarter . They are now planning to train the ToT on the materials developed. Once the ToT is completed they will further train the NFE learners and this indicator will be met . Also one of the sub recipients for this indicator is the ministry of Labor ( due to the delay in signing of MoU with ministry of Labor the release of funds to carry activities as per the MoU was delayed.
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  | Yes | Select | 0 | 2006 | 100 | 0 | The funds for training the NFE instructors has been released to the NFE.The training is schedlued in the 3rd week of december once the ToT is completed. The materials have already been developed. Currently the indicator has not been met
1 | Prevention: BCC - community outreach | Number of hotels, bars and entertainment outlets providing HIV prevention services |  |  |  | No | Select | 0 | 2006 | 100 | 50 | The Bhutan Chamber of Commerce & Industry have conducted sensitization work shop for the hoteliers, bar owners & entertainment outlets at Thimphu & Gelephu.This activity is also being pursued through the World Bank Project for HIV/AIDS & STI control. The hotels providing prevention services are measured through the condom boxes available in the hotels.The training of the employees of bars and hotels, distribution of the IEC materials is yet to be conducted. They are in the process of indentifying the hot spots. Once done this indicator will be met.
1 | Prevention: BCC - community outreach | Number of hospitals providing youth-friendly health services |  |  |  | Yes | Select | 0 | 2006 | 20 | 20 | Health staffs from 20 hospitals been trained on provision of youth friendly health services based on the guidelines adapted from WHO
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  | No | Select | 6000 | 2006 | 3000 | 1056 | The RBP being one of the sub recipients have conducted 3 rounds of sensitization work shop on HIV/AIDS amongst the uniformed personnel * their families. The funds for this activity was utilized from SR own budget which was to be re imbursed once the activity is completed . Therefore it is not reflected as expenditure .The RBA is yet to conduct the sensitization workshop on HIV/AIDS. This indicator will be achieved in subsequent quarters
1 | Prevention: BCC - community outreach | Number of monks reached by HIV/AIDS education in monasteries |  |  |  | Yes | Select | 500 | 2005 | 500 | 185 | Conducted one day work shop for 185 monks of Thimphu monsatery. The curriculum on HIV/AIDS has already been developed, training & printing done through UNICEF funding. The remaining budet will be clubbed to conduct sensitization works shop for the monks on HIV/AIDS. The indicator eill be met after the sensitization . The budget to conduct the sensitization was very low to (USD 860) not sufficent to accomodate more monks.
1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results |  |  |  | No | Select | 1500 | 2005 | 3000 | 4900 | The report is collected & compiled from HISC & integrated VCT from all the district hospitals . It is collected on quarterly basis.
1 | Prevention: Testing and Counseling | Number of basic health units providing VCT services |  |  |  | No | Select | 0 | 2005 | 50 | 62 | in the 3rd quarter 62 health assistants from 62 BHU has been trained on VCT of HIV/AIDS services . Basically counselling services will be provided by the BHU staffs. Testing facilities are not yet avaibale for this BHU II but they give counseling services. Testing facilities are only available in BHU I & HOSPITALS
1 | Prevention: BCC - community outreach | Number of programs (slots) aired on TV and radio on HIV and STI and BCC messages |  |  |  | No | Select | 0 |  | 0 | 0
2 | HSS: Information system & Operational research | Number of health workers trained in revised HIV data reporting and analysis |  |  |  | Yes | Select | 0 | 2005 | 70 | 40 | Due to limited budget we could only train the DHO & DMO of the districts. The remianing training will be conducted through the world bank support
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment |  |  |  | No | Select | 25%(19) | 2006 | 25(33%) | 28 | As of 30th Nove there are 28 PLWHA are put on ARV treatment. This is also done being through the World Bank Project for HIV/AIDS & STI control. The ARV drugs are now procured through the Global Fund funds through Clinton foundation
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select
Select | [5 empty] | Select | Select

## PR_Section 1A & 1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: | 3
iv. Overall evaluation of performance
Over all the performance of the grant is satisfactory. During the third quarter (July - September) . Most of the planned activties from the National HIV/AIDS control has been conducted. However the Sub Recipients are not very pro active and they don’t request for timely release of the funds thereby the financial utilization is quite low.
v. Planned changes in the program, if any.
The following activties of dratsang lhentsho ( religious bodies) has been re appropriated with the approval from the 11th PCM & also from the Fund Port Folio Manager: 1. Development of education materials 2. Local consultant 3. Printing of materials 4 training of lectureres has been re appropriated to conduct HIGH LEVEL ADVOCACY amongst the monks as the above activtities has already been conduted through UNICEF SUPPORT. For RIHS, funds allocated for TA has been re programmed for the purchase of teaching aids for the institute with the permission of 11th PCM & also the FMP.
vi. Other program results, success stories, issues or lessons learned
To coordinate with different sub recipients is a daunting task. Most of them seem to have agreed on one thiing but their cooperation is not much therer. Not getting timely reports from them. ALSO THERE ARE HIRING OF MANY TECHNICAL ASSISTANCE AND GETTING THE RIGHT PERSON IS ALSO A CHALLANGE.
B. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? (Yes/No) | PR Comments
The delivery by the PR of the statement confirming the bank account into which the grant funds will be disbursed |  |  |  | Yes | This condition was fulfilled
The delivery by the PR of of a letter signed by Authorized representative of the PR seeting the name, titel & authenticated specimen signature of each person authorized to sign disbursement request |  |  |  | Yes | fulfilled
The delivery by the PR to the GF of evidence , in fomr and substance satisfactory to the Global Fund , that a project manager has been hired with appropraite qualifications & expereince |  |  |  | Yes | fulfilled
the deliveryof a completed version of the Monitoring and Evaluation Systems Strengthening Tool (Dated January 2006 and available from the Global Fund website) that has been prepared by the Principal Recipient in consultation with the Program stakeholders |  |  |  | Yes | The M&E plan has been prepared through a consultative workshop with the stakeholders. TA was provided by the WHO. The plan has not yet been delivered to GFATM as it has to be aligned to the National Strategic Plan for HIV/AIDS
the delivery of an updated plan for monitoring and evaluating Program activities (the “Updated M&E Plan”) incorporating the recommendations upon completion of the Monitoring and Evaluation Systems Strengthening Tool. |  |  |  | In Progress | PR will deliver the plan after aligning with the National Strategic Plan for HIV/AIDS after 3rd week of July 2008
delivery of a revised budget for the Program Term (the “Revised Program Budget”) if the amendments incorporated into the Updated M&E Plan necessitate amendments to the budget for the Program Term |  |  |  | In Progress | The revised program budget is being made & will be delivered by July end
written approval of the Global Fund of the Updated M&E Plan and Revised Program Budget (the latter only being applicable if condition c. of this sub-section B.2 is applicable); |  |  |  | No | The approval has not been received yet
delivery of evidence, in form and substance acceptable to the Global Fund, that the Sub-recipient management and assessment requirements mandated in article 14. of the Standard Terms and Conditions of this Agreement have been complied with |  |  |  | Yes | SR assessment was carried out by the PR in march 2008.
Project Management Unit of the Principal Recipient has been strengthened, in particular through the hiring of staff, with appropriate qualifications, for the following positions: program officer, M&E officer, and finance officer/accountant. |  |  |  | Yes | PMT has been strengthened , 1 Project manager, 1 M&E officer 2 fiinance officer, 1 office assistant, plans are underway to hire one additional M&E person.
delivery by the Principal Recipient to the Global Fund of a plan for the procurement, use and supply management of the Health Products for the Program as described in subsection (c) of Article 19 of the Standard Terms and Conditions of this Agreement (the “PSM Plan”) |  |  |  | Yes | PSM plan prepaerd for HIV/AIDS for two year & submitted to GFATM
written approval of the Global Fund of the PSM Plan. |  |  |  | No | GFATM hasgiven written apporval of the PSM plan on 28 january 2008
Select

## PR_Section 1C
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: | 3
C. PROGRAM EXPENDITURES
All amounts are in: USD | Budget for Reporting Period | Actual for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | Reason for Variance
1. Total actual expenditures vs. budget | 146742 | 50821.83 | 95920.17 |  | 622600 | 110062.9 | 512537.1
1a. PR's total expenditures | 71646 | 40985.52 | 30660.48 | The RELEASE of the project funds kept in the government fund account with the ministry of finance was delayed for two months ( july to august ) This was done as the national budget has to be approved by the parliament. The delay in funds caused slower implementation. The funds arrived only in the first week of september from the ministry of finance. This has slowed down the implementation | 332344 | 67844.6 | 264499.4 | The budget was received on 15th March 2008 where as the project start date was from 1st Feb 2008. Not much time to utilise the fund. The first quarter has only two months. As soon as fund DR notification was received the PLC account was opened with the Dept of Public Accounts. Also separate FIC opened for the project
1b. Disbursements to sub-recipients | 75096 | 9836.31 | 65259.69 | SR's are not implmenting the activtiies on time despite constant reminder. There also changes in the focal person from SR's They have prior engegement in other activities. Also due to the national cennenerary & coronation celebration most of the SR like BCCI & ARMED FORCES were engaged for the national event. Also the delay in fund release from the ministry of finance has slowed down the fund utilization | 290256 | 42218.3 | 248037.7
2. Health product expenditures vs. budget (already included in '"Total actual" figures above) | 0 | 0 | 0 |  | 25500 | 0 | 25500
2a. Pharmaceuticals |  |  |  |  | 16500 | 0 | 16500 | The MoU for the procurement of ARV drugs from the clinton foundation was signed.
2b. Health products, commodities and equipment |  |  |  |  | 9000 |  | 9000
Program expenditures were used for the procurement of health products: |  |  |  | No
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | Select

## PR_Section 2
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  | Cycle: |  | Semester | Number:
Disbursement Request - Period Covered: |  | Beginning Date: |  |  | End Date:
Disbursement Request - Number: |  | N/A
Section 2: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 6 from Cash Reconciliation section of the period covered
by the previous Progress Update): | [8 empty] | 563358.93
Add: | 2. Cash disbursed to the PR by the Global Fund during the period covered by this progress update: (1)
| 3. Interest received on bank account and other income received: | [7 empty] | 0
Less: | 4. Total program expenditures during period covered by Progress Update (value entered in Section 1C. "Total actual expenditures"): | [6 empty] | 50821.83
| 5. Other expenditures incurred (bank fees, other transaction costs, net exchange rate gains/losses): | [7 empty] | 50821.83
6. Cash Balance: End of period covered by Progress Update: | [8 empty] | 512537.1
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update (2, 3):
7. Period beginning date: |  |  | end date: |  |  | amount as originally budgeted: | forecasted amount:
8. Additional quarter
(cash "buffer") beginning date (4): |  |  | end date: |  |  | amount as originally budgeted: | forecasted amount: |  | 0
Please explain any variance between the forecasted amounts and the amounts as originally budgeted |  |  | The variation in the forcasted amount and the amount as originally budgeted is due to the delay in fund disbursement.Also such activtiies with the line ministries was carried out and also changes are seen in the focal person of the line ministries. The Project Coordinator being assigned such responsibility for the first time.
Less: | Cash Balance: End of period covered by Progress Update (number 6 above): | [6 empty] | 512537.1
| 9. Cash received from the Global Fund after the period covered by Progress Update or cash "in transit" (5) (if any): | [7 empty] | 512537.1
10. PR's Disbursement Request from the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [8 empty] | 0
11. Does the PR's Disbursement Request include funds for health product procurement? |  |  |  |  | Select
12. Exchange Rate (used to translate local currency into USD): |  |  | 39.25
Footnotes:
1 - Gross amount disbursed by the Global Fund (i.e., any associated bank fees or transaction costs should not be deducted in this line, but included in line 5. “Other expenditures incurred”
2 - Expenditures listed must be covered by current budget forecasts
3 - Total forecasted net cash expenditures should include any commitments made in the period covered by the Progress Update that are forecasted to be spent during the period covered by the Disbursement Request
4 - Additional period (cash "buffer"): disbursement of funds for Q9 is contingent upon the signing of Phase 2 or as otherwise stipulated per implementation letter
5 - “Cash in transit” includes amounts disbursed but not yet received by the PR and disbursement requests not yet approved by the Global Fund.

## PR_Section 3
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Bhutan
Disease: | HIV/AIDS
Grant number: | BTN-607-G03-H
Principal Recipient: | GROSS NATIONAL Happiness COMMISSION, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: | 2008-02-01
Currency: | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: | 3
DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: | Cycle: | Semester | Number:
Progress Update - Period Covered: | Beginning Date: |  | End Date:
Progress Update - Number: | N/A
Section 3: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from Section 2.B line 10, in: USD): |  | 0
2. Amount requested in words (in: USD): |  | Zero
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name: | Thinley Namgyel
Title: | Chief Programme Officer
Date and Place:
Bank Account Details (if different than the account details specified on block 9 of the face sheet of the Grant Agreement) |  |  |  |  | Comments (e.g. changes to PR's bank account details, "split disbursements" to the PR and third parties etc.):
Owner of Bank Account:
Account Title:
Account number:
Bank name:
Bank address:
Bank SWIFT Code:
Bank Code:
Routing instructions:

## LFA_Cover page
LFA On-going Progress Review and Disbursement Recommendation
Instructions to the LFA for completing the LFA On-Going Progress Review and Disbursement Recommendation
The Principal Recipient (PR) is required, through the On-Going Progress Update and Disbursement Request, to:
1. Provide past expenditure and programmatic performance information for the Reporting Period just ended; and
2. State its cash requirement for meeting on-going program expenditures.
The LFA is required, using this form, to verify progress and make recommendations on the cash amount requested.
Progress Update
The PR will report past expenditure and programmatic performance information for the Reporting Period just ended as well as progress made towards fulfillment of any conditions precedent/special conditions. The LFA is required to review and verify this information and, in accordance with the information fields set out in this form, to comment on current and cumulative progress.
Disbursement Recommendation
The PR will normally make a disbursement request from the Global Fund covering the PR's cash requirements for one Reporting Period, plus one additional quarter as a cash buffer, to ensure that the PR has adequate cash on hand for program expenses at all times. The Reporting Period for which the Disbursement Request is being made should be the period that immediately follows the Reporting Period covered by the PR's progress update (as explained above). The LFA is required to verify the PR's Cash Reconciliation and to ensure that the cash request is properly calculated. The LFA should recognize that the cash request should be based on the most up-to-date budgets for the relevant periods which the LFA should review for reasonableness.
Documents to be attached/retained
When submitting this form to the Global Fund, the LFA should attach the following:
1. PR On-Going Progress Update and Disbursement Request form (by email with originals to follow by mail)
2. Any supplementary information, as appropriate, to inform the Global Fund of the review and verification process and to support the review and recommendation
The LFA should also retain the PR's detailed Statement of Uses of Funds (Cash Flow Statement) for the Reporting Period just ended as well as any additional relevant documentation of verifications performed (to be provided upon request by the Global Fund).

## LFA_Section 1A (1)
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  | Bhutan | [10 empty] | Bhutan
Disease: |  | HIV/AIDS | [10 empty] | HIV/AIDS
Grant Number: |  | BTN-607-G03-H | [10 empty] | BTN-607-G03-H
Principal Recipient: |  | GROSS NATIONAL Happiness COMMISSION, ROYAL GOVERNMENT OF BHUTAN | [10 empty] | GROSS NATIONAL Happiness COMMISSION, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01 | [10 empty] | 39479
Currency: |  | USD | [10 empty] | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 3 | [7 empty] | Quarter | 3
Progress Update - Period Covered: |  | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30 | [7 empty] | 39630 | 39721
Progress Update - Number: |  | 3 | [10 empty] | 3
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | [8 empty] | Semester
Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  | N/A | [10 empty] | N/A
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic and Financial Progress
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations | [9 empty] | 1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country | [9 empty] | 2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA | [9 empty] | 3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Intended Yearly Targets (from Attachment) | Actual Yearly Results (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on impact and outcome, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | N/A | TBD | Select |  |  | Impact | Percent of women and men aged 15-49 who are HIV infected | N/A | TBD
Impact | HIV prevalence among uniformed personnel |  |  |  |  | N/A | TBD | Select |  |  | Impact | HIV prevalence among uniformed personnel | N/A | TBD
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | N/A | TBD | Select |  |  | Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year | N/A | TBD
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | NA | TBD | Select |  |  | Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year | NA | TBD
Select
Select
Select
Select
Select
Select
Select
Select

## LFA_Section 1A (2)
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: |  | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: |  | 3
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Intended Targets to date (from Attachment) | Actual Results to date (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on progress to date, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
1 | Prevention: BCC - community outreach |  |  |  |  | 0 | 0 | Select |  |  | 1 | Prevention: BCC - community outreach |  | 0 | 0
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | #REF! | #REF! | #REF! | 0 | 0 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | 0 | 0
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | #REF! | #REF! | #REF! | TBD | 0 | Select |  |  | 1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | TBD | 0
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | #REF! | #REF! | #REF! | 400 | 0 | Select |  |  | 1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | 400 | 0
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | #REF! | #REF! | #REF! | 100 | 0 | Select |  |  | 1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | 100 | 0
1 | Prevention: BCC - community outreach | Number of hotels, bars and entertainment outlets providing HIV prevention services | #REF! | #REF! | #REF! | 100 | 50 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of hotels, bars and entertainment outlets providing HIV prevention services | 100 | 50
1 | Prevention: BCC - community outreach | Number of hospitals providing youth-friendly health services | #REF! | #REF! | #REF! | 20 | 20 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of hospitals providing youth-friendly health services | 20 | 20
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | #REF! | #REF! | #REF! | 3000 | 1056 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | 3000 | 1056
1 | Prevention: BCC - community outreach | Number of monks reached by HIV/AIDS education in monasteries | #REF! | #REF! | #REF! | 500 | 185 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of monks reached by HIV/AIDS education in monasteries | 500 | 185
1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | #REF! | #REF! | #REF! | 3000 | 4900 | Select |  |  | 1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | 3000 | 4900
1 | Prevention: Testing and Counseling | Number of basic health units providing VCT services | #REF! | #REF! | #REF! | 50 | 62 | Select |  |  | 1 | Prevention: Testing and Counseling | Number of basic health units providing VCT services | 50 | 62
1 | Prevention: BCC - community outreach | Number of programs (slots) aired on TV and radio on HIV and STI and BCC messages | #REF! | #REF! | #REF! | 0 | 0 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of programs (slots) aired on TV and radio on HIV and STI and BCC messages | 0 | 0
2 | HSS: Information system & Operational research | Number of health workers trained in revised HIV data reporting and analysis | #REF! | #REF! | #REF! | 70 | 40 | Select |  |  | 2 | HSS: Information system & Operational research | Number of health workers trained in revised HIV data reporting and analysis | 70 | 40
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | #REF! | #REF! | #REF! | 25(33%) | 28 | Select |  |  | 3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | 25(33%) | 28
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF! |  |  | Select
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!

## LFA_Section 1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: | 3
B. LFA COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? | LFA Analysis (this should not be a “Copy and Paste” of the comments provided by the PR)
The delivery by the PR of the statement confirming the bank account into which the grant funds will be disbursed |  |  |  | Select |  | The delivery by the PR of the statement confirming the bank account into which the grant funds will be disbursed
The delivery by the PR of of a letter signed by Authorized representative of the PR seeting the name, titel & authenticated specimen signature of each person authorized to sign disbursement request |  |  |  | Select |  | The delivery by the PR of of a letter signed by Authorized representative of the PR seeting the name, titel & authenticated specimen signature of each person authorized to sign disbursement request
The delivery by the PR to the GF of evidence , in fomr and substance satisfactory to the Global Fund , that a project manager has been hired with appropraite qualifications & expereince |  |  |  | Select |  | The delivery by the PR to the GF of evidence , in fomr and substance satisfactory to the Global Fund , that a project manager has been hired with appropraite qualifications & expereince
the deliveryof a completed version of the Monitoring and Evaluation Systems Strengthening Tool (Dated January 2006 and available from the Global Fund website) that has been prepared by the Principal Recipient in consultation with the Program stakeholders |  |  |  | Select |  | the deliveryof a completed version of the Monitoring and Evaluation Systems Strengthening Tool (Dated January 2006 and available from the Global Fund website) that has been prepared by the Principal Recipient in consultation with the Program stakeholders
the delivery of an updated plan for monitoring and evaluating Program activities (the “Updated M&E Plan”) incorporating the recommendations upon completion of the Monitoring and Evaluation Systems Strengthening Tool. |  |  |  | Select |  | the delivery of an updated plan for monitoring and evaluating Program activities (the “Updated M&E Plan”) incorporating the recommendations upon completion of the Monitoring and Evaluation Systems Strengthening Tool.
delivery of a revised budget for the Program Term (the “Revised Program Budget”) if the amendments incorporated into the Updated M&E Plan necessitate amendments to the budget for the Program Term |  |  |  | Select |  | delivery of a revised budget for the Program Term (the “Revised Program Budget”) if the amendments incorporated into the Updated M&E Plan necessitate amendments to the budget for the Program Term
written approval of the Global Fund of the Updated M&E Plan and Revised Program Budget (the latter only being applicable if condition c. of this sub-section B.2 is applicable); |  |  |  | Select |  | written approval of the Global Fund of the Updated M&E Plan and Revised Program Budget (the latter only being applicable if condition c. of this sub-section B.2 is applicable);
delivery of evidence, in form and substance acceptable to the Global Fund, that the Sub-recipient management and assessment requirements mandated in article 14. of the Standard Terms and Conditions of this Agreement have been complied with |  |  |  | Select |  | delivery of evidence, in form and substance acceptable to the Global Fund, that the Sub-recipient management and assessment requirements mandated in article 14. of the Standard Terms and Conditions of this Agreement have been complied with
Project Management Unit of the Principal Recipient has been strengthened, in particular through the hiring of staff, with appropriate qualifications, for the following positions: program officer, M&E officer, and finance officer/accountant. |  |  |  | Select |  | Project Management Unit of the Principal Recipient has been strengthened, in particular through the hiring of staff, with appropriate qualifications, for the following positions: program officer, M&E officer, and finance officer/accountant.
delivery by the Principal Recipient to the Global Fund of a plan for the procurement, use and supply management of the Health Products for the Program as described in subsection (c) of Article 19 of the Standard Terms and Conditions of this Agreement (the “PSM Plan”) |  |  |  | Select |  | delivery by the Principal Recipient to the Global Fund of a plan for the procurement, use and supply management of the Health Products for the Program as described in subsection (c) of Article 19 of the Standard Terms and Conditions of this Agreement (the “PSM Plan”)
written approval of the Global Fund of the PSM Plan. |  |  |  | Select |  | written approval of the Global Fund of the PSM Plan.
Select

## LFA_Section 1C
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: | 3
C. PROGRAM EXPENDITURES
All amounts are in: Please select currency on Page 1 | Budget for Reporting Period | Actual for Reporting Period1 | Variance | LFA Verified (Y/N) | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR) | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR)
1. Total actual expenditures vs. budget | 146742 | 50821.83 | 95920.17 |  |  | 622600 | 110062.9 | 512537.1 | v | 146742 | 50821.83 | 95920.17 | 622600 | 110062.9 | 512537.1
1a. PR's total expenditures | 71646 | 40985.52 | 30660.48 | Select |  | 332344 | 67844.6 | 264499.4 |  | 71646 | 40985.52 | 30660.48 | 332344 | 67844.6 | 264499.4
1b. Disbursements to sub-recipients | 75096 | 9836.31 | 65259.69 | Select |  | 290256 | 42218.3 | 248037.7 |  | 75096 | 9836.31 | 65259.69 | 290256 | 42218.3 | 248037.7
2. Health product expenditures vs. budget (already included in "Total actual" figures above) | 0 | 0 | 0 | Select |  | 25500 | 0 | 25500 |  | 0 | 0 | 0 | 25500 | 0 | 25500
2a. Pharmaceuticals |  |  |  | Select |  | 16500 | 0 | 16500 |  |  |  |  | 16500 | 0 | 16500
2b. Health products, commodities and equipment |  |  |  | Select |  | 9000 |  | 9000 |  |  |  |  | 9000 |  | 9000
Program expenditures were used for the procurement of health products: |  |  |  | Select
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | Select
1 If the LFA makes a correction to the actual expenditures for the reporting period, the LFA should also make a corresponding correction to the PR's requested amount in LFA Section 4.A.1

## LFA_Section 1D
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: |  | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: |  | 3
D. LFA RATING AND COMMENTS ON PROGRAMMATIC AND FINANCIAL PROGRESS
1. LFA's Rating of PR's overall performance (1) |  | Select
2. Reasons for this Rating (including key issues and potential future risks):
3. LFA comments on PR planned changes in the program, if any (please refer to section 1.A.v of the PR's Progress Update / Disbursement Request):
4. LFA comments on data quality and reporting:
5. LFA comments on other program results, success stories, issues or lessons learned (please refer to section 1.A.vi of the PR's Progress Update / Disbursement Request):
1 - This rating should pertain to the cumulative progress (from the beginning of the Program to the end of the period covered by the Progress Update). It should take into consideration programmatic, financial and contextual factors.
- LFA ratings have been modified to be consistent with the Global Fund's new rating system. The new ratings relate to the previous ratings as follows:
New Scale |  | Old Scale
Rating | Description | Rating | Description
A | Expected or exceeding expectations | 5 | Exceptional
|  | 4 | Expected
B1 | Adequate | 3 | Minor adjustments needed
B2 | Inadequate but potential demonstrated | 2 | Major adjustments needed
|  | 1 | Little progress made
C | Unacceptable | 0 | Major program issues
Note on C10: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)

## LFA_Section 2
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number:
Disbursement Request - Period Covered: | Beginning Date: |  | End Date:
Disbursement Request - Number: | N/A
Section 2: LFA Review and Verification of the Principal Recipient's Cash Reconciliation and Disbursement Request
LFA COMMENTS ON THE CASH RECONCILIATION AND DISBURSEMENT REQUEST
1. The PR cash reconciliation is calculated correctly and is supported by a detailed Statement of Sources and Uses of Funds (i.e., Cash Flow statement): |  |  |  | Select
Comments:
2. The PR Cash Request is calculated correctly and is supported by appropriate current budget forecasts: |  |  |  | Select
Comments:
3. The LFA has identified expenditures (incurred or forecasted) that should not be financed by the Global Fund: |  |  |  | Select
Comments:
4. The LFA has identified variance between the forecasted expenditures and the original budget for the disbursement period, including variance in line items: |  |  |  | Select
Comments:

## LFA_Section 3
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number:
Disbursement Request - Period Covered: | Beginning Date: |  | End Date:
Disbursement Request - Number: | N/A
Section 3: LFA Recommendations and Review of Progress on Previous Recommendations
A. LFA RECOMMENDATIONS FOR THE CURRENT PROGRESS UPDATE AND DISBURSEMENT REQUEST
LFA Recommendations |  |  |  | Global Fund Decisions
B. LFA REVIEW OF PROGRESS ON PREVIOUS RECOMMENDATIONS CONFIRMED BY THE GLOBAL FUND
Previous Global Fund Decision |  |  |  | LFA Review of PR Progress

## LFA_Section 4
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | GROSS NATIONAL Happiness COMMISSION, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 3
Progress Update - Period Covered: |  |  | Beginning Date: | 2008-07-01 | End Date: | 2008-09-30
Progress Update - Number: |  |  | 3
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  |  | Cycle: | Semester | Number:
Disbursement Request - Period Covered: |  |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  |  | N/A
Section 4: Disbursement Recommendation and Progress Review Summary
A. DISBURSEMENT RECOMMENDATION
1. Cash amount requested by the Principal Recipient form the Global Fund for next disbursement period plus one additional quarter (amount in: USD): | [6 empty] | 0 |  | 0
2. LFA disbursement recommendation (amount in: USD):
3. Reasons for the LFA's disbursement recommendation:
B. LFA RATING
LFA's rating of PR's overall progress |  |  |  | please select rating in 'LFA_Section 1.D.1'
C. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [7 empty] | Comments regarding verifications, if any:
| Select | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request
| Select | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable).
| Select | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement).
| Select | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress.
| Select | Exchange rate stated by Principal Recipient has been verified and is correct.
| Select | Bank account information provided on the face sheet of Grant Agreement (Grant No. / Mod. No.): |  |  |  |  | (or as otherwise
stated by the PR in its Progress Update / Disbursement Request) has been verified and is correct.
| Select | Current budget forecasts of the Principal Recipient for the next disbursement period plus one additional quarter have been reviewed for reasonableness
Signed on behalf of the LFA:
Name:
Title:
Date and Place:
Note on E34: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)

## LFA_Signature (image)
OPTIONAL - insert image of LFA signature here*: (the size should not exceed the limit of cells B2:D2)
* In every case, the LFA should provide a bona fide signature (in LFA_Section 4) on the original (paper-based) LFA report, sent to the Global Fund by mail.