## PR_Cover page
On-going Progress Update and Disbursement Request
Instructions to the Principal Recipient for completing the On-going Progress Update and Disbursement Request
Progress Update
The Progress Update part of this form requires the Principal Recipient (PR) to provide:
- Past expenditure and programmatic performance information for the reporting period just ended
- An update on the progress made towards satisfaction of the conditions precedent (if any) set forth in Annex A to the Grant Agreement applicable
to the period covered by the Progress Update
- A detailed Statement of Sources and Uses of Funds (Cash Flow Statement) for the reporting period just ended
For the Statement of Sources and Uses of Funds, the PR may use its own usual format and expenditure line items as derived from its budgeting and accounting records. The Global Fund does not prescribe specific expenditure line items, but prefers that the PR's reporting format is activity-based, in conformity with the proposal's objectives and service delivery areas. The PR is expected to clearly show actual expenditures as compared to budget for both its own expenditures as well as for disbursements to sub-recipients. The Statement of Sources and Uses of Funds should support the information disclosed in this form in Section 1.C (Program Expenditures) and Section 2.A (Cash Reconciliation for Period Covered by Progress Update).
Disbursement Request
The Disbursement Request part of this form requires the PR to state the cash requirement for meeting on-going program expenditures. The disbursement requested from the Global Fund normally covers the PR's cash requirements for one reporting period, plus one additional quarter as a cash buffer, to ensure the PR has adequate cash on hand for program expenses at all times. The period covered by the Disbursement Request is the period that immediately follows the Reporting Period covered by the Progress Update (as explained above).
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Section 1A (1)
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: |  | Bhutan
Disease: |  | HIV/AIDS
Grant Number: |  | BTN-607-G03-H
Principal Recipient: |  | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01
Currency: |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: |  | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: |  | 11
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 4
Disbursement Request - Period Covered: |  | Beginning Date: | 2010-11-01 | End Date: | 2011-04-30
Disbursement Request - Number: |  | 5
TERMS AND ACRONYMS USED IN THIS PROGRESS UPDATE AND DISBURSEMENT REQUEST HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: Programmatic and Financial Progress Update
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
Select
Select
Select
Select
Select
Select
Select
Select
Select
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Intended Yearly Targets | Actual Yearly Results | Reasons for deviation and any other comments
[6 empty] | Value | Year
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | 0.05% | 2006 | <0.1% | N/A | Sentinel surveillance will be conducted in the later half of the 2010, currently the surveillance protocol is being revised
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  |  | 0.20% | 2006 | <0.1% | N/A | Sentinel surveillance will be conducted in the later half of the 2010
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | 47% | 2009 | N/A | N/A | The next KAP survey will be conducted in the final year of the project
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | 53% | 2009 | NA | N/A | The next KAP survey will be conducted in the final year of the project
Select
Select
Select
Select
Select
Select
Select
Select
Formulas:
Quarter = IF([Cycle:, row below]="Select","",IF([Cycle:, row below]="N/A","",IF(F13="","",F13+1)))

## PR_Section 1A (2)
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: |  | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: |  | 11
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Directly Tied? | Level | Baseline (if applicable) |  | Intended Targets to date | Actual Results to date | Reasons for programmatic deviation and any other comments
[8 empty] | Value | Year
1 | Prevention: BCC - community outreach | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | Yes | 0 | 0 | 2006 | 44000 | 24106 | The results reported are same as the previous quarter as the focal person was on leave and the reports for the same could not be avialed . However the same will be incroporated in the next reporting.
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education |  |  |  | Yes | 1 | 0 | 2006 | 589 | 269 | The results reported are same as previous quarteras. Since the budget for Q9 was not released this hampered the implementation of the project and also the policy of the ministry of education does not allow teachers to be trained during the academic session and it can be done only during the winter break which is
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  | Yes | 2 | 45 | 2009 | n/a | 45 | As per the findings of the KAP survey on HIV/AIDS
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings |  |  |  | Yes | 1 | N/A |  | 21350 | 19722 | 1274 un enployed graduates were reached by HIV/AIDS education during the graduates orientation programme held in the month of september as per the reports from the ministry of Labor.
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  | Yes | 1 | 0 | 2006 | 827 | 717 | The reports are same as the previous quarter as the budget for Q9 was not available to conduct the additional trainings
1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education |  |  |  | No | 0 | 100 | 2009 | 180 | 269 | additional 200 transport workers were reached with HIV education during the reporting quarter
1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) |  |  |  | Yes | 1 | 0 | 2006 | 30 | 79 | 79 most at risk indivuduals have been reacehed with educational materials in this reporting quarter.
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  | No | 1 | 6000 | 2006 | 10000 | 4388 | There was delay in signing the MOU with the Royal Bhutan Army for the phase 2 and this hampered the implementation of the activties. The focal person from the Royal Bhutan Police was out of station and this has resulted in back log of activties. The results reported are same as the previous quarter.
1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  |  |  | Yes | 2 | 500 | 2005 | 7000 | 5004 | The results reported are same as the previous quarter, the focal person from dratshang was out of station during the reporting period.
1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results |  |  |  | No | 2 | 1500 | 2005 | 26800 | 31979 | A total of 2182people have been conseled and tested incuding the provision of results this quarter.
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment |  |  |  | No | 2 | 25%(19) | 2006 | 50 | 56 | 10 additional HIV patient have been put on ART this quarter
1

## PR_Section 1A & 1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: | 11
iv. Overall evaluation of performance
Due to the delayed disbursement and late signing of the phase 2 agreement than agreed earlier the performance of both PR and SR is rated satisfactory.
v. Planned changes in the program, if any.
Not major planned changes in the activties seen except for the fact that with the writtten approval of the Global Fund some savings were identified to fiance the ongoing activties of the phase 1 which were not budgeted in the pashe2.
vi. Other program results, success stories, issues or lessons learned
During the reporting period , The National HIV/AIDS Control Programme started prevention activities focussing on the Most at Risk Population and the drivers of the HIV epidemic , there was also an increase in the no of people availing VCT services compared to the previous quarters.
B. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? (Yes/No) | PR Comments
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  |  |  | Yes | M&E officer has been recruited at the Project Management Unit to monitor the the GF activties for a duration of 3 years starting April 2010
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country |  |  |  | Yes | PMT has now standardized the reporting format for GF HIV reporting ans trained all the SR's . There are still more reporting formats which needs to be standardised
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  |  |  | No
The Principal Recipient sahall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. |  |  |  | Yes | Updated PSM plan has been developed and submitted to GF
The written approval of the Global Fund of the updated PSM plan |  |  |  | No | PSM plan has been submitted since June 2010 but written approval has not yet been accorded
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  |  |  | Yes | MOH has been designated as the new PR after the signing of the phase 2 agreement of the project.
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of 1,program officer, 2 M&E Coordinator, 3 Finance Officer/Accoutant 4, Project Manager 5 Procurement & Supply management specialist |  |  |  | Yes | The PMU established to faciliate the coordination of GF grant have team comprising of Project Coordinator, M&E officer, 2 finance personel , 1 administrative assiatnt , 1 procurement officer dealing with the procurement of health products to manage the grants
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  |  |  | Yes | The detailed quarterly budget for year 4 &5 has been delivered and been approved by GF
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  |  | In Progress | The PQR shall be updated as & when the products are procured
Select

## PR_Section 1C
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: | 11
C. PROGRAM EXPENDITURES
All amounts are in: USD | Budget for Reporting Period | Actual for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | Reason for Variance | 12369.31
1. Total actual expenditures vs. budget | 159161 | 169161.09 | -10000.09 |  | 1994385.5 | 1482406.18 | 511979.32 |  |  | 12369.31
1a. PR's total expenditures | 98603.5 | 22533.98 | 76069.52 | Most of the planned activties such as training and procurement could not be carried out due to the delay in disbursement of the funds from the Global Fund. | 1098967.5 | 734914.34 | 364053.16 | The cumulative variance is due to the non implementation of Q9 & Q10 planned activties due to non reciept of phase 2 funds. Though the Phase 2 started from Febraury 2010 , there was delay in grant negotiation and also disbursement of DR and in the process two quarters activties are now back logged .
1b. Disbursements to sub-recipients | 60557.5 | 146627.11 | -86069.61 | The huge chunk of disbursement of USD 68,000 for celebrating world AIDS day for 1st December 2010 was released in advance in this quarter to ensure the funds arrive on time and activties are implemented. The budget for Q12 was released in this quarter. | 895418 | 747491.84 | 147926.16
2. Health product expenditures vs. budget (already included in '"Total actual" figures above) | 62169 | 0 | 62169 | The PSM Plan has not yet been approved and also the procurment funds have not been released, no procurment took place during this reporting period. | 264000 | 123807.6 | 140192.4 | The Procurements could not be made due to non availability. Some of the items have been procured but the payments were not made due to delayed DR
2a. Pharmaceuticals | 40419 | 0 | 40419 |  | 49500 | 16927 | 32573
2b. Health products, commodities and equipment | 21750 | 0 | 21750 |  | 214500 | 106880.6 | 107619.4
Program expenditures were used for the procurement of health products: |  |  |  | No
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | Yes

## PR_Section 2
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  |  | Cycle: |  | Semester | Number: | 4
Disbursement Request - Period Covered: |  |  | Beginning Date: |  | 2010-11-01 | End Date: | 2011-04-30
Disbursement Request - Number: |  |  | 5
Section 2: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 6 from Cash Reconciliation section of the period covered
by the previous Progress Update): | [10 empty] | 416.58
Add: | 2. Cash disbursed to the PR by the Global Fund during the period covered by this progress update: (1) | [8 empty] | 428192.77
| 3. Interest received on bank account and other income received: | [8 empty] | 0 | 428192.77
Less: | 4. Total program expenditures during period covered by Progress Update (value entered in Section 1C. "Total actual expenditures"): | [8 empty] | 169161.09
| 5. Other expenditures incurred (bank fees, other transaction costs, net exchange rate gains/losses): | [9 empty] | 169161.09
6. Cash Balance: End of period covered by Progress Update: | [10 empty] | 259448.26
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update (2, 3):
7. Period beginning date: |  | 2010-11-01 |  | end date: | 2011-04-30 |  | amount as originally budgeted: | 219559 | forecasted amount: | 473320.11
8. Additional quarter
(cash "buffer") beginning date (4): |  | 2011-05-01 |  | end date: | 2011-07-31 |  | amount as originally budgeted: | 244572 | forecasted amount: | 244572 | 717892.11
Please explain any variance between the forecasted amounts and the amounts as originally budgeted |  |  |  | All the backlog activties from the q9, q10 & Q11 of phase 2 was moved to the subsequent quarters.
\
Less: | Cash Balance: End of period covered by Progress Update (number 6 above): | [8 empty] | 259448.26
| 9. Cash received from the Global Fund after the period covered by Progress Update or cash "in transit" (5) (if any): | [8 empty] | 0 | 259448.26
10. PR's Disbursement Request from the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [10 empty] | 458443.85
11. Does the PR's Disbursement Request include funds for health product procurement? | [5 empty] | Yes
12. Exchange Rate (used to translate local currency into USD): |  |  |  | 46.74
Footnotes:
1 - Gross amount disbursed by the Global Fund (i.e., any associated bank fees or transaction costs should not be deducted in this line, but included in line 5. “Other expenditures incurred”
2 - Expenditures listed must be covered by current budget forecasts
3 - Total forecasted net cash expenditures should include any commitments made in the period covered by the Progress Update that are forecasted to be spent during the period covered by the Disbursement Request
4 - Additional period (cash "buffer"): disbursement of funds for Q9 is contingent upon the signing of Phase 2 or as otherwise stipulated per implementation letter
5 - “Cash in transit” includes amounts disbursed but not yet received by the PR and disbursement requests not yet approved by the Global Fund.

## PR_Section 3
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Bhutan
Disease: | HIV/AIDS
Grant number: | BTN-607-G03-H
Principal Recipient: | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: | 2008-02-01
Currency: | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: | 11
DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 4
Progress Update - Period Covered: | Beginning Date: | 2010-11-01 | End Date: | 2011-04-30
Progress Update - Number: | 5
Section 3: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from Section 2.B line 10, in: USD): |  | 458443.85
2. Amount requested in words (in: USD): |  | Four hundred fifty eight thousand four hundred forty three and eighty five cents
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name: | Tandin Lhamo
Title: | Programme Officer
Date and Place:
Bank Account Details (if different than the account details specified on block 9 of the face sheet of the Grant Agreement) |  |  |  |  | Comments (e.g. changes to PR's bank account details, "split disbursements" to the PR and third parties etc.):
Owner of Bank Account:
Account Title:
Account number:
Bank name:
Bank address:
Bank SWIFT Code:
Bank Code:
Routing instructions:

## LFA_Cover page
LFA On-going Progress Review and Disbursement Recommendation
Instructions to the LFA for completing the LFA On-Going Progress Review and Disbursement Recommendation
The Principal Recipient (PR) is required, through the On-Going Progress Update and Disbursement Request, to:
1. Provide past expenditure and programmatic performance information for the Reporting Period just ended; and
2. State its cash requirement for meeting on-going program expenditures.
The LFA is required, using this form, to verify progress and make recommendations on the cash amount requested.
Progress Update
The PR will report past expenditure and programmatic performance information for the Reporting Period just ended as well as progress made towards fulfillment of any conditions precedent/special conditions. The LFA is required to review and verify this information and, in accordance with the information fields set out in this form, to comment on current and cumulative progress.
Disbursement Recommendation
The PR will normally make a disbursement request from the Global Fund covering the PR's cash requirements for one Reporting Period, plus one additional quarter as a cash buffer, to ensure that the PR has adequate cash on hand for program expenses at all times. The Reporting Period for which the Disbursement Request is being made should be the period that immediately follows the Reporting Period covered by the PR's progress update (as explained above). The LFA is required to verify the PR's Cash Reconciliation and to ensure that the cash request is properly calculated. The LFA should recognize that the cash request should be based on the most up-to-date budgets for the relevant periods which the LFA should review for reasonableness.
Documents to be attached/retained
When submitting this form to the Global Fund, the LFA should attach the following:
1. PR On-Going Progress Update and Disbursement Request form (by email with originals to follow by mail)
2. Any supplementary information, as appropriate, to inform the Global Fund of the review and verification process and to support the review and recommendation
The LFA should also retain the PR's detailed Statement of Uses of Funds (Cash Flow Statement) for the Reporting Period just ended as well as any additional relevant documentation of verifications performed (to be provided upon request by the Global Fund).

## LFA_Section 1A (1)
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office: |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  | Bhutan | [10 empty] | Bhutan
Disease: |  | HIV/AIDS | [10 empty] | HIV/AIDS
Grant Number: |  | BTN-607-G03-H | [10 empty] | BTN-607-G03-H
Principal Recipient: |  | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN | [10 empty] | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01 | [10 empty] | 39479
Currency: |  | USD | [10 empty] | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 11 | [7 empty] | Quarter | 11
Progress Update - Period Covered: |  | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31 | [7 empty] | 40391 | 40482
Progress Update - Number: |  | 11 | [10 empty] | 11
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 4 | [7 empty] | Semester | 4
Disbursement Request - Period Covered: |  | Beginning Date: | 2010-11-01 | End Date: | 2011-04-30 | [7 empty] | 40483 | 40663
Disbursement Request - Number: |  | 5 | [10 empty] | 5
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic and Financial Progress
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations | [9 empty] | 1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country | [9 empty] | 2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA | [9 empty] | 3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Intended Yearly Targets (from Attachment) | Actual Yearly Results (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on impact and outcome, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | <0.1% | N/A | PR On-site Visit | No change | This will be reported on completion of the sentinneal survey which is planned to be conducted on a yearly basis for 2010, 2011 & 2012.The PR has developed a surveillance strategy (draft) which will make it easier to compare with the baseline information of 2007. The PR is also exploring for funds for this activity without which the PR may not be able to undertake this activity. | Impact | Percent of women and men aged 15-49 who are HIV infected | <0.1% | N/A
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  |  | <0.1% | N/A | PR On-site Visit | No change | This will be reported on completion of the sentinneal survey which is planned to be conducted on a yearly basis for 2010, 2011 & 2012. The PR has developed a surveillance strategy which will make it easier to compare with the baseline information of 2007. The PR is exploring for funds for this activity without which the PR may not be able to undertake this activity. | Impact | Percentage of uniformed personnel who are HIV infected | <0.1% | N/A
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | N/A | N/A | PR On-site Visit | N/A | This will be reported after the second KAP survey which will be done in the fifth and last year of the project. The baseline data as per the 2009 KAP survey shows that 47 % of out of school youth aged 15-24 years reported the consistent use of condoms. | Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year | N/A | N/A
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | NA | N/A | PR On-site Visit | N/A | This will be reported after the second KAP survey which is will be done in the fifth and last year of the project. Baseline data from the 2009 KAP survey shows that 53 % of uniformed personnel reported consistent use of condoms with non regular sexual partner. | Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year | NA | N/A
Select
Select
Select
Select
Select
Select
Select
Select

## LFA_Section 1A (2)
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: |  | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: |  | 11
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Intended Targets to date (from Attachment) | Actual Results to date (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on progress to date, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
1 | Prevention: BCC - community outreach | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | 44000 | 24106 | SR On-site Visit | No change | Cumulative actual/target 24,106/44,000, Cumulative achievment: 55 % This is a top ten indicator There is no progress with regard to this indicator. In this period the SR reported that a number of young people in schools was reached with life skills based HIV/AIDS education, however the reports were not complete and could not be compiled to provide the total number reached. Therefore, the number remain same as reported in Q10 (24,106). A total of 144 schools with standards 7-12 are being targeted for this indicator. Reporting from the schools to the Department of Youth and Sports (DYS), Ministry of Education who is the SR for this activity continues to be haphazard and not on time. Similarly the reporting format agreed upon by the PR and SR is not being used, citing difficulty in using the format by the SR. Reporting from SR to the PR is also not timely, despite the recruitment of an additional M&E person in the Project Management Unit in April 2010. Further, the focal person for the activity in the DYS is currently on leave (at the time of preparing this report and LFA could not meet her) and therefore the SR will be updating this result in the next quarter when all the reports from the schools will be compiled. | 1 | Prevention: BCC - community outreach |  | 44000 | 24106
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | #REF! | #REF! | #REF! | 589 | 269 | PR On-site Visit | No change | Cumulative actual/target: 269/589; Achievement: 46 % There is no progress in this indicator either. No teachers have been trained in this quarter because of delay in receiving disbursements. The actual result is 269 which is same as in Q10. The SR has completed training teachers in three districts and will be reaching more teachers in the coming quarter as SR has planned to conduct the training during the winter vacation so that the training does not disturb the academic session. | 1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | 589 | 269
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | #REF! | #REF! | #REF! | n/a | 45 | PR On-site Visit | No change | No target has been set for this indicator. The only target set is at 60% to be reported by quarter ending in October 2012, which should result from another KAP survey in 2012. The result is the same as for the previous quarter and it is based on the KAP survey report 2009 which shows that 45 % of young people in school correctly identify ways of preventing HIV AIDS. This is much lower than that reported for university students and out of school youths ( >60 %) however the criteria used in the present survey was more stringent (know all five indicators as used in the survey) and this could be the reason for the low knowledge among in school youth. This result will be reported at the end of the project in year 5. | 1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | n/a | 45
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | #REF! | #REF! | #REF! | 21350 | 19722 | PR On-site Visit | No change | Cumulative actual/target19,722/21,350, Cumulative achievment: 92%. This is one of top ten indicators The Ministry of Labour and Human Resources (MoLHR), the SR for this activity conducted the National Graduate Orientation Program (NGOP) in October 2010 and a half day program was organized in partnership with the National AIDS Control Program to reach 1,274 new graduates with information on HIV/AIDS. The NGOP is an annual program organized by the goverment to enable all the goverment agencies to meet and inform the new graduates about their policies and opportunities. It is the ideal forum to reach and inform young people about HIV/AIDS. The MoLHR is the only SR using the new SR reporting format. The focal person has left for further studies at the Masters level and therefore the replacement may face some difficulty in using the format, unless the PR conducts an orientation. In addition the Non Formal Education Division of the MoE, another SR also conducts similar activities however it is not reporting on the results. | 1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | 21350 | 19722
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | #REF! | #REF! | #REF! | 827 | 717 | SR On-site Visit | No change | Cumulative actual/target 717/827, Cumulative achievment: 87 %. This is one of the top ten (training) indicators A total of 250 new NFE instructors were trained till this quarter using UNICEF funds, as the fund disbursements from GF was delayed. This activity was not reported by the SR to the PR because only GF funded results were being reported. There are in total only 715 existing NFE centers and so the cumulative total represents instructors which have been trained including those who have left the system. | 1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | 827 | 717
1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education | #REF! | #REF! | #REF! | 180 | 269 | PR On-site Visit | No change | Cumulative actual/target 269/180, Cumulative achievment: 149 % In this quarter 200 transport workers were reached with HIV education. This is a half day sensitization program and has been carried out in Thimphu and Phuntsholing by health workers at the Health Information Service Center (HISC), located right next to the major Taxi stand. LFA verified the training report of the NACP. It is done in collaboration with the Road Safety and Transport Authority (RSTA). The transport workers consisted of Taxi drivers and truckers who are categorized as Most-at-risk-population (MARP) in Bhutan for HIV. | 1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education | 180 | 269
1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) | #REF! | #REF! | #REF! | 30 | 79 | PR On-site Visit | No change | Cumulative actual/target 79/30, Cumulative achievment: 263 % In this quarter 79 most at risk individuals were reached with HIV education material consisted of pamphlets, audio tapes and musical CD's featuring songs on HIV/AIDS. The most at risk individuals consisted of young boys and girls working in dance bars and young people visiting the Drop in center at Thimphu. They were reached through the HISC center health staff and also by staff at the drop in center in Thimphu, both of which are located in the same building. While the drop in center is an ongoing program, reaching out to Drayang girls with education material is a out reach activity of the HISC center. It will be difficult to reach the specified MARP's because they are hidden and there has been no concrete data on primary substance users (IDU's) and sex workers. The only available reports suggest that girls that sing and dance in bars (Drayangs) could potentially be working as sex workers or be sexually exploited. This topic was debated nationally with the goverment considering closing down the Drayangs while the owners/employees refuting the sexual charges made at them. The Parliament had deferred making any decisions regarding legislations however had ordered indivdual districts to make decisions whether to allow Drayangs to operate in their respective districts. | 1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) | 30 | 79
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | #REF! | #REF! | #REF! | 10000 | 4388 | PR On-site Visit | 4361 | Cumulative actual/target 4,361/10,000, Cumulative achievment: 44 % . This is one of the top ten indicators No awareness workshops were carried out with the police because of delay in recieving disbursements. The variance is due to arithmatical error by the PR as reported in the last quarter. This activity has also been carried out with Royal Bhutan Army (RBA) personel and their families. However, there has been no reports. Reporting by the RBA who carry out the activity using their own medical doctors has been poor as they have failed to submit a single report. There is very limited oversight performed by the PR on this activity especially with regards to RBA. | 1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | 10000 | 4388
1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | #REF! | #REF! | #REF! | 7000 | 5004 | PR On-site Visit | No change | Cumulative actual/target 5,004/7,000, Cumulative achievment: 71 % . This is one of the top ten tindicators In this quarter no monks were reached with HIV/AIDS education though in last Qr. 720 monks were reached with HIV/AIDS education. There were no reports submited by the SR as the focal person is on leave and LFA was unable to contact him. This will be further reported in the next quarter. This activity is conducted by the Dratshang Lhentshog, an autonomous agency that administers and is the goverment arm that deals with monastic institutions in the country. The PR has provided very little oversight over the SR and reporting from the SR has not been timely. There are currently 5 religous personnel who have been detected with HIV and that is the reason for targetting this group. | 1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | 7000 | 5004
1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | #REF! | #REF! | #REF! | 26800 | 31979 | PR On-site Visit | No change | Cumulative actual/target 31,979/26,800, Cumulative achievment: 119 % . This is one of the top ten tindicators In this quarter 2,182 people were counselled and tested during this quarter giving the cumulative figure of 31,979. The target for this quarter has been achieved. This is a routine activity carried out at all hospitals including the Health Information Service Centers (HISC) and is routinely reported by all VCT health centers. The only concern about this indicator has been whether this figure represents those that have been provided results as stated in the indicator. PR should ensure that this indicator is reported correctly. | 1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | 26800 | 31979
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | #REF! | #REF! | #REF! | 60 | #REF! | PR On-site Visit | 56 | Cumulative actual/target 56/60, Cumulative achievment: 93 % This is one of the top ten tindicators In this quarter, 10 more HIV positive people were put on treatment making the cumulative total at 56. (Quarterly report submittted by the health centers). The program continues to use the old standard of starting HAART with a CD4 count of 200. A team of doctors have returned from Thailand after being trained on the new recommendations of starting with CD4 350. The national treatment protocol is not been finalised yet although it was supposed to have been put in place. Using the new criteria it is expected that many more HIV positive people will be on HAART. This is of concern because the PR does not have a plan in place to meet the increased demands for anti retroviral medicines. The procurement plan (including purchase of medicines) has not been approved by the GF. | 3 | #REF! | #REF! | #REF! | #REF!
1 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 1
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 | [6 empty] | 56 |  |  |  | 0 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | 50 | 56
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!

## Annexure A
Annexure A: Indicator Rating
Indicators | Top 10 | Training | Target | Results | % Achievement
Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) | Top 10 |  | 44000 | 24106 | 54.79% | Top 10 |  |  | All Indicators |  | Training Indicators
Number of teachers trained on life skill based HIV/AIDS education |  | Training | 589 | 269 | 45.67% | 54.79% | 82% | B1 | 85% | B1 | 46% | 74% | B1
% of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | Top 10 |  | na | 45 | no target set | 92.37% |  |  |  |  | 87%
People reached by HIV/AIDS education in out-of-school settings | Top 10 |  | 21350 | 19722 | 92.37% | 92% |  |  |  |  | 120%
Non Formal Education Instructors trained to provide HIV out-of-school education | Top 10 | Training | 827 | 717 | 86.7% | 86.7% |  |  |  |  | 44%
Number of Transport workers reached with HIV education |  |  | 180 | 269 | 120% | 43.61% |  |  |  |  | 71%
Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) |  | Training | 30 | 79 | 120% | 71.49%
Number of uniformed personnel and their families participating in HIV Awareness workshops | Top 10 | Training | 10000 | 4361 | 43.61% | 119.3%
Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | Top 10 | Training | 7000 | 5004 | 71.49% | 93.33%
Number of persons counseled and tested including provision of results | Top 10 |  | 26800 | 31979 | 119.3% | 74% (Training Indicators)
Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | Top 10 |  | 60 | 56 | 93.33%

## LFA_Section 1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: | 11
B. LFA COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? | LFA Analysis (this should not be a “Copy and Paste” of the comments provided by the PR)
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  |  |  | Yes | PR has recruited an M & E Officer who is attached with PMT to look after M & E component of all three diseases | Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country |  |  |  | Yes | PR has developed new reporting format and guidelines to be used by SRs to report the quarterly report. However, the reporting format agreed upon by the PR and SR is not being used, citing difficulty in using the format by the few SRs. | Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  |  |  | No | Not done since PR could not recruit M& E Consultant so far due to no candidate responding to advertisement. | Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units
The Principal Recipient sahall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. |  |  |  | Yes | Updated PSM plan was submitted to GF for approval. | The Principal Recipient sahall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund.
The written approval of the Global Fund of the updated PSM plan |  |  |  | No | PR has submitted the revised PSM Plan to GF and there are certain clarification required by GF which PR has not submitted and thus approval of PSM Plan is delayed. However, PR is in process of submitting the clarification. | The written approval of the Global Fund of the updated PSM plan
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  |  |  | Yes | The PCM members during its 14th PCM meeting endorsed that hereafter the Ministry of Health shall be the PR and is responsible for implementation of the program. The Phase 2 documents were also signed both by GNHC and MoH that reflected this arrangement | The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of 1,program officer, 2 M&E Coordinator, 3 Finance Officer/Accoutant 4, Project Manager 5 Procurement & Supply management specialist |  |  |  | Yes | Currently, Mr Tandin Dorji is the overall Program Manager for TB and HIV program. Mr. Sonam Wangdi and Mr Kencho are the Program Officer. Mr Ugyen Tshewang is the Finance Officer and Mr Dinash Rai is working as an Accountant. There is one M & E officer (newly recruited) who will be looking after M & E component of all three diseases. Mr Tandin Dorji, Chief Program Officer of DVED is looking after PSM. | The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of 1,program officer, 2 M&E Coordinator, 3 Finance Officer/Accoutant 4, Project Manager 5 Procurement & Supply management specialist
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  |  |  | Yes | PR submitted the detailed quarterly budget for Year 4 and 5 including detailed breakdown per cost categories and summary budget to LFA on 17 October 2010. LFA verified the submission and was submitted to GF on 18 October 2010 and GF approved the Year 4 and 5 budget including detailed breakdown on 22 October 2010. | No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums.
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  |  | N/A | Since GF has not approved the PSM Plan, no procurement budget were released, PR has therefore has not procured any health products and there is no update on PQR database. | Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting.
Select
Select
Select

## LFA_Section 1C
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: | 11
C. PROGRAM EXPENDITURES
All amounts are in: Please select currency on Page 1 | Budget for Reporting Period | Actual for Reporting Period1 | Variance | LFA Verified (Y/N) | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR) | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR)
1. Total actual expenditures vs. budget | 159161 | 169161.09 | -10000.09 |  |  | 1994385.5 | 1482406.18 | 511979.32 | v | 159161 | 169161.09 | -10000.09 | 1994385.5 | 1482406.18 | 511979.32
1a. PR's total expenditures | 98603.5 | 22533.98 | 76069.52 | Yes | The absorption rate at Q11 end was 106% of the corresponding budget. This is due to disbursement of funds to the SRs including for back log activities. Other variation came from the disbursement of USD 68,800 to the SR- NFE (SDA 1.2.3 - Community activities by youth NFE learners), which is originally planned in Q12. The SR brought forward this activity to Q11 for early implementation. Further analysis of expenditure shows that the budgeted expenditure for Q11 constituted only 9% (USD 15,801.26) of the reported expenditure of USD 169,161.09. More than 50% (USD 85,279.83) of the expenditure pertains to back log activities of Q9 and Q10. As mentioned above, 40% of the expenditure consists of the release to the SR as the activity was brought forward from Q12 amounting to USD 68,800. Detailed analysis is shown in Annexure -C. However, the absorption rate of the PR was only 23% of total corresponding budget USD 98,603.50. The low absorption rate, in the opinion of the LFA, was partly due to shortage of fund as the PR received first Phase 2 disbursement on 23 August 2010. Expenditure figures between the PR and SR is being reviewed and rectified accordingly. | 1098967.5 | 734914.34 | 364053.16 | The overall cumulative burn rate (PR & SR) at Q11 end was 74%. However, closer look into the PR performance reveals that the cumulative burn rate up to Q11 end was only 66% and the cumulative variance is 34% (USD 367,376.33). Main reason stated by the PR was the non availability of fund during the first two quarters into the second Phase, which impeded implementation activities as planned. The LFA observed that the whole of Q9 budget USD 65,008 was not implemented, and in case of Q10 budget, out of USD 82,954.00 only USD 4,306.74 (5%) pertaining to SDA code 1.4.1, 1.7.1 and 1.8.1 were implemented. With regard to Q11 budget the PR was able to implement only 23% of the budget (USD 22,533.98 out of the total budget USD 98,603.00) as the disbursement was received towards the end of August (23 August 2010). These implemented activities relate to SDA code 1.4.1, 1.4.2, 1.71., 2.3.1, 2.2.6, 2.2.3 respectively. However, it may be stated that while the PR awaited Phase 2 approval from the GFATM during the entire period from Q9 and Q10, they implemented Phase 1 activities as approved by the GFATM. Out of the total expenditure reported up to Q11 end USD 467,910.82, 63% (USD 294,097.18) pertains to Phase 1 activities that were implemented during Q9 and Q10. The LFA reviewed and rectified the expenditure figures reported by the PR. | 98603.5 | 22533.98 | 76069.52 | 1098967.5 | 734914.34 | 364053.16
1b. Disbursements to sub-recipients | 60557.5 | 146627.11 | -86069.61 | Yes | The burn rate of SRs was 242% in Q11. This is because the disbursement to SRs exceeded budget by 142%. The total expenditure amounted to USD 146,627.11 out of the total budget provision of only USD 60,557.50. This is mainly due to releases made to SRs to implement back log activities and also Q12 budget USD 68,800 for NFE activities brought to Q11 for early implementation. Detailed analysis is shown in Annexure -C. Expenditure figures between the PR and SR is being reviewed and rectified accordingly. | 895418 | 747491.84 | 147926.16 | The cumulative absorption rate of the SRs at Q11 end was 84% of the corresponding budget. The cumulative variance works out 16% amounting to USD 144,243.53. The high absorption rate achieved was mainly due to huge disbursement made to SRs during Q11 after receiving fund from the GF. Out of the total budget provision of USD 60,557.50 the PR disbursed USD 146,627.11 to SRs in Q11. The disbursement includes USD 68,800.00 pertaining to Q12 activities brought forward in Q11 - Community Activity by Youth NFE learners (SDA 1.2.3). However, out of eight SRs, Department of Youth Services (DYS) did not implement budget from Q9-Q11, which amounts to USD 92,220.00 followed by RBP/RBA USD 36,585 and Monastic Body USD 22, 804 respectively. | 60557.5 | 146627.11 | -86069.61 | 895418 | 747491.84 | 147926.16
2. Health product expenditures vs. budget (already included in "Total actual" figures above) | 62169 | 0 | 62169 | Yes | There were no procurement of Health Products expenditure in Q11. | 264000 | 123807.6 | 140192.4 | There were no procurement of Health Products expenditure in Q11. | 62169 | 0 | 62169 | 264000 | 123807.6 | 140192.4
2a. Pharmaceuticals | 40419 | 0 | 40419 | Yes | There were no procurement of Health Products expenditure in Q11. | 49500 | 16927 | 32573 | The required pharmaceuticals have been procured through World Bank Funding. The amount represents saving. | 40419 | 0 | 40419 | 49500 | 16927 | 32573
2b. Health products, commodities and equipment | 21750 | 0 | 21750 | Yes | No procurement done under this category | 214500 | 106880.6 | 107619.4 | The variance pertains to the budget earmarked for purchase of Elisa Machines | 21750 | 0 | 21750 | 214500 | 106880.6 | 107619.4
Program expenditures were used for the procurement of health products: |  |  |  | No
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | N/A
1 If the LFA makes a correction to the actual expenditures for the reporting period, the LFA should also make a corresponding correction to the PR's requested amount in LFA Section 4.A.1

## Annexure B
Annexure-B
Cash Flow Statement - Q11 (August-October 2010)
Particulars
Cash Inflow
Disbursement received from GFATM | 428192.7706
Opening Cash in hand | 331.68
Opening Bank | 84.9
Total Inflow - A | 428609.3506
Cash Outflow
Actual expenditure for the period (PR) | 22533.98
Actual disbursement to SRs for the period | 146627.11
Total Outflow - B | 169161.09
Balance (A-B) | 259448.2606
Representation by
Balance at DPA | 204771.0182
Bank Balance at MoH | 54670.9991
Cash balance | 6.24
Total Fund at Q11 end | 259448.2573

## Annexure C
Annexure- C
Variance Analysis by Line items - Q11 (ASO-2010)
| Objectives / Service Delivery Areas (SDAs) |  | ASO-2010 |  |  |  | LFA Comments
|  | PR/SR | Budget | Expenditure | Variance | %
SDA 1.1: Providing life-skills-based HIV/AIDS education |  | DYS
1.1.1 | TOT on Life Skill Education in 3 regions (Western, Central,Southern ) - 5 days training program each for region | DYS | 10085 |  | 10085 | 100% | The PR could not implement the activity as planned because the Ministry of Education didn’t approve the release of teachers during the academic sessions. Therefore the training has been postponed to the next quarter (Q12).
1.1.2 | Support to TOT in the implementation of further training of teachers in their communities/districts (5-day training). |  | 21495 |  | 21495 | 100% | The TOT program is being postponed to Qtr 12, and the PR plans to conduct the support training only in Qtr13.
| Subtotal SDA 1.1 |  | 31580 | 0 | 31580
SDA 1.2: Providing life-skills-based HIV/AIDS education |  |  |  |  | 0
1.2.1 | Development & Printing of educational materials(TLM- teaching learning materials) | NFE |  | 5003.24 | -5003.24 |  | Q9 budget implemented in Q11. The original budget provision was USD 5000, hence no major variance observed.
1.2.2 | Training of Teachers/Principals | NFE |  | 37159.99 | -37159.99 |  | Q9 & Q10 budget implemented in Q11. The original budget provision was USD 18,580 in each Qtr. hence no major variance observed.
1.2.3 | Community activities by youth NFE learners | NFE |  | 68800 | -68800 |  | Q12 budget implemented in Q11. The budget provision is USD 68,800.
1.2.5 | Refresher ToT for Vocational Centre teachers | MoLHR |  | 5659.99 | -5659.99 |  | Q9 budget implemented in Q11. The original budget provision was USD 5660, hence no major variance observed.
1.2.6 | Sensitization of unemployed youths and job seekers during the job fairs and NGOP | MoLHR | 6960 | 6956.69 | 3.31 | 0.04756% | The variance is immaterial in the opinion of the LFA.
| Subtotal SDA 1.2 |  | 6960 | 123579.91 | -116619.91
SDA 1.3: Reaching youth through the private sector |  | BCCI |  |  | 0
1.3.2 | Printing of education materials and products |  |  | 3438.94 | -3438.94 |  | Q9 budget implemented in Q11. The original budget provision was USD 5000. The difference represents saving USD 1561.06
1.3.3 | Ex-country training for the focal person on HIV programming |  |  | 3487.38 | -3487.38 |  | Q9 budget implemented in Q11. The original budget provision was USD 3610, hence no major variance observed.
| Subtotal SDA 1.3 |  | 0 | 6926.32 | -6926.32
SDA 1.4: Establishing youth-friendly health services in 30 hospitals |  | NACP |  |  | 0
1.4.1 | Training/refresher of staff about youth-issues |  | 6780 | 5283.74 | 1496.26 | 22.07% | The activity has been completed, the balance amount represents saving.
1.4.2 | Telephone line charges |  | 474 | 966.04 | -492.04 | -103.8% | The expenditure includes payments due in Q10.
1.4.3 | Ex-country training for Youth-hotline staff |  | 8680 |  | 8680 | 100% | Activity postponed to Q12 due to late receipt of disbursement from the GFATM.
| Subtotal SDA 1.4 |  | 15934 | 6249.78 | 9684.22
SDA 1.5: Intensifying HIV prevention among 10,000 uniformed personnel and their families |  | RBG/RBP |  |  | 0
1.5.3 | Sensitization of staff at different levels by RBP |  | 2518 |  | 2518 | 100% | The activity could not be conducted as the whole police staffs were engaged in awareness campaign regarding youth gang issues in Bhutan.
1.5.5 | Awareness program in prisons |  | 3600 |  | 3600 | 100% | The activity was postponed to the next quarter as the prisoners were engaged in the religious discourse program during the quarter
1.5.7 | Attend regional GFATM meetings (for focal persons) |  | 5000 |  | 5000 | 100% | No regional meeting scheduled during the qtr.
| Subtotal SDA 1.5 |  | 11118 | 0 | 11118
SDA 1.6: Increasing HIV awareness among members of faith-based organizations |  | Dratshang |  |  | 0
1.6.3 | Exchange programme |  | 10900 |  | 10900 | 100% | Activity postponed to q12 as the focal person for GF was out of station most of the time during the quarter.
| Subtotal SDA 1.6 |  | 10900 | 0 | 10900
SDA 1.7: Providing services for CSWs, IDUs, and MSMs through NGOs |  | NACP |  |  | 0
1.7.1 | IDU outreach services through sub grantee community organization |  |  | 106.97 | -106.97 |  | Q9 & Q10 budget implemented in Q11. The original budget provision for Q9 & Q10 was USD 8000, hence the PR did not implemented the budget as planned due shortage of fund.
| Subtotal SDA 1.7 |  | 0 | 106.97 | -106.97
SDA 1.8: Expanding prevention packages to the BHU and the community level with CT |  | NACP |  |  | 0
1.8.1 | Rent two VCT centres |  | 999 |  | 999 | 100% | Activity was delayed because of non-availability of suitable house for rent in the required location (urban setting).However the PR did rent a house December. The expenses will be incurred from Q12.
1.8.3 | Test kits and vacutainers |  | 21750 |  | 21750 | 100% | Disbursement for procurement was not made as the PSM plan is under reviewed by the Global Fund.
| Subtotal SDA 1.8 |  | 22749 | 0 | 22749
SDA 1.9 IEC activities |  | ICB |  |  | 0
1.9.3 | Printing of materials for vulnerable groups |  |  | 2620.88 | -2620.88 |  | Q10 budget implemented in Q11. The original budget provision was USD 10,000.
| Subtotal SDA 1.9 |  | 0 | 2620.88 | -2620.88
SDA 2.1: Strengthening STI/HIV/AIDS pre-service training at the Royal Institute of Health Sciences. |  | RIHS |  |  | 0
2.1.2 | Faculty development - continuning education for lecturers on STI & HIV/AIDS |  |  | 9000 | -9000 |  | Q10 budget implemented. The budget provision was USD 9000, hence no variance.
2.1.4 | Refurbishment of classrooms |  |  | 4500 | -4500 |  | Q10 budget implemented. The equal amount was budgeted, hence no variance.
| Subtotal SDA 2.1 |  | 0 | 13500 | -13500
SDA 2.2: Strengthening national capacity for programme monitoring and evaluation |  | NACP |  |  | 0
2.2.1 | Hire M&E consultant in MOH |  | 1950 |  | 1950 | 100% | The required consultancy was provided by the GFATM secretariat through GMS, hence no expenditure was incurred against this budget.
2.2.3 | Undertake supervision and monitoring visits |  | 1251 | 946.73 | 304.27 | 24.32% | Quarterly budget USD 1251 each was provided, but the PR could not implement theplanned activities in Q9 and Q10 due to shortage of fund. However, the PR implemented the activity in Q11 but partially completed also partially due to shortage of fund, hence 24% variance. As the budget is regular quarterly activities, the PR expects to make iup the shortfall n the subsequent quarters.
2.2.4 | Send program staff to international forum for information exchange and attend regional meetings of GFATM |  | 8100 |  | 8100 | 100% | No regional meeting scheduled during the qtr.
2.2.6 | Quarterly meeting of stakeholders |  | 270 | 928.06 | -658.06 | -243.7% | The expenditure includes Q9, Q10 and Q11 activities implemented, which was budgeted USD 270 per quarter (total USD 810). The actual variance works out to USD 118 (15%).
| Subtotal SDA 2.2 |  | 11571 | 1874.79 | 9696.21
SDA 2.3: Strengthening the management and technical capacity of the NACP |  | NACP |  |  | 0
2.3.1 | Diploma in finance management of HIV/AIDS project |  |  | 14302.44 | -14302.44 |  | Q9 budget implemented. The budget provision was USD 11,210. The expenditure exceeded budget by USD 3,092 (27.5%)..
| Subtotal SDA 2.3 |  | 0 | 14302.44 | -14302.44
SDA 2.4: Building the capacity of non-govermental sectors as partner in the national HIV/AIDS response |  | NACP |  |  | 0
2.4.1 | Exchange programme for PLHA |  | 7930 |  | 7930 | 100% | The activity was delayed as the PR was not able to recruit PLHA in Q11 as planned. The PR is currently working on this which will materialize in Q12.
| Subtotal SDA 2.4 |  | 7930 | 0 | 7930
SDA 3. Ensuring care & treatment |  | NACP |  |  | 0
3.1 | Procurement of ARVs |  | 40419 |  | 40419 | 100% | Disbursement for procurement was not made as the PSM plan is being reviewed by the Global Fund.
| TOTAL PROGRAM COSTS |  | 159161 | 169161.09 | -10000.09
Analysis
|  | USD | USD | Percentage
| Budget execution | Budget | Expenditure
| Overall burn rate for Q11 | 159161 | 169161.09 | 106.3%
Expenditure analysis in Q11:
| Budgeted Expenditure | 159161 | 15081.26 | 8.915%
| Expenditure- back log activities implemented |  | 85279.83 | 50.41%
| Q 12 Activities implemented |  | 68800 | 40.67%
| TOTAL | 159161 | 169161.09 | 100%
Implementing Agency
| Expenditure by the PR | 98603 | 22533.98 | 22.85%
| Disbursement to the SRs | 60558 | 146627.11 | 242.1%
| TOTAL | 159161 | 169161.09

## Annexure D
Annexure D: Forecast budget
| Service delivery areas | Qtr 9 | Qtr 10 | Qtr 11 | Qtr 12 | PR Forecast amount | LFA forcast Amount | LFA Comments
1.1.1 | TOT on Life Skill Education in 3 regions (Western, Central,Southern ) - 5 days training program each for region | 10085 |  | 10085 | 10085 | 30255 | 30255 | back log activities of Q9 and Q11
1.1.2 | Support to TOT in the implementation of further training of teachers in their communities/districts (5-day training). |  | 21495 | 21495 |  | 42990 | 42990 | back log activities of Q10 & Q11
1.1.3 | Purchase of Television & DVD for the schools. - 30 sets required | 12000 |  |  |  | 12000 | 12000 | back log activities of Q9
1.1.4 | Purchase of sound syetem (Ahuja) | 5850 |  |  |  | 5850 | 5850 | back log activities of Q9
1.1.5 | Purchase of LCD Projector with desktop computer | 4500 |  |  |  | 4500 | 4500 | back log activities of Q9
1.1.6 | Sound proofing of the Auditorium |  |  |  |  | 0 | 0 | back log activities of Q9
1.1.7 | Purchase of wall mounted projector scerr 119" | 450 |  |  |  | 450 | 450 | back log activities of Q9
1.1.8 | Purchase of Plasma TV | 3150 |  |  |  | 3150 | 3150 | back log activities of Q9
1.1.9 | Attend regional GFATM meetings | 2250 |  |  |  | 2250 | 2250 | back log activities of Q9
1.1.10 | Monitoring and evaluation |  | 860 |  | 860 | 1720 | 860 | Q10 budget excluded
1.2.3 | community activities by youth NFE Learners |  |  |  | 68800 |  |  | implemented in Q11
1.2.4 | Attend regional GFATM meetings | 2250 |  |  |  | 2250 | 2250 | back log activities of Q9
1.2.7 | Attend regional GFATM meetings | 2250 |  |  |  | 2250 | 2250 | back log activities of Q9
1.3.1 | Sensitization of private sectors in 5 towns |  | 3450 |  |  | 3450 | 3450 | back log activities of Q9
1.3.4 | Ex-change of experience among private sectors |  | 2225 |  |  | 2225 | 2225 | back log activities of Q9
1.4.2 | Telephone line charges |  |  |  | 474 | 474 | 474
1.4.3 | Ex-country training for Youth-hotline staff |  |  | 8680 |  | 8680 | 8680 | back log activities of Q9
1.5.1 | Development and Printing of HIV information package | 3000 |  |  |  | 3000 | 3000 | back log activities of Q9
1.5.2 | Capacity building of women police volunteers | 4820 |  |  |  | 4820 | 4820 | back log activities of Q9
1.5.4 | Sensitization program for RBA & RBG | 2517.5 | 2517.5 |  |  | 5035 | 5035 | back log activities of Q9 & Q10
1.5.5 | Awareness program in prisons |  |  | 3600 |  | 3600 | 3600 | back log activities of Q10
1.5.7 | Attend regional GFATM meetings (for focal persons) | 5000 |  | 5000 |  | 10000 | 10000 | back log activities of Q9 & Q11
1.6.4 | Annual review meeting |  |  |  | 1860 | 1860 | 1860
1.7.1 | IDU outreach services through sub grantee community organization | 2000 | 6000 |  |  | 8000 | 8000 | back log activities of Q9
1.7.2 | SW outreach services through sub grantee community | 8000 |  |  |  | 8000 | 8000 | back log activities of Q9
1.8.2 | Procurement of computers & printers for the two VCT centers | 3982 |  |  |  | 3982 | 3982 | back log activities of Q9
1.8.1 | Rent two VCT centres |  |  |  | 999 | 999 | 999
1.8.3 | Test kits and vacutainers |  |  | 21750 |  | 21750 | 21750 | back log activities of Q10
1.8.4 | Procurement of CD4 reagenst |  | 13750 |  |  | 13750 | 13750 | back log activities of Q9
1.9.5 | Undertake supervision and monitoring visits |  |  |  | 450 | 450 | 450
2.2.1 | Hire M&E consultant in MOH |  |  |  | 1950 | 1950 | 1950
2.2.2 | Master in epidemiology | 25000 | 25000 |  |  | 50000 | 50000 | back log activities of Q9 & Q10
2.2.3 | Undertake supervision and monitoring visits |  |  |  | 1251 | 1251 | 1251
2.2.4 | Send program staff to international forum for information exchange and attend regional meetings of GFATM | 8100 |  | 8100 |  | 16200 | 16200 | back log activities of Q9 and Q10
2.2.6 | Quarterly meeting of stakeholders |  |  |  | 270 | 270 | 270
2.3.2 | Building a local pool of expertise in key technical areas |  | 15000 |  |  | 15000 | 15000 | back log activities of Q9
2.4.1 | Exchange programme for PLHA |  |  | 7930 |  | 7930 | 7930 | back log activities of Q10
3.1 | Procurement of ARVs |  |  | 40419.04 |  | 40419.04 | 40419.04 | back log activities of Q11
| TOTAL | 105204.5 | 90297.5 | 127059.04 | 18199 | 340760.04 | 339900.04
| Cash Disbursement Request | PR calculation | LFA calculation
| Backlog budget (Q9-11) | 322561.04 | 321701.04
| Forecast amount (Q12) | 18199 | 18199
| Total (Q9-12) | 340760.04 | 339900.04
| Q13 budget | 132560.07 | 132560.07 | Recommended the original budget for Q13
| Total (Q9-13) | 473320.11 | 472460.11
| Buffer Q14 budget | 244572 | 244572
| Total | 717892.11 | 717032.11
| Less cash balance | -259448.26 | -259448.26
| LFA Recommended DR | 458443.85 | 457583.85
Budget from Q9-Q14 ( this will be removed while submitting to GF. This is only for your consumption)
|  | Q9 |  | 170349.5
|  | Q10 |  | 162429
|  | Q11 |  | 159160.58
|  | Q12 |  | 86999
|  | Q13 |  | 132560.072
|  | Q14 |  | 244572

## LFA_Section 1D
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: |  | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: |  | 11
D. LFA RATING AND COMMENTS ON PROGRAMMATIC AND FINANCIAL PROGRESS
1. LFA's Rating of PR's overall performance (1) |  | B1
2. Reasons for this Rating (including key issues and potential future risks):
Of the seven top ten indicators, the average percentage of achievement is 82 % which is commendable, and average for all the indicators is 85 percent which is also high especially considering that the disbursements was received at the end of August 2010. Most of the CPs have been met. The financial achievement for this quarter is 106 percent as the expenditure was USD 169,161.09 from the quarter budget of USD 159,161. Many of the activities are carried out by SRs who are managed by the Project Management Unit (PMU). The National AIDS Control Program (NACP) carried out only three activities. There has been poor coordination between these three implementers (PMU, SR and NACP) which has resulted in the low performance since the financial achievement is mainly due to expenditure made for previous quarters and for Q12.. The quarterly meeting that was planned between these three implementers has not taken place regularly and also the reporting by the SRs has been poor which is further compounded by weak oversight by the PMU. Thus, the overall achievement for this quarter is rated as B1.
3. LFA comments on PR planned changes in the program, if any (please refer to section 1.A.v of the PR's Progress Update / Disbursement Request):
As mentioned in the earlier PUDRs, the Program Manager (Ms Sangay Wangmo) of the NACP had been transferred and no replacements have been made, which has left the program with three staff. Now another staff (Mr Kencho) will soon be leaving for further studies at the Masters level. This will affect the program as it will leave only 2 staff to manage all the activities.
4. LFA comments on data quality and reporting:
Reporting by the SR to the PR has not been on time and in some cases (RBA) it has been very poor. In this quarter, many of the SR have not been able to provide updated reports and coordination between the PMU and the SR's have been poor.
5. LFA comments on other program results, success stories, issues or lessons learned (please refer to section 1.A.vi of the PR's Progress Update / Disbursement Request):
The PR has not provided adequate oversight over the SRs and reporting has been very poor. There is a need for the PR to coordinate the activites of the PMU, NACP and the SRs so that activites are caried out effeciently and reporting is timely and complete. The SRs are also not aware of the reporting mechanisms and the details to be provided. A CCM secretariate has also been instituted and is located in the Ministry of Health building, with two staff, one CCM coordinator and one M&E personnel. GF has fielded a consultant to train PR and SRs on the PUDR reporting and training was conducted in December 2010 and LFA is yet to see the impact of the training in next PU/DR.
1 - This rating should pertain to the cumulative progress (from the beginning of the Program to the end of the period covered by the Progress Update). It should take into consideration programmatic, financial and contextual factors.
- LFA ratings have been modified to be consistent with the Global Fund's new rating system. The new ratings relate to the previous ratings as follows:
New Scale |  | Old Scale
Rating | Description | Rating | Description
A | Expected or exceeding expectations | 5 | Exceptional
|  | 4 | Expected
B1 | Adequate | 3 | Minor adjustments needed
B2 | Inadequate but potential demonstrated | 2 | Major adjustments needed
|  | 1 | Little progress made
C | Unacceptable | 0 | Major program issues
Note on C10: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)

## LFA_Section 2
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number: | 4
Disbursement Request - Period Covered: | Beginning Date: | 2010-11-01 | End Date: | 2011-04-30
Disbursement Request - Number: | 5
Section 2: LFA Review and Verification of the Principal Recipient's Cash Reconciliation and Disbursement Request
LFA COMMENTS ON THE CASH RECONCILIATION AND DISBURSEMENT REQUEST
1. The PR cash reconciliation is calculated correctly and is supported by a detailed Statement of Sources and Uses of Funds (i.e., Cash Flow statement): |  |  |  |  | Yes
Comments:
The PR has prepared the cash reconciliation statement based on the books of accounts maintained as per the government financial rules and regulations and the underlying supporting documents. The LFA verified opening balances against the closing balances of Q10 PU report and also the Cash Book. The closing bank and cash balances for Q11 have been verified against the Bank Statement and the cash book maintained by the PR. All recorded expenditures are supported with relevant documents and all payments were approved by the appropriated approving authority. Therefore, in the opinion of the LFA, the cash reconciliation has been prepared correctly. The cash reconciliation statement for Q11 is shown in Annexure B.
2. The PR Cash Request is calculated correctly and is supported by appropriate current budget forecasts: |  |  |  |  | No
Comments:
The cash request is calculated USD 458,443.85 by PR. However, the LFA review shows that the correct cash request should have been USD 457,583.85. This is arrived by adding forecast budget of USD 339,900.04 (unimplemnted budgets for Q9-11 plus Q12 budget of USD 18,199 after deducting USD 68,800 which was implemented in Q11), plus Q13 budget (USD 132,560.07 which is recommended as reflected in original budget and workplan) and Q14 as buffer USD 244,572.00 less existing cash balance USD 259,448.26. See annexure D.
3. The LFA has identified expenditures (incurred or forecasted) that should not be financed by the Global Fund: |  |  |  |  | No
Comments:
The LFA saw all expenditures incurred (USD 169,161.09) for this quarter (Q11) and the budget forecast amounting to USD 458,443.85 are within the GFATM approved work plan and the approved budget. The only variance is that some expenditures are made and forecasted in different quarters but all these activities are all included in approved work plan and budget of the program.
4. The LFA has identified variance between the forecasted expenditures and the original budget for the disbursement period, including variance in line items: |  |  |  |  | Yes
Comments:
The actaul forecasted expenditure for the disbursement period should have been USD 204,682.81 (USD 464,131.07 as original budget for Q12 and Q13 plus Q14 as buffer less cash balance of USD 259,448.26). There is difference of USD 253,761.04 as pointed out in PR Section 2, PR included all the budget for backlog activities of Q9-11 as part of forecast budget.

## LFA_Section 3
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number: | 4
Disbursement Request - Period Covered: | Beginning Date: | 2010-11-01 | End Date: | 2011-04-30
Disbursement Request - Number: | 5
Section 3: LFA Recommendations and Review of Progress on Previous Recommendations
A. LFA RECOMMENDATIONS FOR THE CURRENT PROGRESS UPDATE AND DISBURSEMENT REQUEST
LFA Recommendations |  |  |  |  | Global Fund Decisions
The PR should institute better coordination between the PMU, NACP and the SRs. The scheduled coorindation meetings should take place regularly. Consideration should be made on handing over the SR management to the NACP provided that the NACP has replacement staff (for those that have left and also for the one that is going for long term studies). The PMU can continue to function as the coordinating unit of GF projects. Time line: ASAP |  |  |  |  | Decision yet to made
The SRs should report on the agreed upon SR reporting form. The focal persons from each of the SR should be trained to report using the new format. The PR should also communicate and coordinate with the RBA which has not provided a singe report. Time Line: Starting Q12 |  |  |  |  | Decision yet to made
The PR should provide adequate information to the SRs regarding GF procedures/requirements and reporting of activities since there are still some SRs who are not aware off. Timeline: ASAP |  |  |  |  | Decision yet to made
New staff recruited by the PMU (M&E personnel) and the programs should receive comprehensive information and be familiar with GF reporting format and processes.Timeline: ASAP |  |  |  |  | decision yet to made
Both PR and SR should accelerate the implementation of Q9-11 activities since many activities remained unimplemented at the end of Q11. This has resulted in low achievement of important indicators as highlighted in Section B of LFA Section 3.Timeline: starting Q12 |  |  |  |  | This was communicated by GF as evidence from below during the implementation letter (See section B of LFA Section 3).
B. LFA REVIEW OF PROGRESS ON PREVIOUS RECOMMENDATIONS CONFIRMED BY THE GLOBAL FUND
Previous Global Fund Decision |  |  |  |  | LFA Review of PR Progress
Monitoring and Evaluation: It has been noted that there were delays in submission of reports by SRs. We believe that reports for people reached with life skill based education were received only from 11 districts. Schools in the remaining nine districts could not report as they were conducting the mid-term examinations. We would like to request you to obtain the reports from the remaining districts and report in the upcoming progress update. Similarly, the reports for the indicator ‘number of uniformed personnel and their families participating in HIV awareness workshops’. Kindly take the necessary actions and report the achievement to the Global Fund in the next progress report |  |  |  |  | There is still delay in reporting from the SRs and requires streamlining, in particular with the Department of Youth and Sports and the Royal Bhutan Army. The quarterly meeting between SRs, National Aids Control Program (NACP) and the Project Management Team requires to be held in time and reporting issues need to be streamlined.
Program management: We would like to request you to accelerate the implementation of the quarter 9 activities. We noted that during the reporting period (1 Feb – 30 April 2010) the activities that were implemented are from previous quarter. |  |  |  |  | Very few activities from Q9 were implemented in Q11. Besides, many activities from Q10 and Q11 remain unimplemented at the end of Q11.
Submission of the progress report: The PU/DR was submitted more than 60 days after the reporting period. We would strongly recommend for the timely submission of progress updates. This would help us in processing the disbursement request on time. |  |  |  |  | For this Quarter, the submission date line is 15 November 2010 but PR submitted the progress update to LFA on 30 December 2010. Q10 PU was submitted before the dateline.
The budget for phase 2: As per the Grant Agreement, the detailed budget for Year 4 and 5 needs to be submitted by 31 October 2010. We would like to request you to initiate the process. |  |  |  |  | Year 4 and 5 budget is submitted to GF and approval was accorded on 22 October 2010 by GF.
EFR: The EFR was submitted with the phase 2 request covering periods till July 2009. We would like to request you to update us on the status of the EFR for August 2009 – January 2010. Please submit the EFR to the LFA by 15 September, 2010. |  |  |  |  | EFR was submitted to LFA which was reviewed and submitted to GF
Improve the acheivement for indicator: Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  |  | This is one of the top ten indicators and the achievement is 55% and no results were made for this quarter as the reach of 24,106 was made till Q10. The target for Q11 was 44,000.
Improve the acheivement for indicator: Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  |  |  |  | This is one of the top ten indicators and also training indicator. The achievement is 71% and but no monks and nuns were reached during this quarter as the reach of 5,004 was made till Q10. The target for Q11 was 7000.
Improve the acheivement for indicator: Number of uniformed personnel and their families participating in HIV awareness workshops |  |  |  |  | Similarly PR and SR could not reach uniformed personnel and their families in this quarter as the result of 4,361 was conducted till end of Q10. The target for Q11 was 10,000 and the achievement is only 44 percent. This indicator is also one of the top ten indicators and also training indicator.
Note: The above decision were communicated to PR through Management letter for BTN-607-G03 H for 1 Feb - 30 April 2010 dated 17 August 2010 by GF addressed to Mr Tandin Dorji, Chief Program Officer copied to LFA and GNHC.

## LFA_Section 4
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office: |  |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 11
Progress Update - Period Covered: |  |  | Beginning Date: | 2010-08-01 | End Date: | 2010-10-31
Progress Update - Number: |  |  | 11
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  |  | Cycle: | Semester | Number: | 4
Disbursement Request - Period Covered: |  |  | Beginning Date: | 2010-11-01 | End Date: | 2011-04-30
Disbursement Request - Number: |  |  | 5
Section 4: Disbursement Recommendation and Progress Review Summary
A. DISBURSEMENT RECOMMENDATION
1. Cash amount requested by the Principal Recipient form the Global Fund for next disbursement period plus one additional quarter (amount in: USD): | [6 empty] | 458443.85 |  | 458443.85
2. LFA disbursement recommendation (amount in: USD): | [6 empty] | 457583.85
3. Reasons for the LFA's disbursement recommendation:
The LFA recommended USD 457,583.85 for disbursement which is less than (USD 860) the amount requested by the PR. The actaul forecasted expenditure for the disbursement period should have been USD 204,682.81. There is difference of USD 253,761.04 as PR included budget for unimplemented activities of Q9-11 (USD 321,701.04). The recommendation is made as PR was directed by GF to accelerate the implementation of back log activities through implementation letter dated 17 August 2010 and thus LFA is in opinion that PR would be able to accelerate the activities with enough budget. Besides, PR has already implemented USD 68,800 activity in Q11and only budget of USD 18, 199 is left to be implemented in Q12. Thus, PR and SRs could use Q12 quarter to implement back log activities if budgets are available. Further, the LFA is of the view that the PR requires this disbursement in order to make immediate disbursements to SRs. For instance, Department of Youth Services, Dratshang Lengthso, Royal Bhutan Police/ Royal Bhutan Army and RIHS have not received disbursement in Q11. The details of the recommendation on DR is provided in Annexure D.
B. LFA RATING
LFA's rating of PR's overall progress |  |  |  | B1
C. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [7 empty] | Comments regarding verifications, if any:
| Yes | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request | [5 empty] | Verified and found to be correct
| Partially | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable). | [5 empty] | CPs for this disbursement has been met
| Yes | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement). | [5 empty] | Verified and found to be correct
| Yes | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress. | [5 empty] | Verified and found to be correct
| Yes | Exchange rate stated by Principal Recipient has been verified and is correct. | [5 empty] | The exchange rates are: First disbursement= 1 USD= Nu. 39.25; Second disbursement =1 USD =Nu. 47.841; third disbursement 1 USD= Nu. 46.04; Fourth Disbursement 1 USD= 46.74
| Yes | Bank account information provided on the face sheet of Grant Agreement (Grant No. / Mod. No.): |  |  |  | BTN-607-G03-H | (or as otherwise | correct
stated by the PR in its Progress Update / Disbursement Request) has been verified and is correct.
| Yes | Current budget forecasts of the Principal Recipient for the next disbursement period plus one additional quarter have been reviewed for reasonableness | [5 empty] | The current budget forecasts USD 458,443.85 made by the PR for the next disbursement has been verified and found reasonable and, one additional quarter as buffer USD 244,572.00 is correctly stated. However, LFA recommended USD 457,583.85 after verification as there was minor mistake.
Signed on behalf of the LFA:
Name: |  |  | Chhewang Rinzin
Title: |  |  | Finance Expert, LFA
Date and Place: |  |  | 10 Jan 2011, Thimphu, Bhutan
Note on E34: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)
DRAFT

## LFA_Signature (image)
OPTIONAL - insert image of LFA signature here*: (the size should not exceed the limit of cells B2:D2)
* In every case, the LFA should provide a bona fide signature (in LFA_Section 4) on the original (paper-based) LFA report, sent to the Global Fund by mail.