## PR_Cover page
On-going Progress Update and Disbursement Request
Instructions to the Principal Recipient for completing the On-going Progress Update and Disbursement Request
Progress Update
The Progress Update part of this form requires the Principal Recipient (PR) to provide:
- Past expenditure and programmatic performance information for the reporting period just ended
- An update on the progress made towards satisfaction of the conditions precedent (if any) set forth in Annex A to the Grant Agreement applicable
to the period covered by the Progress Update
- A detailed Statement of Sources and Uses of Funds (Cash Flow Statement) for the reporting period just ended
For the Statement of Sources and Uses of Funds, the PR may use its own usual format and expenditure line items as derived from its budgeting and accounting records. The Global Fund does not prescribe specific expenditure line items, but prefers that the PR's reporting format is activity-based, in conformity with the proposal's objectives and service delivery areas. The PR is expected to clearly show actual expenditures as compared to budget for both its own expenditures as well as for disbursements to sub-recipients. The Statement of Sources and Uses of Funds should support the information disclosed in this form in Section 1.C (Program Expenditures) and Section 2.A (Cash Reconciliation for Period Covered by Progress Update).
Disbursement Request
The Disbursement Request part of this form requires the PR to state the cash requirement for meeting on-going program expenditures. The disbursement requested from the Global Fund normally covers the PR's cash requirements for one reporting period, plus one additional quarter as a cash buffer, to ensure the PR has adequate cash on hand for program expenses at all times. The period covered by the Disbursement Request is the period that immediately follows the Reporting Period covered by the Progress Update (as explained above).
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Section 1A (1)
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: |  | Bhutan
Disease: |  | HIV/AIDS
Grant Number: |  | BTN-607-G03-H
Principal Recipient: |  | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01
Currency: |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: |  | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: |  | 12
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | Select
Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  | N/A
TERMS AND ACRONYMS USED IN THIS PROGRESS UPDATE AND DISBURSEMENT REQUEST HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: Programmatic and Financial Progress Update
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
Select
Select
Select
Select
Select
Select
Select
Select
Select
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Intended Yearly Targets | Actual Yearly Results | Reasons for deviation and any other comments
[6 empty] | Value | Year
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | 0.05% | 2006 | <0.1% | N/A | Sentinel surveillance will be conducted in the later half of the 2010, currently the surveillance protocol is being revised
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  |  | 0.20% | 2006 | <0.1% | N/A | Sentinel surveillance will be conducted in the later half of the 2010
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | 47% | 2009 | N/A | N/A | The next KAP survey will be conducted in the final year of the project
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | 53% | 2009 | NA | N/A | The next KAP survey will be conducted in the final year of the project
Select
Select
Select
Select
Select
Select
Select
Select

## PR_Section 1A (2)
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: |  | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: |  | 12
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Directly Tied? | Level | Baseline (if applicable) |  | Intended Targets to date | Actual Results to date | Reasons for programmatic deviation and any other comments
[8 empty] | Value | Year
1 | Prevention: BCC - community outreach | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | No | 0 | 0 | 2006 | 62100 | 45528 | DYS has not reported for Q11 previously. During the current reporting period DYS has reported for both Q11 &Q12 and the results achieved during this 2 quarters is 21422 ( 10967 girls & 10455 boys of grade 7 and above from 62 schools in the country from 7 districts ( dagana, gasa, sarpang, chukha, haa & Thimphu) have been reacehd with LSE onHIV/AIDS. The remaining 22598 students will be covered by end of 2011.
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education |  |  |  | Yes | 1 | 0 | 2006 | 629 | 1379 | DYS has trainded 1110 teachers on LSE on HIV/AIDS. Since there was over budgeting at the time of budget development , the budget allocated was sufficient to train additional 750teachers over the target of 629.
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  | Yes | 2 | 45 | 2009 | n/a | 45 | As per the findings of the KAP survey on HIV/AIDS 2009 May
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings |  |  |  | Yes | 1 | N/A |  | 21350 | 48843 | During the World AIDS day celebration the funds were release to all the 714 NFE centers in the country and a results 12499 youth NFE learners and 16622 other community youths were reahced with the HIV/AIDS education.
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  | Yes | 1 | 0 | 2006 | 827 | 816 | during the reporting quarter a total of additional 99 principals were trained on LSE HIV Education in two batches in Phuntsholing. The unmet target will be covered up in subsequent quarters.
1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education |  |  |  | No | 0 | 100 | 2009 | 480 | 472 | The HISC under the AIDS control has been able to reach out to additional 203 transport workers with HIV education during the reporting quarter
1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) |  |  |  | Yes | 1 | 0 | 2006 | 150 | 142 | The peer deducators and counsellors from HISC have able to reach out to 63 most at risk indivuduals with educational materials in this reporting quarter.
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  | No | 1 | 6000 | 2006 | 11000 | 7508 | During the reporting quarter 799 armed forces and families from RBA was sensitized . 2321 armed forces and their families from RBP was sensitized on HIV / AIDS ( This figure include 1011 prisoners and 4 women police officers who attneded capacity development workshop)
1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  |  |  | Yes | 2 | 500 | 2005 | 7000 | 6404 | A total of about 1,400 monks reached through a one day training and advocacy program conducted across the country initiated by respective District Monastic Bodies (Rabdeys). There are a total of 20 Rabdeys under this one day program. Each Rabdey will be conducting their respective one day training and advocacy program in collaboration with the District Medical Officers.About 70 monks from each Rabdey will be participating for the training and the advocacy program
1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results |  |  |  | No | 2 | 1500 | 2005 | 27200 | 33321 | A total of 1342 people have been conseled and tested incuding the provision of results this quarter. The reports are compiled from various VCT centers in the country
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment |  |  |  | No | 2 | 25 percent (19) | 2006 | 75 | 57 | only 1 additional HIV patient have been put on ART treatment this quarter
1

## PR_Section 1A & 1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: | 12
iv. Overall evaluation of performance
The SR have actively implementded all their planned activties for the quarter. All the funds with the PR have been disbursed to the respective SR's and over all the financial achievement is very good this quarter.
v. Planned changes in the program, if any.
No major changes in the planned activties. Procurment of Health products were delayed due to the non approval of the PSM plan .
vi. Other program results, success stories, issues or lessons learned
The Project Management Team have been able to get the reports on time from the SR's through the regular Quarterly Review meetings. Almost 80% of SR's have reported in the template. From the Q13 it was made mandatory that 100% of SR should report in the template. A financial management workshop for the SR was also conducted in December 2010 with the consultant fielded by The Global Fund. The workshop was a big success as it could outline on GF issues especially on financial and auditing requirements and also mitigating the risk and other corruption.
B. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? (Yes/No) | PR Comments
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  |  |  | Yes | M&E officer has been recruited at the Project Management Unit to monitor the the GF activties for a duration of 3 years starting April 2010
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country; and |  |  |  | Yes | PMT has now standardized the reporting format for GF HIV reporting ans trained all the SR's . There are still more reporting formats which needs to be standardised
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  |  |  | No
The disbursement by the GF or use by PR of global funds to finance the procurement of Health products (as defined in Article 19 of the Standard Terms and Condition of this Agreement), is subject to the following conditions: |  |  |  | Yes | Updated PSM plan has been developed and submitted to GF
(a) The Principal Recipient shall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. The Updated PSM shall: |  |  |  | Yes
(i) address the deficiencies identified during the Phase 1 review in consultation with the GF, particularly those deficiencies relating to procurement process, quality assurance systems, storage and distribution as well as inventory mangement; and |  |  |  | Yes
(ii) include assumptions on forecasting for ARVs and testing products in order to ensure alignment with the performance framework and work plan and budget, where appropriate; and |  |  |  | Yes
(b) The written approval of the Global Fund of the updated PSM plan |  |  |  |  | PSM plan has been submitted since June 2010 but written approval has not yet been accorded
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  |  |  | Yes | MOH has been designated as the new PR after the signing of the phase 2 agreement of the project.
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of (1) program officer, (2) M& E Coordinator, (3) Finance Officer/Accoutant (4) Project Manager |  |  |  | Yes | The PMU established to faciliate the coordination of GF grant have team comprising of Project Coordinator, M&E officer, 2 finance personel , 1 administrative assiatnt , 1 procurement officer dealing with the procurement of health products to manage the grants
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  |  |  | Yes | The detailed quarterly budget for year 4 &5 has been delivered and been approved by GF
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  |  | In Progress | The PQR shall be updated as & when the products are procured

## PR_Section 1C
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: | 12
C. PROGRAM EXPENDITURES
All amounts are in: USD | Budget for Reporting Period | Actual for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | Reason for Variance | 12369.31
1. Total actual expenditures vs. budget | 86999 | 241587.9 | -154588.9 |  | 2081384.5 | 1723994.08 | 357390.42 |  |  | 12369.31
1a. PR's total expenditures | 5394 | 72823.3 | -67429.3 | The over expenditure was due to the implementation of spill over activties from the previous quarters. | 1104361.5 | 807737.64 | 296623.86 | The cumulative variance is due to the non implementation of Q9 & Q10 planned activties due to non reciept of phase 2 funds. Though the Phase 2 started from Febraury 2010 , there was delay in grant negotiation and also disbursement of DR and in the process two quarters activties are now back logged .
1b. Disbursements to sub-recipients | 81605 | 168764.6 | -87159.6 | The huge chunk of disbursement of USD 68,000 for celebrating world AIDS day for 1st December 2010 was released in advance in this quarter to ensure the funds arrive on time and activties are implemented. The budget for Q12 was released in this quarter. | 977023 | 916256.44 | 60766.56
2. Health product expenditures vs. budget (already included in '"Total actual" figures above) | 0 | 0 | 0 | The PSM Plan has not yet been approved and also the procurment funds have not been released, no procurment took place during this reporting period. | 264000 | 123807.6 | 140192.4 | The Procurements could not be made due to non availability. Some of the items have been procured but the payments were not made due to delayed DR
2a. Pharmaceuticals | 0 | 0 | 0 |  | 49500 | 16927 | 32573
2b. Health products, commodities and equipment | 0 | 0 | 0 |  | 214500 | 106880.6 | 107619.4
Program expenditures were used for the procurement of health products: |  |  |  | No
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | Yes

## PR_Section 2
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  | Cycle: |  | Semester | Number:
Disbursement Request - Period Covered: |  | Beginning Date: |  |  | End Date:
Disbursement Request - Number: |  | N/A
Section 2: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 6 from Cash Reconciliation section of the period covered
by the previous Progress Update): | [8 empty] | 259448.26
Add: | 2. Cash disbursed to the PR by the Global Fund during the period covered by this progress update: (1)
| 3. Interest received on bank account and other income received: | [6 empty] | 0 | 0
Less: | 4. Total program expenditures during period covered by Progress Update (value entered in Section 1C. "Total actual expenditures"): | [6 empty] | 241587.9
| 5. Other expenditures incurred (bank fees, other transaction costs, net exchange rate gains/losses): | [7 empty] | 241587.9
6. Cash Balance: End of period covered by Progress Update: | [8 empty] | 17860.36
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update (2, 3):
7. Period beginning date: |  |  | end date: |  |  | amount as originally budgeted: | forecasted amount:
8. Additional quarter
(cash "buffer") beginning date (4): |  |  | end date: |  |  | amount as originally budgeted: | forecasted amount: | 0 | 0
Please explain any variance between the forecasted amounts and the amounts as originally budgeted
\
Less: | Cash Balance: End of period covered by Progress Update (number 6 above): | [6 empty] | 17860.36
| 9. Cash received from the Global Fund after the period covered by Progress Update or cash "in transit" (5) (if any): | [6 empty] | 0 | 17860.36
10. PR's Disbursement Request from the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [8 empty] | 0
11. Does the PR's Disbursement Request include funds for health product procurement? |  |  |  |  | Yes
12. Exchange Rate (used to translate local currency into USD): |  |  | 46.74
Footnotes:
1 - Gross amount disbursed by the Global Fund (i.e., any associated bank fees or transaction costs should not be deducted in this line, but included in line 5. “Other expenditures incurred”
2 - Expenditures listed must be covered by current budget forecasts
3 - Total forecasted net cash expenditures should include any commitments made in the period covered by the Progress Update that are forecasted to be spent during the period covered by the Disbursement Request
4 - Additional period (cash "buffer"): disbursement of funds for Q9 is contingent upon the signing of Phase 2 or as otherwise stipulated per implementation letter
5 - “Cash in transit” includes amounts disbursed but not yet received by the PR and disbursement requests not yet approved by the Global Fund.

## PR_Section 3
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Bhutan
Disease: | HIV/AIDS
Grant number: | BTN-607-G03-H
Principal Recipient: | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: | 2008-02-01
Currency: | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: | 12
DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: | Cycle: | Semester | Number:
Progress Update - Period Covered: | Beginning Date: |  | End Date:
Progress Update - Number: | N/A
Section 3: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from Section 2.B line 10, in: USD): |  | 0
2. Amount requested in words (in: USD):
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name: | Tandin Lhamo
Title: | Programme Officer, GNHC
Date and Place: | 22 March 2011, Thimphu
Bank Account Details (if different than the account details specified on block 9 of the face sheet of the Grant Agreement) |  |  |  |  | Comments (e.g. changes to PR's bank account details, "split disbursements" to the PR and third parties etc.):
Owner of Bank Account:
Account Title:
Account number:
Bank name:
Bank address:
Bank SWIFT Code:
Bank Code:
Routing instructions:

## LFA_Cover page
LFA On-going Progress Review and Disbursement Recommendation
Instructions to the LFA for completing the LFA On-Going Progress Review and Disbursement Recommendation
The Principal Recipient (PR) is required, through the On-Going Progress Update and Disbursement Request, to:
1. Provide past expenditure and programmatic performance information for the Reporting Period just ended; and
2. State its cash requirement for meeting on-going program expenditures.
The LFA is required, using this form, to verify progress and make recommendations on the cash amount requested.
Progress Update
The PR will report past expenditure and programmatic performance information for the Reporting Period just ended as well as progress made towards fulfillment of any conditions precedent/special conditions. The LFA is required to review and verify this information and, in accordance with the information fields set out in this form, to comment on current and cumulative progress.
Disbursement Recommendation
The PR will normally make a disbursement request from the Global Fund covering the PR's cash requirements for one Reporting Period, plus one additional quarter as a cash buffer, to ensure that the PR has adequate cash on hand for program expenses at all times. The Reporting Period for which the Disbursement Request is being made should be the period that immediately follows the Reporting Period covered by the PR's progress update (as explained above). The LFA is required to verify the PR's Cash Reconciliation and to ensure that the cash request is properly calculated. The LFA should recognize that the cash request should be based on the most up-to-date budgets for the relevant periods which the LFA should review for reasonableness.
Documents to be attached/retained
When submitting this form to the Global Fund, the LFA should attach the following:
1. PR On-Going Progress Update and Disbursement Request form (by email with originals to follow by mail)
2. Any supplementary information, as appropriate, to inform the Global Fund of the review and verification process and to support the review and recommendation
The LFA should also retain the PR's detailed Statement of Uses of Funds (Cash Flow Statement) for the Reporting Period just ended as well as any additional relevant documentation of verifications performed (to be provided upon request by the Global Fund).

## LFA_Section 1A (1)
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office: |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  | Bhutan | [10 empty] | Bhutan
Disease: |  | HIV/AIDS | [10 empty] | HIV/AIDS
Grant Number: |  | BTN-607-G03-H | [10 empty] | BTN-607-G03-H
Principal Recipient: |  | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN | [10 empty] | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01 | [10 empty] | 39479
Currency: |  | USD | [10 empty] | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 12 | [7 empty] | Quarter | 12
Progress Update - Period Covered: |  | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31 | [7 empty] | 40483 | 40574
Progress Update - Number: |  | 12 | [10 empty] | 12
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | [8 empty] | Semester
Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  | N/A | [10 empty] | N/A
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic and Financial Progress
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations | [9 empty] | 1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country | [9 empty] | 2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA | [9 empty] | 3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Intended Yearly Targets (from Attachment) | Actual Yearly Results (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on impact and outcome, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | <0.1% | N/A | PR On-site Visit | N/A | As per the PF, sentinneal survey is to be conducted on a yearly basis for 2010 (Year 3), 2011 (Year 4) & 2012 (Year 5). However, the PR has not been able to conduct the survey (this is the planned annual HIV sentinel surveillance) as per the schedule in Year 3 because of lack of funds. A new surveillance strategy (draft) has been developed, which will make it easier to compare with the baseline information of 2007. However, without funds, it will not be possible for the PR to implement the strategy. The prevalence as it stands is reported as 0.2 % with a range of 0.1-0.3 % (Source UNAIDS 2009), however this needs to be confirmed through valid reports. | Impact | Percent of women and men aged 15-49 who are HIV infected | <0.1% | N/A
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  |  | <0.1% | N/A | PR On-site Visit | N/A | As per the PF, sentinneal survey is to be conducted on a yearly basis for 2010, 2011 & 2012. However, the PR has not been able to conduct the survey as per schedule in 2010 because of lack of funds. A new surveillance strategy (draft) has been developed, which will make it easier to compare with the baseline information of 2007 however without funds for the activity, it will not be possible for the PR to implement the strategy. The prevalence as it stands is reported as less than 0.1 % (Source UNAIDS, 2009), however this needs to be confirmed through valid reports. | Impact | Percentage of uniformed personnel who are HIV infected | <0.1% | N/A
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | N/A | N/A | PR On-site Visit | N/A | This is not due for reporting and will be reported after the second KAP survey which is scheduled to be done in the fifth (last) year of the project. The baseline data as per the 2009 KAP survey shows that 47 % of out of school youth aged 15-24 years reported the consistent use of condoms. | Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year | N/A | N/A
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | NA | N/A | PR On-site Visit | N/A | This is not due for reporting and will be reported after the second KAP survey which is will be done in the fifth and last year of the project. Baseline data from the 2009 KAP survey shows that 53 % of uniformed personnel reported consistent use of condoms with non regular sexual partner. | Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year | NA | N/A
Select
Select
Select
Select
Select
Select
Select
Select

## LFA_Section 1A (2)
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: |  | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: |  | 12
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Intended Targets to date (from Attachment) | Actual Results to date (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on progress to date, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
1 | Prevention: BCC - community outreach | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | 62100 | 45528 | PR On-site Visit | No change | Cumulative achievment: 73.3% Cumulative actual/target 45,528/62,100. This result shows under-achievement.This is a top ten indicator Results reported over program term. In this quarter, a total of 21, 422 children were reached with Life skills based HIV/AIDS education, taking the cumulative total to 45,528. The under-achievement in this quarter can be corrected by taking up activities in next 2 Quarters as the target remains the same for the next two quarters. The present report is from 62 schools out of the total 144 schools targetted for this activity, and so with activities planned for the other remaining schools it is likely that the target will be reached by the end of Q14. The SR has also begun using the new SR reporting formats from this quarter and reporting has improved in that it is timely, all the relevant supporting documents are attached and details of the activity have been provided. | 1 | Prevention: BCC - community outreach |  | 62100 | 45528
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | #REF! | #REF! | #REF! | 629 | 1379 | PR On-site Visit | No change | Cumulative achievment: 219.2 % Cumulative actual/target 1,379/629. This result shows over-achievement. Results reported over program term. This activity was conveniently scheduled to be conducted during the school break which was from December to February. As a result, SR was able to reach a large number of teachers. A total of 1,110 teachers were trained in this Quarter. However, not all teachers were from grades 7 and above. Even teachers from the primary schools were included, although the report did not give a breakdown. (Source of information: Quarterly report from DYS, letter number DYS/CSHD/GFATM/2011/2103 dated 4/3/2011) Training teachers from the primary level may be beneficial, not only in making them aware but because some of them may be transferred to higher schools later. The curriculum for life skills education is taught from grade 7 only. There was over budgeting of this activity and as a result there were more than adequate funds to train not only grade 7 and above teachers but also primary school teachers. | 1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | 629 | 1379
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | #REF! | #REF! | #REF! | n/a | 45 | PR On-site Visit | No change | No target has been set for this indicator. results are not due for reporting. Results not cumulative The only target set is at 60% to be reported by quarter ending (Q19) in October 2012, which should result from another KAP survey in 2012. The last result is based on the KAP survey report 2009 which shows that 45 % of young people in school correctly identify ways of preventing HIV AIDS. This is much lower than that reported for university students and out of school youths ( >60 %) however the criteria used in the last survey was more stringent (know all five indicators as used in the survey) and this could be the reason for the low knowledge among in school youth. | 1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | n/a | 45
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | #REF! | #REF! | #REF! | 21350 | 48843 | PR On-site Visit | No change | Cumulative achievment: 228.8 % Cumulative actual/target 48,843/21,350. This result shows over-achievement. Results reported over program term. Funds were released by the PR to the SR -Non Formal Education division of the Ministry of Education. The SR in turn distributed the funds to all 714 NFE centers in the country to celebrate World AIDS day in December 2010, where a number of people from out of school setting was made aware of HIV. A total of 12,499 (4,062 males and 8,437 females) along with 16,622 other community people were reached making a total of 29,121 people reached. World AIDS day has become popular over the years with media giving a lot of attention, therefore, this activity having reached large numbers of people (much higher than the target) will be beneficial in educating people in out of school setting. By "reached", the PR has included all the people that turned up for the world AIDS celebrations and who attended the awareness session on HIV AIDS. | 1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | 21350 | 48843
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | #REF! | #REF! | #REF! | 827 | 816 | PR On-site Visit | No change | Cumulative achievment: 98.7 % Cumulative actual/target 816/827 This result shows slight under-achievement. This is one of the top ten (training) indicators Results reported over program term. A total of 99 principals of the schools were trained in two batches in Phuntsholing in this quarter. The first batch consisted of 42 principals and was conducted between 22 - 26 December 2010, while the second had 52 participants and was held between 31 December 2010 - 4 January 2011. Each training was conducted for five days and the training agenda contained comprehensive instructions on HIV/AIDS. Although the targets have not been achieved, the SR has scheduled to train more principals in the coming quarters and so it is likely that targets in the coming quarters will be achieved. Although non formal instructors were to be trained, the new work plan has included the training of principals of schools as all the NFE instructors have been trained. This is appropriate because the principals will be performing oversight functions for the NFE instructors and will be also supervising them. | 1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | 827 | 816
1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education | #REF! | #REF! | #REF! | 480 | 472 | PR On-site Visit | No change | Cumulative achievment: 98.3 % Cumulative actual/target 472/480. This result shows slight under-achievement. Results reported over program term. In this quarter 203 transport workers were reached with HIV education. One day training was held for 163 taxi and truck drivers by the HISC (Health Information and Service Center) in Samdrup Jongkhar which borders the Indian state of Assam in the East. The second training was held for 40 transport workers in Phuntsholing and this was conducted by the HISC center. LFA verified the training report submitted to the NACP (reference EDA/Health/ADM - 31 dated 11/2/2011). The vehicle numbers are being submitted as reflected in the PF. The transport workers consist of Taxi drivers and truckers who are categorized as Most-at-risk-population (MARP) in Bhutan for HIV. | 1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education | 480 | 472
1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) | #REF! | #REF! | #REF! | 150 | 142 | PR On-site Visit | No change | Cumulative achievement: 94.7 % Cumulative actual/target 142/150 This result shows slight under-achievement. Results report cumulative over program term. In this quarter, 63 most at risk individuals were reached with HIV education material in Phuntsholing. This included 23 most at risk individuals who visited the VCT center for HIV testing and another 40 young people who volunteered to work with the police in a program called Police-Youth partnership, initiated by the Police with funding from Save the Children, Bhutan. The activity was conducted by the HISC center. The issue with the Drayang (Bars with dancers) girls is still being debated with the Ministry of Labour contemplating programs to rehabilitate these girls. The negative and stigmatizing label put on the employees of the Drayangs is being strongly objected by the employers and the girls who work in the bars. Nevertheless they remain vulnerable and are grouped as most at risk. | 1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) | 150 | 142
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | #REF! | #REF! | #REF! | 11000 | 7508 | PR On-site Visit | 7481 | Cumulative achievment: 68 % Cumulative actual/target 7,481/11,000 This result shows under-achievement. This is one of the top ten (training) indicators Results reported over program term. For this Quarter, 799 Army personnel and their families participated in HIV awareness workshop as verified from the workshop report. Reporting by the Royal Bhutan Army who carry out the activity using their own medical doctors has been poor as they have failed to submit a single report. The present report has been submitted by the M&E officer of the PMT (Project Management Unit) who visited three districts at the time of the activity being conducted. In addition 2,321 police personnel and their families were also reached in this quarter. The police have been reporting this acitivity regularly and they are using the new format. The quality of the data is good in that it is timely and has all details. The PR needs to meet the RBA and sought out the reporting mechanism and bring the SR to send in timely reports. A new handbook titled "HIV/AIDS & STIs, Curriculum for Armed Forces" has been developed to be used to educate all new army recruits. This will be of beneficial as it will be sustainable being incorporated into the system. The same should also be used for police recruits. The variance is due to earlier arithmatical error (reported in last quarter) | 1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | 11000 | 7508
1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | #REF! | #REF! | #REF! | 7000 | 6404 | PR On-site Visit | No change | Cumulative achievement: 91.5 % Cumulative actual/target 6,404/7,000 This result shows under-achievement. This is one of the top ten (training) indicators Results reported over program term. The Dratshang Lhentshog has submitted the report in this quarter and the report was for Year 3 with all four quarters. The SR has not used the SR reporting format. It has reported that 1,400 monks in 20 Rabdeys (district monastry) have been reached by HIV/AIDS education. There is very limited supporting documents and mostly in the form of photographs of some Rabdeys. The PR has not provided adequate oversight and reporting by the SR is also not timely. Despite the quarterly SR and PR meeting, the SR for this activity has not been reporting on time and in the correct format. | 1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | 7000 | 6404
1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | #REF! | #REF! | #REF! | 27200 | 33321 | PR On-site Visit | No change | Cumulative achievement: 122.5 % Cumulative actual/target 33,321/27,200 This result shows over-achievement. This is one of the top ten (training) indicators. Results report cumulative over program term. In this quarter, 1,342 people were counselled, tested and provided with results during this quarter. In the past PR reported on number of people tested, however in this quarter, the results are correctly reported and include only those that have been provided with results. Source of information is the quarterly VCT report compiled by the NACP. This is in line with the PF and is also more appropriate.This is a routine activity carried out at all hospitals including the Health Information Service Centers (HISC) and is routinely reported by all VCT health centers. | 1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | 27200 | 33321
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | #REF! | #REF! | #REF! | 75 | #REF! | PR On-site Visit | 57 (76%) | Cumulative achievement: 76 % Cumulative actual/target 57/75. This result shows slight under-achievement. This is one of the top ten (training) indicators Results report cumulative over program term. In this quarter, only 1 HIV positive person was put on treatment. (Quarterly report submittted by the health centers). The program continues to use the old standard of starting HAART with a CD4 count of 200. The national treatment protocol has still not been finalised and new criteria for starting treatment as recommended by WHO (CD4 count of 350) have not been implemented. Using the new criteria it is expected that many more HIV positive people will be on HAART. | 3 | #REF! | #REF! | #REF! | #REF!
1 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 1
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 | [6 empty] | 57 |  |  |  | 0 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | 75 | 57
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!

## Annexure A
Annexure A: Indicator Rating | ANNEXURE A: INDICATOR RATING
Indicators |  | Top 10 | Training | Target | Results | % Achievement
Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  | Top 10 |  | 62100 | 45528 | 73.31% | Top 10 |  |  | All Indicators |  | Training Indicators
Number of teachers trained on life skill based HIV/AIDS education |  |  | Training | 629 | 1379 | 120% | 73.31% | 95.8% | A2 | 96% | A2 | 120% | 94.6% | A2
% of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  | Top 10 |  | na | 45 | no target set | 120% |  |  |  |  | 98.67%
People reached by HIV/AIDS education in out-of-school settings |  | Top 10 |  | 21350 | 48843 | 120% | 120% |  |  |  |  | 94.7%
Non Formal Education Instructors trained to provide HIV out-of-school education |  | Top 10 | Training | 827 | 816 | 98.67% | 98.67% |  |  |  |  | 68.01%
Number of Transport workers reached with HIV education |  |  |  | 480 | 472 | 98% | 68.01% |  |  |  |  | 91.49%
Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) |  |  | Training | 150 | 142 | 94.7% | 91.49%
Number of uniformed personnel and their families participating in HIV Awareness workshops |  | Top 10 | Training | 11000 | 7481 | 68.01% | 120%
Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  | Top 10 | Training | 7000 | 6404 | 91.49% | 76%
Number of persons counseled and tested including provision of results |  | Top 10 |  | 27200 | 33321 | 120% | 94.6%
Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment |  | Top 10 |  | 75 | 57 | 76%

## LFA_Section 1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: | 12
B. LFA COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? | LFA Analysis (this should not be a “Copy and Paste” of the comments provided by the PR)
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  |  |  | Yes | PR has recruited an M & E Officer who is attached with PMT to look after M & E component of all three diseases | Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country; and |  |  |  | Yes | PR has developed new reporting format and guidelines to be used by SRs to report the quarterly report. However, the reporting format agreed upon by the PR and SR is not being used by few SRs. During the 12 Quarterly meeting held on 15 March 2011, PMT requested SRs to use the format and all SRs agreed to the request. | Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country; and
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  |  |  | No | In Q11, PR reported that since PR could not recruit M& E Consultant due to no candidate responding to advertisement that they would be recruiting a local Consultant for the work. Now it is being discussed whether to recruit a local Consultant or to re-tender for International TA since PR is not sure if Local Consultant could be able to perform all the required fucntions. The decision is yet to be made. | Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units
The disbursement by the GF or use by PR of global funds to finance the procurement of Health products (as defined in Article 19 of the Standard Terms and Condition of this Agreement), is subject to the following conditions: |  |  |  | Yes | Updated PSM plan was submitted to GF and was approved on 2 Feb 2011. | The disbursement by the GF or use by PR of global funds to finance the procurement of Health products (as defined in Article 19 of the Standard Terms and Condition of this Agreement), is subject to the following conditions:
(a) The Principal Recipient shall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. The Updated PSM shall: | [5 empty] | (a) The Principal Recipient shall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. The Updated PSM shall:
(i) address the deficiencies identified during the Phase 1 review in consultation with the GF, particularly those deficiencies relating to procurement process, quality assurance systems, storage and distribution as well as inventory mangement; and |  |  |  | Yes | This has been done. There were several exchange of comments and revisions on the Phase 2 PSM Plan. The deficiecies were corrected and based on the revision, GF provided the approval for PSM Plan. | (i) address the deficiencies identified during the Phase 1 review in consultation with the GF, particularly those deficiencies relating to procurement process, quality assurance systems, storage and distribution as well as inventory mangement; and
(ii) include assumptions on forecasting for ARVs and testing products in order to ensure alignment with the performance framework and work plan and budget, where appropriate; and |  |  |  | Yes | PR has submitted forecasting for ARVs and testing products while submiting PSM Plan which is aligned with PF, workplan and budget | (ii) include assumptions on forecasting for ARVs and testing products in order to ensure alignment with the performance framework and work plan and budget, where appropriate; and
(b) The written approval of the Global Fund of the updated PSM plan |  |  |  | Yes | The written approval of the GF of the updated PSM Plan was provided on 2 Feb 2011. | (b) The written approval of the Global Fund of the updated PSM plan
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  |  |  | Yes | The PCM members during its 14th PCM meeting endorsed that hereafter the Ministry of Health shall be the PR and is responsible for implementation of the program. The Phase 2 documents were also signed both by GNHC and MoH to reflect this arrangement | The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of (1) program officer, (2) M& E Coordinator, (3) Finance Officer/Accoutant (4) Project Manager |  |  |  | Yes | The required staffs are in place. Currently, Mr Tandin Dorji is the overall Program Manager for TB and HIV program. Mr. Sonam Wangdi is the Program Officer. Mr Ugyen Tshewang is the Finance Officer and Mr Dinash Rai is working as an Accountant. There is one M & E officer (newly recruited) who will be looking after M & E component of all three diseases. Mr Tandin Dorji, Chief Program Officer of DVED is looking after PSM. | The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of (1) program officer, (2) M& E Coordinator, (3) Finance Officer/Accoutant (4) Project Manager
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  |  |  | Yes | PR submitted the detailed quarterly budget for Year 4 and 5 including detailed breakdown per cost categories and summary budget to LFA on 17 October 2010. LFA verified the submission and was submitted to GF on 18 October 2010 and GF approved the Year 4 and 5 budget including detailed breakdown on 22 October 2010. | No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums.
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  |  | Yes | Since GF approved the PSM Plan only on 2 Feb 2011, no procurement budget were released, PR has therefore has not procured any health products and there is no update on PQR database. | Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting.

## LFA_Section 1C
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: | 12
C. PROGRAM EXPENDITURES
All amounts are in: Please select currency on Page 1 | Budget for Reporting Period | Actual for Reporting Period1 | Variance | LFA Verified (Y/N) | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR) | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR)
1. Total actual expenditures vs. budget | 86999 | 241587.9 | -154588.9 |  |  | 1853036 | 1723994.08 | 129041.92 | v | 86999 | 241587.9 | -154588.9 | 2081384.5 | 1723994.08 | 357390.42
1a. PR's total expenditures | 5394 | 72823.3 | -67429.3 | Yes | The overall budget absorption rate of Q12 end is 278% of the corresponding budget of USD 86,999.00. This is mainly due to disbursement of funds to the SRs including funds for back log activities. The budget implemented (partially or fully) in Q12 amounts to 17% (USD 14,939) while 79% (USD 68,800.00) of the Q12 budget has been implemented in Q11 (Community activities by youth NFE learners) and only 4% (USD 3,260) remains un-implemented at Q12 end. Regarding expenditure, 14% (USD 34,679.30) pertains to budgeted expenditure while 86% (USD 206,908.59) relates to back log activities. With respect to the PR’s budget and expenditure analysis, the PR’s budget absorption rate of Q12 end is 1350% i.e. expenditure USD 72,823.30 against the corresponding budget USD 5,394.00. But out of the total budget, the PR implemented budget (fully or partially) of 56% (USD 2,944) and 44% of the budget (2,400.00) has not been implemented by Q12 end. Analysis of expenditure shows that, budgeted expenditure constitutes only 4% (USD 2,596.03) of the reported expenditure of USD 72,823.30, while 96% (USD 70,227.27) of the expenditure pertains to back log activities of Q9, Q10 and Q11 respectively. This indicates, that the PR implemented substantial amount of budgeted pertaining to previous quarters in Q12. Detailed analysis is shown in Annexure -C. | 872561 | 800603.01 | 71957.99 | The overall cumulative burn rate (PR & SR) achieved at Q12 end is 93%. This is after adjusting- by deducting undisbursed fund amounting to USD 228,780.00 at the end of Phase I (reflected at Section 2.2.4 of Phase 2 Review) from the cumulative budget and the cumulative variances. Hence, the cumulative budget amounting to USD 1,853,038.00 and the cumulative expenditure USD 1,723,994.02 at Q12 end reflects actual budget and the expenditure of HIVAIDS program for both Phase I and Phase II which is on-going. This adjustment has been affected upon advice from the GFATM. The cumulative variance of USD 129,043.98 mainly consist of procurement budget of USD 92,063.53 (Year 3) and remaining USD 36,980.45 which is about 2 % is insignificant. Detailed line item variance analysis for Q9-Q12 (Year 3 of Phase II) is shown in Annexure D. | 5394 | 72823.3 | -67429.3 | 1104361.5 | 807737.64 | 296623.86
1b. Disbursements to sub-recipients | 81605 | 168764.6 | -87159.6 | Yes | The SRs achieved 207% burn rate at Q12 end, i.e. total expenditure of USD 168,764.60 against the corresponding budget of USD 81,605.00. Out of this, 15% budget (USD 11,945.00) is fully or partially implemented, while 84% (USD 68,800.00) of the budget has been implemented in Q11, and only 1% (USD 860) of the budget related to M&E activities (SDA 1.1.10) remains unimplemented in Q12 end. Detailed analysis is shown in Annexure -C. | 980475 | 923391.07 | 57083.93 | The cumulative absorption rate of the SRs at Q12 end is 94% of the corresponding budget amounting to USD 980,475.00 and the cumulative variance works out 6% (USD 57,083.99). Out of this, only 16% (USD 8,950) pertains to Phase II activities while 84% (USD 48,134) is the balance amount which is carried over from Phase I activities. The un-implemented Phase II activities are- building up library resource (2.1.1) USD 4,000, and attend FGATM meeting USD 4,950 (2.1.3 and 1.1.9) respectively. | 81605 | 168764.6 | -87159.6 | 977023 | 916256.44 | 60766.56
2. Health product expenditures vs. budget (already included in "Total actual" figures above) | 0 | 0 | 0 | No | There were no procurement of Health Products expenditure in Q12. | 589919 | 297167.28 | 292751.72 |  | 0 | 0 | 0 | 264000 | 123807.6 | 140192.4
2a. Pharmaceuticals | 0 | 0 | 0 | No | There is no budget for procurement of Pharmaceuticals in Q12. | 250000 | 133300.14 | 116699.86 | Budget is not utilised in Phase II as the PSM plan is not approved for purchase of Pharmaceuticals. | 0 | 0 | 0 | 49500 | 16927 | 32573
2b. Health products, commodities and equipment | 0 | 0 | 0 | No | There is no budget for procurement of Health Products expenditure in Q12. | 339919 | 163867.14 | 176051.86 | Budget is not utilised in Phase II as the PSM plan is not approved for purchase of Health products and equipments. | 0 | 0 | 0 | 214500 | 106880.6 | 107619.4
Program expenditures were used for the procurement of health products: |  |  |  | No
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | N/A
1 If the LFA makes a correction to the actual expenditures for the reporting period, the LFA should also make a corresponding correction to the PR's requested amount in LFA Section 4.A.1

## Annexure B
Annexure-B
Cash Flow Statement - Q12 (November- Dec- Jan )
Particulars | USD
Cash Inflow
Disbursement received from GFATM | 0
Opening Cash in hand | 6.24
Opening Bank | 259442.02
Total Inflow - A | 259448.26
Cash Outflow
Actual expenditure for the period (PR) | 72823.2976
Actual disbursement to SRs for the period | 168764.5956
Total Outflow - B | 241587.8932
Balance (A-B) | 17860.3668
Representation by
Balance at DPA
Bank Balance at MoH | 17860.37
Cash balance | 0
Total Fund at Q12 end* | 17860.37
* The fund balance does not include the last disbursement received from the GFATM on 17 February 2011 amounting to USD 276,261.00

## Annexure C
Annexure- C
| Variance Analysis by Line items- Q12 (NDJ 2011). | Amounts in USD
|  |  | Budget | Expenditure | Variance | LFA Comment
SDA 1.1: Providing life-skills-based HIV/AIDS education in schools |  | PR/SR
1.1.1 | TOT on Life Skill Education in 3 regions (Western, Central,Southern ) - 5 days training program each for region | SR | 10085 | 30254.0009 | -20169.0009 | The excess expenditure relates to Q 9 and Q11 budget paid in Q12
1.1.2 | Support to TOT in the implementation of further training of teachers in their communities/districts (5-day training). | SR |  | 42988.8746 | -42988.8746 | Q10 and Q11 budget implemented in Q12
1.1.3 | Purchase of Television & DVD for the schools. - 30 sets required | SR |  | 12000 | -12000 | Q9 budget implemented in Q12
1.1.4 | Purchase of sound syetem (Ahuja) | SR |  | 5850 | -5850 | Q9 budget implemented in Q12
1.1.5 | Purchase of LCD Projector with desktop computer | SR |  | 4500 | -4500 | Q9 budget implemented in Q12
1.1.6 | Sound proofing of the Auditorium | SR |  | 0 | 0
1.1.7 | Purchase of wall mounted projector scerr 119" | SR |  | 450 | -450 | Q9 budget implemented in Q12
1.1.8 | Purchase of Plasma TV | SR |  | 3150 | -3150 | Q9 budget implemented in Q12
1.1.9 | Attend regional GFATM meetings | SR |  |  | 0
1.1.10 | Monitoring and evaluation | SR | 860 |  | 860
| Subtotal SDA 1.1 |  | 10945 | 99192.8755 | -88247.8755
SDA 1.2: Providing life-skills-based HIV/AIDS education
1.2.1 | Development & Printing of educational materials(TLM- teaching learning materials) | SR |  | 0 | 0
1.2.2 | Training of Teachers/Principals | SR |  | 0 | 0
1.2.3 | Community activities by youth NFE learners | SR | 68800 | 0 | 68800 | implemented in Q11
1.2.4 | Attend regional GFATM meetings | SR |  | 2250 | -2250 | Q9 budget implemented in Q12
1.2.5 | Refresher ToT for Vocational Centre teachers | SR |  | 0 | 0
1.2.6 | Sensitization of unemployed youths and job seekers during the job fairs and NGOP | SR |  | 0 | 0
1.2.7 | Attend regional GFATM meetings | SR |  | 2250 | -2250 | Q9 budget implemented in Q12
| Subtotal SDA 1.2 |  | 68800 | 4500 | 64300
SDA 1.3: Reaching youth through the private sector
1.3.1 | Sensitization of private sectors in 5 towns | SR |  | 3450 | -3450 | Q10 budget implemented in Q12
1.3.2 | Printing of education materials and products | PR |  | 0 | 0
1.3.3 | Ex-country training for the focal person on HIV programming | PR |  | 0 | 0
1.3.4 | Ex-change of experience among private sectors | PR |  | 2225 | -2225 | Q10 budget implemented in Q12
| Subtotal SDA 1.3 |  | 0 | 2225 | -2225
SDA 1.4: Establishing youth-friendly health services in 30 hospitals
1.4.1 | Training/refresher of staff about youth-issues | PR |  | 1824.4223 | -1824.4223 | Q11 budget partially implemented in Q12
1.4.2 | Telephone line charges | PR | 474 | 328.006 | 145.994 | Regualar quarterly budget
1.4.3 | Ex-country training for Youth-hotline staff | PR |  | 8680 | -8680 | Q11 budget partially implemented in Q12
| Subtotal SDA 1.4 |  | 474 | 10832.4283 | -10358.4283
SDA 1.5: Intensifying HIV prevention among Military Personnels
1.5.1 | Development and Printing of HIV information package | SR |  | 1000 | -1000 | Q9 budget implemented in Q12
1.5.2 | Capacity building of women police volunteers | SR |  | 4818.1429 | -4818.1429 | Q9 budget implemented in Q12
1.5.3 | Sensitization of staff at different levels by RBP | SR |  | 5358.3654 | -5358.3654 | Q10 & Q11 budget implemented in Q12
1.5.4 | Sensitization program for RBA & RBG | SR |  | 2503.2092 | -2503.2092 | Q9 budget implemented in Q12
1.5.5 | Awareness program in prisons | SR |  | 3598.6307 | -3598.6307 | Q11 budget partially implemented in Q12
1.5.6 | Training of instructors from the Military training institutes (RBP, RBG, RBA) | SR |  | 5990.5862 | -5990.5862 | Q11 budget partially implemented in Q12
1.5.7 | Attend regional GFATM meetings (for focal persons) | SR |  | 8634.3603 | -8634.3603 | Q9 & Q10 budget implemented in Q12
| Subtotal SDA 1.5 |  | 0 | 31903.2948 | -31903.2948
SDA 1.6: Increasing HIV awareness among members of faith-based organizations
1.6.1 | Cascade Training for Shedras/Lobdras/ community religious practitioners | SR |  | 9092.8541 | -9092.8541 | Q10 budget implemented in Q12
1.6.2 | Purchase of 1 laptop and 1 projector | SR |  | 2625.1605 | -2625.1605 | Q9 budget implemented in Q12
1.6.3 | Exchange programme | SR |  | 10727.4283 | -10727.4283 | Q11 budget partially implemented in Q12
1.6.4 | Annual review meeting | SR | 1860 | 1829.2683 | 30.7317 | The variance is not material
| Subtotal SDA 1.6 |  | 1860 | 24274.7112 | -22414.7112
SDA 1.7: Providing services for CSWs, IDUs, and MSMs through NGOs
1.7.1 | IDU outreach services through sub grantee community organization | PR |  | 5546.4484 | -5546.4484 | Q9 & Q10 budget implemented in Q12
1.7.2 | SW outreach services through sub grantee community | PR |  | 5372 | -5372 | Q9 budget implemented in Q12
| Subtotal SDA 1.7 |  | 0 | 10918.4484 | -10918.4484
SDA 1.8: Expanding prevention packages to the BHU and the community level with CT services to two additional VCT centers, 176 BHUs and 16 army health units
1.8.1 | Rent two VCT centres | PR | 999 | 1775 | -776 | The excess amount pertains to Q9 budget implemented in Q12
1.8.2 | Procurement of computers & printers for the two VCT centers | PR |  | 639.2811 | -639.2811 | Q9 budget implemented in Q12
1.8.3 | Test kits and vacutainers | PR |  | 8645.6996 | -8645.6996 | Q11 budget partially implemented in Q12
1.8.4 | Procurement of CD4 reagenst | PR |  |  | 0
| Subtotal SDA 1.8 |  | 999 | 11059.9807 | -10060.9807
SDA 1.9 IEC activities
1.9.1 | Consultative meeting to develop IEC materials for vulnerable groups | PR |  | 718.1857 | -718.1857 | Q9 budget implemented in Q12
1.9.2 | Field testing of the materials | PR |  | 64.3132 | -64.3132 | Q9 budget implemented in Q12
1.9.3 | Printing of materials for vulnerable groups | PR |  | 3415.7681 | -3415.7681 | Q10 budget implemented in Q12
1.9.4 | Sensitization and Breifing to the Media personnel on HIV/AIDS issues | PR |  | 1245.4472 | -1245.4472 | Q10 budget implemented in Q12
1.9.5 | Undertake supervision and monitoring visits | PR | 450 |  | 450
| Subtotal SDA 1.9 |  | 450 | 5443.7142 | -4993.7142
SDA 2.1: Strengthening STI/HIV/AIDS pre-service training and continuous education at the Royal Institute of Health Sciences.
2.1.1 | Build up library resources | SR |  |  | 0
2.1.2 | Faculty development - continuning education for lecturers on STI & HIV/AIDS | SR |  |  | 0
2.1.3 | Attend Global Fund meeting | SR |  |  | 0
2.1.4 | Refurbishment of classrooms | SR |  |  | 0
| Subtotal SDA 2.1 |  | 0 | 0 | 0
SDA 2.2: Strengthening national capacity for programme monitoring and evaluation
2.2.1 | Hire M&E consultant in MOH | PR | 1950 | 0 | 1950
2.2.2 | Master in epidemiology | PR |  | 758.344 | -758.344 | Long term study budget provided in Q9
2.2.3 | Undertake supervision and monitoring visits | PR | 1251 | 408.9431 | 842.0569
2.2.4 | Send program staff to international forum for information exchange and attend regional meetings of GFATM | PR |  | 7544.0843 | -7544.0843 | Q9 & Q10 budget implemented in Q12
2.2.5 | Training one support staff from NACP on data punching, record keeping | PR |  | 4711.4089 | -4711.4089 | Q10 budget implemented in Q12
2.2.6 | Quarterly meeting of stakeholders | PR | 270 | 84.0822 | 185.9178
| Subtotal SDA 2.2 |  | 3471 | 13506.8624 | -10035.8624
SDA 2.3: Strengthening the management and technical capacity of the NACP
2.3.1 | Diploma in finance management of HIV/AIDS project | PR |  | 1350.5777 | -1350.5777 | Q9 budget implemented in Q12
2.3.2 | Building a local pool of expertise in key technical areas | PR |  | 15000 | -15000 | Q10 budget implemented in Q12
| Subtotal SDA 2.3 |  | 0 | 16350.5777 | -16350.5777
SDA 2.4: Building the capacity of non-govermental sectors as partner in the national HIV/AIDS response
2.4.1 | Exchange programme for PLHA | PR |  | 7930 | -7930 | Q11 budget partially implemented in Q12
| Subtotal SDA 2.4 |  | 0 | 7930 | -7930
SDA 3. Ensuring care & treatment
3.1 | Procurement of ARVs | PR |  |  | 0
| TOTAL PROGRAM COSTS |  | 86999 | 241587.8932 | -154588.8932
Analysis
|  |  | PR | SR | Total
| Budget allocation for Q12 |  | 5394 | 81605 | 86999
| Current budget fully or partially implemented for Q12 |  | 2994 | 11945 | 14939
| Q12 budget not implemented |  | 2400 | 860 | 3260
| Q 12 budget implemented in Q11 |  |  | 68800 | 68800
| % Q12 budget fully or partially implemented |  | 55.51% | 14.64% | 17.17%
| % Q12 budget not implemented |  | 44.49% | 84.31% | 3.747%
Expenditure Analysis
| Total Expenditure |  | 72823.2976 | 168764.5956 | 241587.8932
| Total Expenditure related to Q12 |  | 2596.0312 | 32083.2691 | 34679.3004
| Total Expenditure related to other quarters |  | 70227.2664 | 136681.3265 | 206908.5929
| % Budgeted expenditure |  | 3.565% | 19.01% | 14.35%
| % Expenditure related to other qtrs. |  | 96.44% | 80.99% | 85.65%
| Overall variance |  | -67429.2976 | -87159.5956 | -154588.8932
| % Varainace |  | -1250% | -106.8% | -177.7%
| Q12 absorption rate (%) |  | 1350% | 206.8% | 277.7%

## Annexure D
Annexure D
Analysis of cumulative variances by Line Items from Q9-Q12
| Objectives / Service Delivery Areas (SDAs) |  | FMA |  |  | MJJ |  |  | ASO |  |  | NDJ |  |  | Analysis of Cu variance up to Q12 end
|  | PR/SR | Qtr 9 | EXP. | Variance | Qtr 10 | EXP. | Variance | Qtr 11 | EXP. | Variance | Qtr 12 | EXP. | Variance | CU. Budget | CU. Exp. | Cu. Variance | % Variance
SDA 1.1: Providing life-skills-based HIV/AIDS education in 140 schools (grade 7 and above) |  | DYS | [16 empty] | LFA Comments
1.1.1 | TOT on Life Skill Education in 3 regions (Western, Central,Southern ) - 5 days training program each for region |  | 10085 | 3806.69 | 6278.31 |  |  | 0 | 10085 |  | 10085 | 10085 | 30254.0009 | -20169.0009 | 30255 | 34060.6909 | -3805.6909 | -12.58% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.1.2 | Support to TOT in the implementation of further training of teachers in their communities/districts (5-day training). |  |  |  | 0 | 21495 |  | 21495 | 21495 |  | 21495 |  | 42988.8746 | -42988.8746 | 42990 | 42988.8746 | 1.1254 |  | The variance is not immaterial
1.1.3 | Purchase of Television & DVD for the schools. - 30 sets required |  | 12000 |  | 12000 |  | 3627.28 | -3627.28 |  |  | 0 |  | 12000 | -12000 | 12000 | 15627.28 | -3627.28 | -30.23% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.1.4 | Purchase of sound syetem (Ahuja) |  | 5850 |  | 5850 |  |  | 0 |  |  | 0 |  | 5850 | -5850 | 5850 | 5850 | 0
1.1.5 | Purchase of LCD Projector with desktop computer |  | 4500 |  | 4500 |  |  | 0 |  |  | 0 |  | 4500 | -4500 | 4500 | 4500 | 0
1.1.6 | Sound proofing of the Auditorium |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
1.1.7 | Purchase of wall mounted projector scerr 119" |  | 450 |  | 450 |  |  | 0 |  |  | 0 |  | 450 | -450 | 450 | 450 | 0
1.1.8 | Purchase of Plasma TV |  | 3150 |  | 3150 |  |  | 0 |  |  | 0 |  | 3150 | -3150 | 3150 | 3150 | 0
1.1.9 | Attend regional GFATM meetings |  | 2250 |  | 2250 |  |  | 0 |  |  | 0 |  |  | 0 | 2250 | 0 | 2250 |  | GFATM meeting not yet attended
1.1.10 | Monitoring and evaluation |  |  | 11500 | -11500 | 860 |  | 860 |  |  | 0 | 860 |  | 860 | 1720 | 11500 | -9780 | -568.6% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 1.1 |  | 38285 | 15306.69 | 22978.31 | 22355 | 3627.28 | 18727.72 | 31580 | 0 | 31580 | 10945 | 99192.8755 | -88247.8755 | 103165 | 118126.8455 | -14961.8455
SDA 1.2: Providing life-skills-based HIV/AIDS education | [16 empty] | 0
1.2.1 | Development & Printing of educational materials(TLM- teaching learning materials) | NFE | 5000 |  | 5000 |  |  | 0 |  | 5003.24 | -5003.24 |  | 0 | 0 | 5000 | 5003.24 | -3.24 |  | The variance is immaterial
1.2.2 | Training of Teachers/Principals | NFE | 18580 |  | 18580 | 18580 |  | 18580 |  | 37159.99 | -37159.99 |  | 0 | 0 | 37160 | 37159.99 | 0.01 |  | The variance is immaterial
1.2.3 | Community activities by youth NFE learners | NFE |  | 2048.54 | -2048.54 |  |  | 0 |  | 68800 | -68800 | 68800 | 0 | 68800 | 68800 | 70848.54 | -2048.54 | -2.978% | The variance is immaterial
1.2.4 | Attend regional GFATM meetings | NFE | 2250 |  | 2250 |  |  | 0 |  |  | 0 |  | 2250 | -2250 | 2250 | 2250 | 0 |  | GFATM meeting not yet attended
1.2.5 | Refresher ToT for Vocational Centre teachers | MoLHR | 5660 |  | 5660 |  |  | 0 |  | 5659.99 | -5659.99 |  | 0 | 0 | 5660 | 5659.99 | 0.01 |  | The variance is im-material
1.2.6 | Sensitization of unemployed youths and job seekers during the job fairs and NGOP | MoLHR |  |  | 0 |  |  | 0 | 6960 | 6956.69 | 3.31 |  | 0 | 0 | 6960 | 6956.69 | 3.31 |  | The variance is im-material
1.2.7 | Attend regional GFATM meetings | MoLHR | 2250 |  | 2250 |  |  | 0 |  |  | 0 |  | 2250 | -2250 | 2250 | 2250 | 0 |  | GFATM meeting not yet attended
1.2.8 | M & E |  |  | 8598.33 | -8598.33 |  |  | 0 |  |  | 0 |  |  | 0 |  | 8598.33 | -8598.33 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 1.2 |  | 33740 | 10646.87 | 23093.13 | 18580 | 0 | 18580 | 6960 | 123579.91 | -116619.91 | 68800 | 4500 | 64300 | 128080 | 138726.78 | -10646.78
SDA 1.3: Reaching youth through the private sector |  |  |  |  | 0
1.3.1 | Sensitization of private sectors in 5 towns | BCCI |  | 4535.19 | -4535.19 | 3450 | 345.81 | 3104.19 |  |  | 0 |  | 3450 | -3450 | 3450 | 8331 | -4881 | -141.5% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.3.2 | Printing of education materials and products |  | 5000 |  | 5000 |  |  | 0 |  | 3438.94 | -3438.94 |  | 0 | 0 | 5000 | 3438.94 | 1561.06 | 31.22% | Activity completed, the amount represents saving.
1.3.3 | Ex-country training for the focal person on HIV programming |  | 3610 |  | 3610 |  |  | 0 |  | 3487.38 | -3487.38 |  | 0 | 0 | 3610 | 3487.38 | 122.62 | 3.397% | variance not material
1.3.4 | Ex-change of experience among private sectors |  |  | 7993.05 | -7993.05 | 2225 |  | 2225 |  |  | 0 |  | 2225 | -2225 | 2225 | 10218.05 | -7993.05 | -359.2% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 1.3 |  | 8610 | 12528.24 | -3918.24 | 5675 | 345.81 | 5329.19 | 0 | 6926.32 | -6926.32 | 0 | 5675 | -5675 | 14285 | 25475.37 | -11190.37
SDA 1.4: Establishing youth-friendly health services in 30 hospitals |  | NACP
1.4.1 | Training/refresher of staff about youth-issues |  |  | 153.56 | -153.56 |  | 144.77 | -144.77 | 6780 | 5283.74 | 1496.26 |  | 1824.4223 | -1824.4223 | 6780 | 7406.4923 | -626.4923 | -9.24%
1.4.2 | Telephone line charges |  | 474 | 1247.73 | -773.73 | 474 | 1554.76 | -1080.76 | 474 | 966.04 | -492.04 | 474 | 328.006 | 145.994 | 1896 | 4096.536 | -2200.536 | -116.1% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.4.3 | Ex-country training for Youth-hotline staff |  |  |  | 0 |  |  | 0 | 8680 |  | 8680 |  | 8680 | -8680 | 8680 | 8680 | 0
1.4.2 | WHO Guidelines |  |  | 1240.42 | -1240.42 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1240.42 | -1240.42 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.4.7 | Training HIV core Team at JDWNRH |  |  | 5495.74 | -5495.74 |  |  | 0 |  |  | 0 |  |  | 0 |  | 5495.74 | -5495.74 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 1.4 |  | 474 | 8137.45 | -7663.45 | 474 | 1699.53 | -1225.53 | 15934 | 6249.78 | 9684.22 | 474 | 10832.4283 | -10358.4283 | 17356 | 26919.1883 | -9563.1883
SDA 1.5: Intensifying HIV prevention among 10,000 uniformed personnel and their families |  | RBG/RBP
1.5.1 | Development and Printing of HIV information package |  | 3000 | 819.85 | 2180.15 |  |  | 0 |  |  | 0 |  | 1000 | -1000 | 3000 | 1819.85 | 1180.15 |  | Activity completed, the amount represents saving.
1.5.2 | Capacity building of women police volunteers |  | 4820 |  | 4820 |  |  | 0 |  |  | 0 |  | 4818.1429 | -4818.1429 | 4820 | 4818.1429 | 1.8571
1.5.3 | Sensitization of staff at different levels by RBP |  |  |  | 0 | 2517.5 |  | 2517.5 | 2518 |  | 2518 |  | 5358.3654 | -5358.3654 | 5035.5 | 5358.3654 | -322.8654 | -6.412% | Variance not material
1.5.4 | Sensitization program for RBA & RBG |  | 2517.5 |  | 2517.5 | 2517.5 |  | 2517.5 |  |  | 0 |  | 2503.2092 | -2503.2092 | 5035 | 2503.2092 | 2531.7908 |  | Activity completed, the amount represents saving.
1.5.5 | Awareness program in prisons |  |  |  | 0 |  |  | 0 | 3600 |  | 3600 |  | 3598.6307 | -3598.6307 | 3600 | 3598.6307 | 1.3693
1.5.6 | Training of instructors from the Military training institutes (RBP, RBG, RBA) |  |  |  | 0 | 5095 |  | 5095 |  |  | 0 |  | 5990.5862 | -5990.5862 | 5095 | 5990.5862 | -895.5862 | -17.58% | The activity completed but 18% budget overspent due to new training programs included.
1.5.7 | Attend regional GFATM meetings (for focal persons) |  | 5000 |  | 5000 |  |  | 0 | 5000 |  | 5000 |  | 8634.3603 | -8634.3603 | 10000 | 8634.3603 | 1365.6397 |  | Activity completed, the amount represents saving.
1.5.8 | M & E Survey |  |  | 787.26 | -787.26 |  |  | 0 |  |  | 0 |  |  | 0 |  | 787.26 | -787.26 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 1.5 |  | 15337.5 | 1607.11 | 13730.39 | 10130 | 0 | 10130 | 11118 | 0 | 11118 | 0 | 31903.2948 | -31903.2948 | 36585.5 | 33510.4048 | 3075.0952 |  | 0
SDA 1.6: Increasing HIV awareness among members of faith-based organizations |  | Dratshang
1.6.1 | Cascade Training for Shedras/Lobdras/ community religious practitioners |  |  |  | 0 | 9235 |  | 9235 |  |  | 0 |  | 9092.8541 | -9092.8541 | 9235 | 9092.8541 | 142.1459 |  | Activity completed, the amount represents saving.
1.6.2 | Purchase of 1 laptop and 1 projector |  | 2669 |  | 2669 |  |  | 0 |  |  | 0 |  | 2625.1605 | -2625.1605 | 2669 | 2625.1605 | 43.8395 |  | Activity completed, the amount represents saving.
1.6.3 | Exchange programme |  |  | 1132.93 | -1132.93 |  |  | 0 | 10900 |  | 10900 |  | 10727.4283 | -10727.4283 | 10900 | 11860.3583 | -960.3583 | -8.811% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.6.4 | Annual review meeting |  |  |  | 0 |  |  | 0 |  |  | 0 | 1860 | 1829.2683 | 30.7317 | 1860 | 1829.2683 | 30.7317 |  | Activity completed, the amount represents saving.
| Subtotal SDA 1.6 |  | 2669 | 1132.93 | 1536.07 | 9235 | 0 | 9235 | 10900 | 0 | 10900 | 1860 | 24274.7112 | -22414.7112 | 24664 | 25407.6412 | -743.6412 |  | 0
SDA 1.7: Providing services for CSWs, IDUs, and MSMs through NGOs |  | NACP |  |  | 0
1.7.1 | IDU outreach services through sub grantee community organization |  | 2000 | 1020.81 | 979.19 | 6000 | 127.85 | 5872.15 |  | 106.97 | -106.97 |  | 5546.4484 | -5546.4484 | 8000 | 6802.0784 | 1197.9216 |  | Activity completed, the amount represents saving.
1.7.2 | SW outreach services through sub grantee community |  | 8000 |  | 8000 |  |  | 0 |  |  | 0 |  | 5372 | -5372 | 8000 | 5372 | 2628 |  | Activity completed, the amount represents saving.
| Subtotal SDA 1.7 |  | 10000 | 1020.81 | 8979.19 | 6000 | 127.85 | 5872.15 | 0 | 106.97 | -106.97 | 0 | 10918.4484 | -10918.4484 | 16000 | 12174.0784 | 3825.9216 | 0
SDA 1.8: Expanding prevention packages to the BHU and the community level with CT services to two additional VCT centers, 176 BHUs and 16 army health units |  | NACP |  |  | 0
1.8.1 | Rent two VCT centres |  | 999 |  | 999 | 999 | 2624.13 | -1625.13 | 999 |  | 999 | 999 | 1775 | -776 | 3996 | 4399.13 | -403.13 | -10.09%
1.8.2 | Procurement of computers & printers for the two VCT centers |  | 3982 |  | 3982 |  |  | 0 |  |  | 0 |  | 639.2811 | -639.2811 | 3982 | 639.2811 | 3342.7189 |  | The PR did not make procurement as planned.
1.8.3 | Test kits and vacutainers |  |  | 21810.6 | -21810.6 |  | 1973.98 | -1973.98 | 21750 |  | 21750 |  | 8645.6996 | -8645.6996 | 21750 | 32430.2796 | -10680.2796 | -49.1% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.8.4 | Procurement of CD4 reagenst |  |  |  | 0 | 13750 |  | 13750 |  |  | 0 |  |  | 0 | 13750 | 0 | 13750 |  | Procurement not done as the GFATM did not approve PSM plan.
1.8.6 | Purchase of Elisa Readers |  |  | 1710.84 | -1710.84 |  | 21840.59 | -21840.59 |  |  | 0 |  |  | 0 |  | 23551.43 | -23551.43 |  | Procurement not done as the GFATM did not approve PSM plan.
1.8.10 | Ex-country training of councilors |  |  |  | 0 |  | 5159.92 | -5159.92 |  |  | 0 |  |  | 0 |  | 5159.92 | -5159.92 |  | Spill over activity of Phase 1 implemented in Q10.
| Subtotal SDA 1.8 |  | 4981 | 23521.44 | -18540.44 | 14749 | 31598.62 | -16849.62 | 22749 | 0 | 22749 | 999 | 11059.9807 | -10060.9807 | 43478 | 66180.0407 | -22702.0407
SDA 1.9 IEC activities |  | NACP |  |  | 0
1.9.1 | Consultative meeting to develop IEC materials for vulnerable groups |  | 984 | 0 | 984 |  | 899.04 | -899.04 |  |  | 0 |  | 718.1857 | -718.1857 | 984 | 1617.2257 | -633.2257 | -64.35% | The excess expenditure resulted from implementing Phase I spill over activities in Q9, However, the absolute amount is not substantial.
1.9.2 | Field testing of the materials |  | 338 | 3207.97 | -2869.97 |  |  | 0 |  |  | 0 |  | 64.3132 | -64.3132 | 338 | 3272.2832 | -2934.2832 | -868.1% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.9.3 | Printing of materials for vulnerable groups |  |  | 1736.25 | -1736.25 | 10000 |  | 10000 |  | 2620.88 | -2620.88 |  | 3415.7681 | -3415.7681 | 10000 | 7772.8981 | 2227.1019 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.9.4 | Sensitization and Breifing to the Media personnel on HIV/AIDS issues |  |  | 18718.72 | -18718.72 | 3680 | 433.97 | 3246.03 |  |  | 0 |  | 1245.4472 | -1245.4472 | 3680 | 20398.1372 | -16718.1372 | -454.3% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.9.5 | Undertake supervision and monitoring visits |  | 450 | 2985.27 | -2535.27 |  | 251.87 | -251.87 |  |  | 0 | 450 |  | 450 | 900 | 3237.14 | -2337.14 | -259.7% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.9.6 | M & E |  |  | 24302.99 | -24302.99 |  |  | 0 |  |  | 0 |  |  | 0 |  | 24302.99 | -24302.99 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 1.9 |  | 1772 | 50951.2 | -49179.2 | 13680 | 1584.88 | 12095.12 | 0 | 2620.88 | -2620.88 | 450 | 5443.7142 | -4993.7142 | 15902 | 60600.6742 | -44698.6742
SDA 2.1: Strengthening STI/HIV/AIDS pre-service training and continuous education at the Royal Institute of Health Sciences. |  | RIHS |  |  | 0
2.1.1 | Build up library resources |  | 4000 |  | 4000 |  |  | 0 |  |  | 0 |  |  | 0 | 4000 | 0 | 4000 |  | Budget reappropriated for activity 2.1.4 and is planned to implement in Q13.
2.1.2 | Faculty development - continuning education for lecturers on STI & HIV/AIDS |  |  |  | 0 | 9000 |  | 9000 |  | 9000 | -9000 |  |  | 0 | 9000 | 9000 | 0
2.1.3 | Attend Global Fund meeting |  | 2700 |  | 2700 |  |  | 0 |  |  | 0 |  |  | 0 | 2700 | 0 | 2700 |  | Budget reappropriated for activity 2.1.4 and is planned to implement in Q13.
2.1.4 | Refurbishment of classrooms |  |  |  | 0 | 4500 |  | 4500 |  | 4500 | -4500 |  |  | 0 | 4500 | 4500 | 0
| Subtotal SDA 2.1 |  | 6700 | 0 | 6700 | 13500 | 0 | 13500 | 0 | 13500 | -13500 | 0 | 0 | 0 | 20200 | 13500 | 6700 | 0
SDA 2.2: Strengthening national capacity for programme monitoring and evaluation |  | NACP |  |  | 0
2.2.1 | Hire M&E consultant in MOH |  | 1950 | 868.81 | 1081.19 | 1950 |  | 1950 | 1950 |  | 1950 | 1950 | 0 | 1950 | 7800 | 868.81 | 6931.19 |  | The PR not able to hire international consultant as planned.
2.2.2 | Master in epidemiology |  | 25000 |  | 25000 | 25000 |  | 25000 |  |  | 0 |  | 758.344 | -758.344 | 50000 | 758.344 | 49241.656 |  | Candidate identified and planned to implement in Q13.
2.2.3 | Undertake supervision and monitoring visits |  | 1251 | 6010.32 | -4759.32 | 1251 | 32.19 | 1218.81 | 1251 | 946.73 | 304.27 | 1251 | 408.9431 | 842.0569 | 5004 | 7398.1831 | -2394.1831 | -47.85% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
2.2.4 | Send program staff to international forum for information exchange and attend regional meetings of GFATM |  | 8100 | 3587.12 | 4512.88 |  |  | 0 | 8100 |  | 8100 |  | 7544.0843 | -7544.0843 | 16200 | 11131.2043 | 5068.7957 |  | Activity completed, the amount represents saving.
2.2.5 | Training one support staff from NACP on data punching, record keeping |  |  |  | 0 | 4580 | 133.58 | 4446.42 |  |  | 0 |  | 4711.4089 | -4711.4089 | 4580 | 4844.9889 | -264.9889 | -5.786% | Variance not material.
2.2.6 | Quarterly meeting of stakeholders |  | 270 |  | 270 | 270 |  | 270 | 270 | 928.06 | -658.06 | 270 | 84.0822 | 185.9178 | 1080 | 1012.1422 | 67.8578 |  | Variance not material.
2.2.10 | PCM meeting |  |  | 1282.97 | -1282.97 |  | 2467.62 | -2467.62 |  |  | 0 |  |  | 0 |  | 3750.59 | -3750.59 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
2.2.13 | KAP Survey |  |  | 16661.6 | -16661.6 |  | 29070.62 | -29070.62 |  |  | 0 |  |  | 0 |  | 45732.22 | -45732.22 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 2.2 |  | 36571 | 28410.82 | 8160.18 | 33051 | 31704.01 | 1346.99 | 11571 | 1874.79 | 9696.21 | 3471 | 13506.8624 | -10035.8624 | 84664 | 75496.4824 | 9167.5176
SDA 2.3: Strengthening the management and technical capacity of the NACP |  | NACP
2.3.1 | Diploma in finance management of HIV/AIDS project |  | 11210 |  | 11210 |  |  | 0 |  | 14302.44 | -14302.44 |  | 1350.5777 | -1350.5777 | 11210 | 15653.0177 | -4443.0177 | -39.63% | The activity completed and the expenditure exceeded budget due to increase in SDA rate.
2.3.2 | Building a local pool of expertise in key technical areas |  |  | 17625.95 | -17625.95 | 15000 | 3880.63 | 11119.37 |  |  | 0 |  | 15000 | -15000 | 15000 | 36506.58 | -21506.58 | -143.4% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 2.3 |  | 11210 | 17625.95 | -6415.95 | 15000 | 3880.63 | 11119.37 | 0 | 14302.44 | -14302.44 | 0 | 16350.5777 | -16350.5777 | 26210 | 52159.5977 | -25949.5977 |  | 0
SDA 2.4: Building the capacity of non-govermental sectors as partner in the national HIV/AIDS response |  | NACP |  |  | 0
2.4.1 | Exchange programme for PLHA |  |  | 8489.25 | -8489.25 |  | 3653.89 | -3653.89 | 7930 |  | 7930 |  | 7930 | -7930 | 7930 | 20073.14 | -12143.14 | -153.1% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
2.4.4 | Workshop |  |  | 27508.1 | -27508.1 |  |  | 0 |  |  | 0 |  |  | 0 |  | 27508.1 | -27508.1 |  | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Subtotal SDA 2.4 |  | 0 | 35997.35 | -35997.35 | 0 | 3653.89 | -3653.89 | 7930 | 0 | 7930 | 0 | 7930 | -7930 | 7930 | 47581.24 | -39651.24
SDA 3. Ensuring care & treatment |  | NACP |  |  | 0
3.1 | Procurement of ARVs |  |  |  | 0 |  | 13640.39 | -13640.39 | 40419 |  | 40419 |  |  | 0 | 40419 | 13640.39 | 26778.61 |  | Procurement not done as the GFATM did not approve PSM plan.
| TOTAL PROGRAM COSTS |  | 170349.5 | 206886.86 | -36537.36 | 162429 | 91862.89 | 70566.11 | 159161 | 169161.09 | -10000.09 | 86999 | 241587.8932 | -154588.8932 | 578938.5 | 709498.7332 | -130560.2332
Analysis
| Phase 1 (Q1-8) | PR | SR | Total
| Cumulative budget at end of Q8 (Phase 1) | 620602 | 653496 | 1274098
| Cumulative expenditure at end of Q8 (Phase 1) | 504317.2 | 510178.16 | 1014495.36
| Cumulative variance at end of Q8 (Phase 1) | 116284.8 | 143317.84 | 259602.64
Phase 2 (Q9-12)
| Cumulative budget for Q9-12 | 251959 | 326979 | 578938
| Cumulative expenditure for Q9-12 | 296285.78 | 413212.94 | 709498.72
| Cumulative variance for Q9-12 | -44326.78 | -86233.94 | -130560.72
Cumulative for Phase 1+ (Q9-12)
| Cumulative budget at end of Q12 | 872561 | 980475 | 1853036
| Cumulative expenditure at end of Q12 | 800602.98 | 923391.1 | 1723994.08
| Cumulative varaince at end of Q12 | 71958.02 | 57083.9 | 129041.92
| Expenditure as % of total budget at end of Q12 | 91.75% | 94.18% | 93.04%
| % Cumulative variance at end of Q12 | 8.247% | 5.822% | 6.964%

## LFA_Section 1D
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: |  | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: |  | 12
D. LFA RATING AND COMMENTS ON PROGRAMMATIC AND FINANCIAL PROGRESS
1. LFA's Rating of PR's overall performance (1) |  | A
2. Reasons for this Rating (including key issues and potential future risks):
Program achievement: The average percentage achievement for the seven top ten indicators is 95 % which is commendable, and average for all the indicators is 96 percent which is also very high. Out of seven top indicators, the achievement for two indicators are above 100 percent and other five indicators ranges between 73.3 percent-98.7 percent. For the over all indicators, the lowest is 68 percent for uniformed personnel and thier families participating in HIV awareness workshop. The main reasons for this high success in this quarter was due to the winter school break and many of the training components especially for the teachers could be implemented without hindering the schools. The only two indicators which have not performed well are the number of students reached with life skills based HIV education and the number of uniformed personnel attending awareness workshops. While some of the SRs have begun to use the new reporting format, Dratshng Lhentshog and RBA are either not reporting in time or not at all. The PMU is coordinating the quarterly meeting between the SR and NACP, however this is yet to make its impact. Financial Achievement: The overall budget absorption rate of Q12 end is 278% of the corresponding budget of USD 86,999.00. This is mainly due to disbursement of funds to the SRs including funds for back log activities. The budget implemented (partially or fully) in Q12 amounts to 17% (USD 14,939) while 79% (USD 68,800.00) of the Q12 budget has been implemented in Q11 (Community activities by youth NFE learners) and only 4% (USD 3,260) remains un-implemented at Q12 end. Regarding expenditure, 14% (USD 34,679.30) pertains to budgeted expenditure while 86% (USD 206,908.59) relates to back log activities. The expenditure of PR is USD 2,994 out of budget of USD 5,394 and SR expenditure is USD 11,945 out of USD 81,605. However, USD 68,800 of SR budget was implemented in Q11. Without USD 68,800, the total budget for Q12 is USD 18,199 and percentage of expenditure only for Q12 would be 82 percent. Overall Rating: Since both program and financial achievement are above 90 percent, LFA provided a rating of "A2" for this quarter.
3. LFA comments on PR planned changes in the program, if any (please refer to section 1.A.v of the PR's Progress Update / Disbursement Request):
Mr Kencho, Assistant Program Officer has left for studies for a period of 18 months (Masters in Sexual Health) and this has left only two staff at the NACP. Although it manages only three activities, the program nevertheless compiles and collects all the data with relation to HIV.
4. LFA comments on data quality and reporting:
As reported earlier reporting by some of the SRs (Dratshang Lhentshog) to the PR has not been on time and in some cases (RBA) it has been very poor. The new SR reporting format is also not being used consistently by all the SRs, while supporting documents in some are missing. The PR needs to conduct more stringent oversight and ensure that SRs report in time and in the correct format. The indicator on number of people counseled and tested including provision of results has been reported correctly in this quarter.
5. LFA comments on other program results, success stories, issues or lessons learned (please refer to section 1.A.vi of the PR's Progress Update / Disbursement Request):
Coordination between PMU, SR and NACP are improving in that quarterly meeting have taken place, nevertheless few SRs continue to under perform. The RBA in particular has failed to report any of its activities and even the present results have been submitted by the PMU. By this it gives the impression that the SR is working in isolation. Awareness of the SRs on the national strategy and to work in close partenrship with the NACP and the PMU needs to be increased. There is a need for the PR to coordinate the activites of the PMU, NACP and the SRs so that activites are caried out effeciently and reporting is timely and complete. It would be most appropriate if the management of the SRs is handed over the NACP, provided that the program has additional manpower. This would enable the SRs to work in line with the national strategy as set by the NACP and also allow the program to guide and monitor the SRs. The PMU's role should be mainly in coordinating all the GF projects and also communicating between GF and the programs. The CCM is also being reformed with more participation of civil society and also having representatives from various other constituencies. The chairman will also be elected from among the new CCM members. People infected and affected with the disease in particular PLWHA are also being included in the new CCM structure.
1 - This rating should pertain to the cumulative progress (from the beginning of the Program to the end of the period covered by the Progress Update). It should take into consideration programmatic, financial and contextual factors.
- LFA ratings have been modified to be consistent with the Global Fund's new rating system. The new ratings relate to the previous ratings as follows:
New Scale |  | Old Scale
Rating | Description | Rating | Description
A | Expected or exceeding expectations | 5 | Exceptional
|  | 4 | Expected
B1 | Adequate | 3 | Minor adjustments needed
B2 | Inadequate but potential demonstrated | 2 | Major adjustments needed
|  | 1 | Little progress made
C | Unacceptable | 0 | Major program issues
Note on C10: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)

## LFA_Section 2
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number:
Disbursement Request - Period Covered: | Beginning Date: |  | End Date:
Disbursement Request - Number: | N/A
Section 2: LFA Review and Verification of the Principal Recipient's Cash Reconciliation and Disbursement Request
LFA COMMENTS ON THE CASH RECONCILIATION AND DISBURSEMENT REQUEST
1. The PR cash reconciliation is calculated correctly and is supported by a detailed Statement of Sources and Uses of Funds (i.e., Cash Flow statement): |  |  |  | Yes
Comments:
The PR has prepared the cash reconciliation statement based on the books of accounts maintained as per the government financial rules and regulations and the underlying supporting documents. The LFA verified opening balances against the closing balances of Q11 PU report and also the Cash Book. The closing bank and cash balances for Q12 have been verified against the Bank Statement and the cash book maintained by the PR. All recorded expenditures are supported with relevant documents and all payments were approved by the appropriated approving authority. Therefore, in the opinion of the LFA, the cash reconciliation is correctly prepared. The cash reconciliation statement for Q12 is shown in Annexure B.
2. The PR Cash Request is calculated correctly and is supported by appropriate current budget forecasts: |  |  |  | No
Comments:
There is no disbursement request in Q12.
3. The LFA has identified expenditures (incurred or forecasted) that should not be financed by the Global Fund: |  |  |  | No
Comments:
There is no disbursement request in Q12 and hance no expenditure forecast is made. However, in case of recorded expenditure of Q12, it has been incurred as per GFATM approved activities.
4. The LFA has identified variance between the forecasted expenditures and the original budget for the disbursement period, including variance in line items: |  |  |  | No
Comments:
There is no disbursement request in Q12.

## LFA_Section 3
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number:
Disbursement Request - Period Covered: | Beginning Date: |  | End Date:
Disbursement Request - Number: | N/A
Section 3: LFA Recommendations and Review of Progress on Previous Recommendations
A. LFA RECOMMENDATIONS FOR THE CURRENT PROGRESS UPDATE AND DISBURSEMENT REQUEST
LFA Recommendations |  |  |  | Global Fund Decisions
The PR should institute better coordination between the PMU, NACP and the SRs. There needs to be better SR management and in this regard consideration should be made on handing over the SR management to the NACP provided that the NACP has replacement staff (for those that have left for higher studies). The PMU can continue to function as the coordinating unit of GF projects. Time line: ASAP |  |  |  | decision yet to be made
All SRs should report on the agreed upon SR reporting form. The focal persons from Dratshang Lhentshog, RBA and HISC should be instructed to use the new format. The PR should also communicate and coordinate with the RBA which has not provided a singe report. Time Line: Starting Q13 |  |  |  | decision yet to be made
PR need to take faster decision for recruitment of TA for developing supervision plan and implemention of M&E activities. Timeline: As soon as possible
The achievement of the indicator " Number of uniformed personnel and thier family participating in HIV awareness workshop" is 68 percent which is the lowest ( although not bad) for this quarter need be enhanced. Besides, reporting by the RBA who carry out the activity using their own medical doctors has been poor as they have failed to submit a single report. The present report has been submitted by the M&E officer of the PMT (Project Management Unit) who visited three districts at the time of the activity being conducted.The PR needs to meet the RBA and sought out the reporting mechanism and bring the SR to send in timely reports. Timeline: Starting Q13 |  |  |  | decision yet to be made
B. LFA REVIEW OF PROGRESS ON PREVIOUS RECOMMENDATIONS CONFIRMED BY THE GLOBAL FUND
Previous Global Fund Decision |  |  |  | LFA Review of PR Progress
We would very much encourage the team to submit the progress Update on time. This would facilitate the process of a timely disbursement from the GF to your Ministry |  |  |  | PR submitted Q12 Progress Update on 22 March 2011 and due date was on 15 March 2011.
The amount that has been recommended for disbursement includes the training budget for Q12-14 which totals USD 257,241. However, usage of this budget for any training requires submission of a plan to GF. Upon receiving approval from the GF, the training budget can be used. In view of this, we would like to request your team to submit an annual training plan to the GF for approval. The official communication on this has been shared with you by the Director, Country Program |  |  |  | PR submitted Training Plan which was reviewed by LFA and was forwarded to GF on 17 March 2011. No approval was provided so far by GF
We would kindly request the PR to complete the recruitment of M&E Consultant for implementing M&E training and development of supervision plan for reporting units. We are aware there were challenges in recruiting an international consultant and your good office would like to recruit national consultant for this purpose. We would like to request you to kindly complete the recruitment process soon as M&E training is crucial for program |  |  |  | This is still a problem since PR has not been able to recruit local consultant. Now PR is discusing whether to recruit a Local consultant or to float for another tender to recruit International Consultant.
The Coordination between PMT,NACP and SRs requires further strengthening for effective implementation of the grant. We would like to request your good office to reqularize the coordination meeting between PMT, NACP and SRs |  |  |  | 12th Quarterly meeting between PMT, NACP and SRs was conducted on 15 March 2011 at MoH conference hall attended by all the SRs. LFA and CCM secretariat also attended the meeting.
The reporting templates have been developed for the SRs to report on the activities. The report needs to be submitted on the agreed upon reporting format. The focal persons from each of the SR should be trained to report using the new format. |  |  |  | All of the focal persons have been trained on using the reporting templates. However, few SRs (Dratshang, RBA and HISC) are not using the new format. This problem was highligted during the 12 Quarterly meeting and all SRs agreed to use the new format from next quarter.
The newly recruited personnel in the PMT and CCM Secretariat are required to have adequate information on the GF guidelines for effective coordination and reporting |  |  |  | The previous CCM Secretary, Mr Kinley Dorji provides in-house training to newly recruited CCM Secretariat staffs and PMT Staff on daily basis. The visit by Mr Edward Greene, FPM and Ms Fawzia Rasheed, Senior Policy Analyist, CCM unit has been very useful since they took time to explain various GF guidelines.
Note: The above decision were communicated to PR through Management letter dated 10 Feb 2011 by GF addressed to Dasho Gado Tshering, Secretary, MoH and Chairman of CCM, copied to GNHC, PMT and LFA during the fifth disbursement of USD 276,261.89

## LFA_Section 4
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office: |  |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | Ministry of Health and GNHC, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 12
Progress Update - Period Covered: |  |  | Beginning Date: | 2010-11-01 | End Date: | 2011-01-31
Progress Update - Number: |  |  | 12
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  |  | Cycle: | Semester | Number:
Disbursement Request - Period Covered: |  |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  |  | N/A
Section 4: Disbursement Recommendation and Progress Review Summary
A. DISBURSEMENT RECOMMENDATION
1. Cash amount requested by the Principal Recipient form the Global Fund for next disbursement period plus one additional quarter (amount in: USD): | [6 empty] | 0 |  | 0
2. LFA disbursement recommendation (amount in: USD):
3. Reasons for the LFA's disbursement recommendation:
B. LFA RATING
LFA's rating of PR's overall progress |  |  |  | A
C. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [7 empty] | Comments regarding verifications, if any:
| Yes | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request | [5 empty] | Verified and found to be correct
| Partially | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable). | [5 empty] | All CPs for this disbursement has been met except PR has not implemented M& E training and supervision plan for reporting units
| Yes | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement). | [5 empty] | Verified and found to be correct
| Yes | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress. | [5 empty] | Verified and found to be correct
| Yes | Exchange rate stated by Principal Recipient has been verified and is correct. | [5 empty] | The exchange rates are: First disbursement= 1 USD= Nu. 39.25; Second disbursement =1 USD =Nu. 47.841; third disbursement 1 USD= Nu. 46.04; Fourth Disbursement 1 USD= 46.74; Fifth disbursement 1USD=Nu.45.37
| Yes | Bank account information provided on the face sheet of Grant Agreement (Grant No. / Mod. No.): |  |  |  | BTN-607-G03-H | (or as otherwise | Correct
stated by the PR in its Progress Update / Disbursement Request) has been verified and is correct.
| Select | Current budget forecasts of the Principal Recipient for the next disbursement period plus one additional quarter have been reviewed for reasonableness | [5 empty] | No DR
Signed on behalf of the LFA:
Name: |  |  | Chhewang Rinzin
Title: |  |  | Finance Expert, LFA
Date and Place: |  |  | 29 March 2011, Thimphu, Bhutan
Note on E34: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)
DRAFT

## LFA_Signature (image)
OPTIONAL - insert image of LFA signature here*: (the size should not exceed the limit of cells B2:D2)
* In every case, the LFA should provide a bona fide signature (in LFA_Section 4) on the original (paper-based) LFA report, sent to the Global Fund by mail.