## PR_Cover page
On-going Progress Update and Disbursement Request
Instructions to the Principal Recipient for completing the On-going Progress Update and Disbursement Request
Progress Update
The Progress Update part of this form requires the Principal Recipient (PR) to provide:
- Past expenditure and programmatic performance information for the reporting period just ended
- An update on the progress made towards satisfaction of the conditions precedent (if any) set forth in Annex A to the Grant Agreement applicable
to the period covered by the Progress Update
- A detailed Statement of Sources and Uses of Funds (Cash Flow Statement) for the reporting period just ended
For the Statement of Sources and Uses of Funds, the PR may use its own usual format and expenditure line items as derived from its budgeting and accounting records. The Global Fund does not prescribe specific expenditure line items, but prefers that the PR's reporting format is activity-based, in conformity with the proposal's objectives and service delivery areas. The PR is expected to clearly show actual expenditures as compared to budget for both its own expenditures as well as for disbursements to sub-recipients. The Statement of Sources and Uses of Funds should support the information disclosed in this form in Section 1.C (Program Expenditures) and Section 2.A (Cash Reconciliation for Period Covered by Progress Update).
Disbursement Request
The Disbursement Request part of this form requires the PR to state the cash requirement for meeting on-going program expenditures. The disbursement requested from the Global Fund normally covers the PR's cash requirements for one reporting period, plus one additional quarter as a cash buffer, to ensure the PR has adequate cash on hand for program expenses at all times. The period covered by the Disbursement Request is the period that immediately follows the Reporting Period covered by the Progress Update (as explained above).
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Section 1A (1)
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: |  | Bhutan
Disease: |  | HIV/AIDS
Grant Number: |  | BTN-607-G03-H
Principal Recipient: |  | GROSS NATIONAL Happiness Commission, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01
Currency: |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: |  | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: |  | 4
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2009-01-01 | End Date: | 2009-06-30
Disbursement Request - Number: |  | 2
TERMS AND ACRONYMS USED IN THIS PROGRESS UPDATE AND DISBURSEMENT REQUEST HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: Programmatic and Financial Progress Update
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
Select
Select
Select
Select
Select
Select
Select
Select
Select
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Intended Yearly Targets | Actual Yearly Results | Reasons for deviation and any other comments
[6 empty] | Value | Year
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | 0.05% | 2006 | N/A | TBD | this will be determined at the 5th year of the project
Impact | HIV prevalence among uniformed personnel |  |  |  |  | 0.20% | 2006 | N/A | TBD | this will be determined at the 5th year of the project
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | TBD | N/A | N/A | TBD | The results will be determined at the end of the KAP survey
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | TBD at the end of 1st year |  | NA | TBD | Targets to be included based on Baseline survey which will be conducted at the end of year 1
Select
Select
Select
Select
Select
Select
Select
Select
Formulas:
Quarter = IF([Cycle:, row below]="Select","",IF([Cycle:, row below]="N/A","",IF(F13="","",F13+1)))

## PR_Section 1A (2)
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: |  | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: |  | 4
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Directly Tied? | Level | Baseline (if applicable) |  | Intended Targets to date | Actual Results to date | Reasons for programmatic deviation and any other comments
[8 empty] | Value | Year
1 | Prevention: BCC - community outreach | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | Yes | 0 | 0 | 2006 | 0 | 0 | The department of Youth responsible for fulfilling this indicator has conducted a consultative a work shop for the life skill based material development on HIV/AIDS. They are in the process of hiring a TA to develop the materials.Once the curriculum is developed it will be printed and integrated into the schools
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education |  |  |  | Yes | Select | 0 | 2006 | 20 | 0 | The masters trainer of 20 teachers targetted for this quarter will be met once the curriculum is developed
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  | Yes | Select | TBD |  | TBD | 0 | This will be determined through the KAP study. The PMT has evaluated CV for the M&E consultant. Once the consultant is hired the KAP study will be conduted. One of the main ToR for the consultant is to develop the protocols for the KAP study.
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings |  |  |  | Yes | Select | N/A |  | 10000 | 1505 | The Non formal education division of the ministry of education has already developed life skills based materials on HIV/AIDS for youth NFE learners during the given quarter . They are now in the process of printing the materials developed. funds were released to commemorate the world AIDS Day and from the reports recieved about 1505 people were reached by HIV/AIDS education in out of school settings . This indicator will also be met by the ministry of Labor & Human resources after they have developed the HIV/AIDS information package and distribution takes place to the out of school youhts
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  | Yes | Select | 0 | 2006 | 200 | 314 | A total of 314 NFE instructors were trained to provide HIV out of school education.(28 Master trainers trained & 286 NFE instructors trained). Additonal 114 were trained due to budget availability but in cumulative by q8 we would have met the target of 669 instructors trained
1 | Prevention: BCC - community outreach | Number of hotels, bars and entertainment outlets providing HIV prevention services |  |  |  | No | Select | 0 | 2006 | 200 | 232 | The Bhutan Chamber of Commerce & Industry have conducted sensitization work shop for the hoteliers, bar owners & entertainment outlets at Thimphu & Gelephu.This activity is also being pursued through the World Bank Project for HIV/AIDS & STI control. The SR is now in the process of training for employees of Hotels & entertianment zones on HIV/AIDS transmission & spread. The funds for the same has been processed for release from the ministry of finance.
1 | Prevention: BCC - community outreach | Number of hospitals providing youth-friendly health services |  |  |  | Yes | Select | 0 | 2006 | 30 | 40 | 20 Health staffs from hospitals been trained on provision of youth friendly health services based on the guidelines adapted from WHO& cascade training for additional 20 health workers from hospital & BHU were provided during the quarter
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  | No | Select | 6000 | 2006 | 3000 | 2057 | The RBP being one of the sub recipients have conducted 3 rounds of sensitization work shop on HIV/AIDS amongst the uniformed personnel * their families. The RBA is yet to conduct the sensitization workshop on HIV/AIDS. This indicator will be achieved in subsequent quarters. RBA has developed relevant messages on HIV/AIDS for armed forces and have also conducte the ToT on the materials developed
1 | Prevention: BCC - community outreach | Number of monks reached by HIV/AIDS education in monasteries |  |  |  | Yes | Select | 500 | 2005 | 2000 | 185 | Conducted one day work shop for 185 monks of Thimphu monsatery. The curriculum on HIV/AIDS has already been developed, training & printing done through UNICEF funding. The remaining budet will be clubbed to conduct sensitization works shop for the monks on HIV/AIDS. The indicator eill be met after the sensitization . The budget to conduct the sensitization was very low to (USD 860) not sufficent to accomodate more monks. This indicator will be met once the revised curicullum is instituted into the monsatic institutions. | 756 | 2057
1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results |  |  |  | No | Select | 1500 | 2005 | 6000 | 7226 | The report is collected & compiled from HISC & integrated VCT from all the district hospitals . It is collected on quarterly basis. The indicted figure is for a year ( Jan - dec) cumulative of 4 quarters
1 | Prevention: Testing and Counseling | Number of basic health units providing VCT services |  |  |  | No | Select | 0 | 2005 | 75 | 81 | Cumulatively 81 health workers from BHUS trained on provision of VCT services as of Dec 08.
1 | Prevention: BCC - community outreach | Number of programs (slots) aired on TV and radio on HIV and STI and BCC messages |  |  |  | No | Select | 0 |  | 72 | 0 | The quotation for airing tv & radio spots have been floated for the media firms and currently the bids are being received. Once after avaulation MoU will be signed with the firm and the radio & tv spots will be aired as targetted. The TV spots & radio HAVE ALREADY BEEN DEVELOPED.
2 | HSS: Information system & Operational research | Number of health workers trained in revised HIV data reporting and analysis |  |  |  | Yes | Select | 0 | 2005 | 140 | 158 | A total of 158 health workers were trained on revised HIV data reporting
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment |  |  |  | No | Select | 25%(19) | 2006 | 25(33%) | 29 | 29 people on HAART treatment

## PR_Section 1A & 1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: | 4
iv. Overall evaluation of performance
Over all the performance of the grant is satisfactory. During the4th quarter (Oct -Dec) . Most of the planned activties from the National HIV/AIDS control has been conducted. However the Sub Recipients are not very pro active and they don’t request for timely release of the funds thereby the financial utilization is quite low. Overall the spenind is quite remarkable this quarter as compared to previous quarters: a total of USD 199,261.43 has been spent against total budget of USD 138,810.
v. Planned changes in the program, if any.
Not many planned changes in the activties in this quarter except that due to too many TA planned in the plan only few have been recruited as hiring the right TA and also with lot of procurement rules to be followed hinders the grant implementation process.
vi. Other program results, success stories, issues or lessons learned
To coordinate with different sub recipients is a daunting task. Most of them seem to have agreed on one thiing but their cooperation is not much therer. Not getting timely reports from them. as agreed in the MoU. ALSO THERE ARE HIRING OF MANY TECHNICAL ASSISTANCE AND GETTING THE RIGHT PERSON IS ALSO A CHALLANGE. There is shortages of Human resources both in the project manngement unit and also the National AIDS programme to effectively coordinate & monitor the activties.
B. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? (Yes/No) | PR Comments
The delivery by the PR of the statement confirming the bank account into which the grant funds will be disbursed |  |  |  | Yes | This condition was fulfilled
The delivery by the PR of of a letter signed by Authorized representative of the PR seeting the name, titel & authenticated specimen signature of each person authorized to sign disbursement request |  |  |  | Yes | fulfilled
The delivery by the PR to the GF of evidence , in fomr and substance satisfactory to the Global Fund , that a project manager has been hired with appropraite qualifications & expereince |  |  |  | Yes | fulfilled
the deliveryof a completed version of the Monitoring and Evaluation Systems Strengthening Tool (Dated January 2006 and available from the Global Fund website) that has been prepared by the Principal Recipient in consultation with the Program stakeholders |  |  |  | Yes | The M&E plan has been prepared through a consultative workshop with the stakeholders. TA was provided by the WHO. The plan has not yet been delivered to GFATM as it has to be aligned to the National Strategic Plan for HIV/AIDS
the delivery of an updated plan for monitoring and evaluating Program activities (the “Updated M&E Plan”) incorporating the recommendations upon completion of the Monitoring and Evaluation Systems Strengthening Tool. |  |  |  | Yes | The plan has been developed during the M&E WORKHSOP, The PR has not been able to deliver the plan to the TGF . It will be very soon delivered
delivery of a revised budget for the Program Term (the “Revised Program Budget”) if the amendments incorporated into the Updated M&E Plan necessitate amendments to the budget for the Program Term |  |  |  | Yes | The revised program budget is being made & will be delivered by End of March to the TGF
written approval of the Global Fund of the Updated M&E Plan and Revised Program Budget (the latter only being applicable if condition c. of this sub-section B.2 is applicable); |  |  |  | No | The approval has not been received yet from the GFATM on the update M&E plan
delivery of evidence, in form and substance acceptable to the Global Fund, that the Sub-recipient management and assessment requirements mandated in article 14. of the Standard Terms and Conditions of this Agreement have been complied with |  |  |  | Yes | SR assessment was carried out by the PR in march 2008. and SR assessment report was submitted both to the TGF & also to the LFA.
Project Management Unit of the Principal Recipient has been strengthened, in particular through the hiring of staff, with appropriate qualifications, for the following positions: program officer, M&E officer, and finance officer/accountant. |  |  |  | Yes | PMT has been strengthened , 1 Project manager, 1 M&E officer 2 fiinance officer, 1 office assistant, plans are underway to hire one additional M&E person. However since the PMT is manning two projects i.e GFATM & HIVAIDS it is difficult to properly coordinate & monitor the activties being implemented by the SR's
delivery by the Principal Recipient to the Global Fund of a plan for the procurement, use and supply management of the Health Products for the Program as described in subsection (c) of Article 19 of the Standard Terms and Conditions of this Agreement (the “PSM Plan”) |  |  |  | Yes | PSM plan prepaerd for HIV/AIDS for two year & submitted to GFATM
written approval of the Global Fund of the PSM Plan. |  |  |  | Yes | GFATM hasgiven written apporval of the PSM plan on 28 january 2008
Select

## PR_Section 1C
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: | 4
C. PROGRAM EXPENDITURES
All amounts are in: USD | Budget for Reporting Period | Actual for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | Reason for Variance
1. Total actual expenditures vs. budget | 139810 | 184162.27 | -44352.27 |  |  | 762409 | 294225.2 | 468183.8
1a. PR's total expenditures | 77416 | 135365.07 | -57949.07 | The spill over activities of the Q2 & Q3 were taken up during this quarter. So the expenditure has exceeded the budget. The budget for the previous quarters were not relected here. |  | 409760 | 203209.7 | 206550.3 | The low absorption of the funds are due to not being able to get the right technical assistance as planned . A total of 112,100 USD is provisioned for the TA services and apparently on USD 7800 has been used for the purpose. The PR lacks adequate capaccity and skills to hire external consultant which is very much time consuming in nature. Also there was no expenditure incurred during the first quarter so cumulatively the fund utilization comes quite poor.
1b. Disbursements to sub-recipients | 62394 | 48797.2 | 13596.8 | Most of SR do not implement the activities on time . The spillover activties of the previous quarters have been conducted during this quarter. |  | 352649 | 91015.5 | 261633.5 | No expenditure in the first quarter as such the cumulative exp is low. Also only two months given for implenting the first quarter activities. DYS under the MoE who is one of the biggest SR has still not implemented major chunk of activites with budgettary support of USD 75,713 for year 1
2. Health product expenditures vs. budget (already included in '"Total actual" figures above) | 0 | 0 | 0 |  |  | 25500 | 0 | 25500
2a. Pharmaceuticals | [5 empty] | 16500 |  | 16500
2b. Health products, commodities and equipment | [5 empty] | 9000 |  | 9000
Program expenditures were used for the procurement of health products: |  |  |  | No
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | Select
216135614.0406

## PR_Section 2
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  |  | Cycle: |  | Semester | Number: | 2
Disbursement Request - Period Covered: |  |  | Beginning Date: |  | 2009-01-01 | End Date: | 2009-06-30
Disbursement Request - Number: |  |  | 2
Section 2: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 6 from Cash Reconciliation section of the period covered
by the previous Progress Update): | [10 empty] | 512537.1
Add: | 2. Cash disbursed to the PR by the Global Fund during the period covered by this progress update: (1)
| 3. Interest received on bank account and other income received: | [9 empty] | 0
Less: | 4. Total program expenditures during period covered by Progress Update (value entered in Section 1C. "Total actual expenditures"): | [8 empty] | 184162.27
| 5. Other expenditures incurred (bank fees, other transaction costs, net exchange rate gains/losses): | [9 empty] | 184162.27
6. Cash Balance: End of period covered by Progress Update: | [10 empty] | 328374.83
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update (2, 3):
7. Period beginning date: |  | 2009-01-01 |  | end date: | 2009-06-30 |  | amount as originally budgeted: | 613621 | forecasted amount: | 613621
8. Additional quarter
(cash "buffer") beginning date (4): |  | 2009-07-01 |  | end date: | 2009-09-30 |  | amount as originally budgeted: | 74840 | forecasted amount: | 74840 | 688461
Please explain any variance between the forecasted amounts and the amounts as originally budgeted |  |  |  | The variation in the forcasted amount and the amount as originally budgeted is due to the delay in fund disbursement.Also such activtiies with the line ministries was carried out and also changes are seen in the focal person of the line ministries. The Project Coordinator being assigned such responsibility for the first time.
Less: | Cash Balance: End of period covered by Progress Update (number 6 above): | [8 empty] | 328374.83
| 9. Cash received from the Global Fund after the period covered by Progress Update or cash "in transit" (5) (if any): | [9 empty] | 328374.83
10. PR's Disbursement Request from the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [10 empty] | 360086.17
11. Does the PR's Disbursement Request include funds for health product procurement? | [5 empty] | Yes
12. Exchange Rate (used to translate local currency into USD): |  |  |  | 39.25
Footnotes:
1 - Gross amount disbursed by the Global Fund (i.e., any associated bank fees or transaction costs should not be deducted in this line, but included in line 5. “Other expenditures incurred”
2 - Expenditures listed must be covered by current budget forecasts
3 - Total forecasted net cash expenditures should include any commitments made in the period covered by the Progress Update that are forecasted to be spent during the period covered by the Disbursement Request
4 - Additional period (cash "buffer"): disbursement of funds for Q9 is contingent upon the signing of Phase 2 or as otherwise stipulated per implementation letter
5 - “Cash in transit” includes amounts disbursed but not yet received by the PR and disbursement requests not yet approved by the Global Fund.

## PR_Section 3
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Bhutan
Disease: | HIV/AIDS
Grant number: | BTN-607-G03-H
Principal Recipient: | GROSS NATIONAL Happiness Commission, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: | 2008-02-01
Currency: | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: | 4
DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: | Beginning Date: | 2009-01-01 | End Date: | 2009-06-30
Progress Update - Number: | 2
Section 3: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from Section 2.B line 10, in: USD): |  | 360086.17
2. Amount requested in words (in: USD): |  | Three hundred sixty thousand eighty six & seventeen cents
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name: | Karma Tshiteem
Title: | Secretary
Date and Place:
Bank Account Details (if different than the account details specified on block 9 of the face sheet of the Grant Agreement) |  |  |  |  | Comments (e.g. changes to PR's bank account details, "split disbursements" to the PR and third parties etc.):
Owner of Bank Account:
Account Title:
Account number:
Bank name:
Bank address:
Bank SWIFT Code:
Bank Code:
Routing instructions:

## LFA_Cover page
LFA On-going Progress Review and Disbursement Recommendation
Instructions to the LFA for completing the LFA On-Going Progress Review and Disbursement Recommendation
The Principal Recipient (PR) is required, through the On-Going Progress Update and Disbursement Request, to:
1. Provide past expenditure and programmatic performance information for the Reporting Period just ended; and
2. State its cash requirement for meeting on-going program expenditures.
The LFA is required, using this form, to verify progress and make recommendations on the cash amount requested.
Progress Update
The PR will report past expenditure and programmatic performance information for the Reporting Period just ended as well as progress made towards fulfillment of any conditions precedent/special conditions. The LFA is required to review and verify this information and, in accordance with the information fields set out in this form, to comment on current and cumulative progress.
Disbursement Recommendation
The PR will normally make a disbursement request from the Global Fund covering the PR's cash requirements for one Reporting Period, plus one additional quarter as a cash buffer, to ensure that the PR has adequate cash on hand for program expenses at all times. The Reporting Period for which the Disbursement Request is being made should be the period that immediately follows the Reporting Period covered by the PR's progress update (as explained above). The LFA is required to verify the PR's Cash Reconciliation and to ensure that the cash request is properly calculated. The LFA should recognize that the cash request should be based on the most up-to-date budgets for the relevant periods which the LFA should review for reasonableness.
Documents to be attached/retained
When submitting this form to the Global Fund, the LFA should attach the following:
1. PR On-Going Progress Update and Disbursement Request form (by email with originals to follow by mail)
2. Any supplementary information, as appropriate, to inform the Global Fund of the review and verification process and to support the review and recommendation
The LFA should also retain the PR's detailed Statement of Uses of Funds (Cash Flow Statement) for the Reporting Period just ended as well as any additional relevant documentation of verifications performed (to be provided upon request by the Global Fund).

## LFA_Section 1A (1)
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  | Bhutan | [10 empty] | Bhutan
Disease: |  | HIV/AIDS | [10 empty] | HIV/AIDS
Grant Number: |  | BTN-607-G03-H | [10 empty] | BTN-607-G03-H
Principal Recipient: |  | GROSS NATIONAL Happiness Commission, ROYAL GOVERNMENT OF BHUTAN | [10 empty] | GROSS NATIONAL Happiness Commission, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01 | [10 empty] | 39479
Currency: |  | USD | [10 empty] | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 4 | [7 empty] | Quarter | 4
Progress Update - Period Covered: |  | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31 | [7 empty] | 39722 | 39813
Progress Update - Number: |  | 4 | [10 empty] | 4
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 2 | [7 empty] | Semester | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2009-01-01 | End Date: | 2009-06-30 | [7 empty] | 39814 | 39994
Disbursement Request - Number: |  | 2 | [10 empty] | 2
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic and Financial Progress
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations | [9 empty] | 1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country | [9 empty] | 2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA | [9 empty] | 3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Intended Yearly Targets (from Attachment) | Actual Yearly Results (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on impact and outcome, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | N/A | TBD | Select |  |  | Impact | Percent of women and men aged 15-49 who are HIV infected | N/A | TBD
Impact | HIV prevalence among uniformed personnel |  |  |  |  | N/A | TBD | Select |  |  | Impact | HIV prevalence among uniformed personnel | N/A | TBD
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | N/A | TBD | Select |  |  | Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year | N/A | TBD
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | NA | TBD | Select |  |  | Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year | NA | TBD
Select
Select
Select
Select
Select
Select
Select
Select

## LFA_Section 1A (2)
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: |  | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: |  | 4
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Intended Targets to date (from Attachment) | Actual Results to date (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on progress to date, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
1 | Prevention: BCC - community outreach |  |  |  |  | 0 | 0 | Select |  |  | 1 | Prevention: BCC - community outreach |  | 0 | 0
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | #REF! | #REF! | #REF! | 20 | 0 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | 20 | 0
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | #REF! | #REF! | #REF! | TBD | 0 | Select |  |  | 1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | TBD | 0
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | #REF! | #REF! | #REF! | 10000 | 1505 | Select |  |  | 1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | 10000 | 1505
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | #REF! | #REF! | #REF! | 200 | 314 | Select |  |  | 1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | 200 | 314
1 | Prevention: BCC - community outreach | Number of hotels, bars and entertainment outlets providing HIV prevention services | #REF! | #REF! | #REF! | 200 | 232 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of hotels, bars and entertainment outlets providing HIV prevention services | 200 | 232
1 | Prevention: BCC - community outreach | Number of hospitals providing youth-friendly health services | #REF! | #REF! | #REF! | 30 | 40 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of hospitals providing youth-friendly health services | 30 | 40
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | #REF! | #REF! | #REF! | 3000 | 2057 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | 3000 | 2057
1 | Prevention: BCC - community outreach | Number of monks reached by HIV/AIDS education in monasteries | #REF! | #REF! | #REF! | 2000 | 185 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of monks reached by HIV/AIDS education in monasteries | 2000 | 185
1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | #REF! | #REF! | #REF! | 6000 | 7226 | Select |  |  | 1 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | 6000 | 7226
1 | Prevention: Testing and Counseling | Number of basic health units providing VCT services | #REF! | #REF! | #REF! | 75 | 81 | Select |  |  | 1 | Prevention: Testing and Counseling | Number of basic health units providing VCT services | 75 | 81
1 | Prevention: BCC - community outreach | Number of programs (slots) aired on TV and radio on HIV and STI and BCC messages | #REF! | #REF! | #REF! | 72 | 0 | Select |  |  | 1 | Prevention: BCC - community outreach | Number of programs (slots) aired on TV and radio on HIV and STI and BCC messages | 72 | 0
2 | HSS: Information system & Operational research | Number of health workers trained in revised HIV data reporting and analysis | #REF! | #REF! | #REF! | 140 | 158 | Select |  |  | 2 | HSS: Information system & Operational research | Number of health workers trained in revised HIV data reporting and analysis | 140 | 158
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | #REF! | #REF! | #REF! | 25(33%) | 29 | Select |  |  | 3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | 25(33%) | 29
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
0 |  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!

## LFA_Section 1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: | 4
B. LFA COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? | LFA Analysis (this should not be a “Copy and Paste” of the comments provided by the PR)
The delivery by the PR of the statement confirming the bank account into which the grant funds will be disbursed |  |  |  | Select |  | The delivery by the PR of the statement confirming the bank account into which the grant funds will be disbursed
The delivery by the PR of of a letter signed by Authorized representative of the PR seeting the name, titel & authenticated specimen signature of each person authorized to sign disbursement request |  |  |  | Select |  | The delivery by the PR of of a letter signed by Authorized representative of the PR seeting the name, titel & authenticated specimen signature of each person authorized to sign disbursement request
The delivery by the PR to the GF of evidence , in fomr and substance satisfactory to the Global Fund , that a project manager has been hired with appropraite qualifications & expereince |  |  |  | Select |  | The delivery by the PR to the GF of evidence , in fomr and substance satisfactory to the Global Fund , that a project manager has been hired with appropraite qualifications & expereince
the deliveryof a completed version of the Monitoring and Evaluation Systems Strengthening Tool (Dated January 2006 and available from the Global Fund website) that has been prepared by the Principal Recipient in consultation with the Program stakeholders |  |  |  | Select |  | the deliveryof a completed version of the Monitoring and Evaluation Systems Strengthening Tool (Dated January 2006 and available from the Global Fund website) that has been prepared by the Principal Recipient in consultation with the Program stakeholders
the delivery of an updated plan for monitoring and evaluating Program activities (the “Updated M&E Plan”) incorporating the recommendations upon completion of the Monitoring and Evaluation Systems Strengthening Tool. |  |  |  | Select |  | the delivery of an updated plan for monitoring and evaluating Program activities (the “Updated M&E Plan”) incorporating the recommendations upon completion of the Monitoring and Evaluation Systems Strengthening Tool.
delivery of a revised budget for the Program Term (the “Revised Program Budget”) if the amendments incorporated into the Updated M&E Plan necessitate amendments to the budget for the Program Term |  |  |  | Select |  | delivery of a revised budget for the Program Term (the “Revised Program Budget”) if the amendments incorporated into the Updated M&E Plan necessitate amendments to the budget for the Program Term
written approval of the Global Fund of the Updated M&E Plan and Revised Program Budget (the latter only being applicable if condition c. of this sub-section B.2 is applicable); |  |  |  | Select |  | written approval of the Global Fund of the Updated M&E Plan and Revised Program Budget (the latter only being applicable if condition c. of this sub-section B.2 is applicable);
delivery of evidence, in form and substance acceptable to the Global Fund, that the Sub-recipient management and assessment requirements mandated in article 14. of the Standard Terms and Conditions of this Agreement have been complied with |  |  |  | Select |  | delivery of evidence, in form and substance acceptable to the Global Fund, that the Sub-recipient management and assessment requirements mandated in article 14. of the Standard Terms and Conditions of this Agreement have been complied with
Project Management Unit of the Principal Recipient has been strengthened, in particular through the hiring of staff, with appropriate qualifications, for the following positions: program officer, M&E officer, and finance officer/accountant. |  |  |  | Select |  | Project Management Unit of the Principal Recipient has been strengthened, in particular through the hiring of staff, with appropriate qualifications, for the following positions: program officer, M&E officer, and finance officer/accountant.
delivery by the Principal Recipient to the Global Fund of a plan for the procurement, use and supply management of the Health Products for the Program as described in subsection (c) of Article 19 of the Standard Terms and Conditions of this Agreement (the “PSM Plan”) |  |  |  | Select |  | delivery by the Principal Recipient to the Global Fund of a plan for the procurement, use and supply management of the Health Products for the Program as described in subsection (c) of Article 19 of the Standard Terms and Conditions of this Agreement (the “PSM Plan”)
written approval of the Global Fund of the PSM Plan. |  |  |  | Select |  | written approval of the Global Fund of the PSM Plan.
Select

## LFA_Section 1C
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: | 4
C. PROGRAM EXPENDITURES
All amounts are in: Please select currency on Page 1 | Budget for Reporting Period | Actual for Reporting Period1 | Variance | LFA Verified (Y/N) | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR) | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR)
1. Total actual expenditures vs. budget | 139810 | 184162.27 | -44352.27 |  |  | 762409 | 294225.2 | 468183.8 | v | 139810 | 184162.27 | -44352.27 | 762409 | 294225.2 | 468183.8
1a. PR's total expenditures | 77416 | 135365.07 | -57949.07 | Select |  | 409760 | 203209.7 | 206550.3 |  | 77416 | 135365.07 | -57949.07 | 409760 | 203209.7 | 206550.3
1b. Disbursements to sub-recipients | 62394 | 48797.2 | 13596.8 | Select |  | 352649 | 91015.5 | 261633.5 |  | 62394 | 48797.2 | 13596.8 | 352649 | 91015.5 | 261633.5
2. Health product expenditures vs. budget (already included in "Total actual" figures above) | 0 | 0 | 0 | Select |  | 25500 | 0 | 25500 |  | 0 | 0 | 0 | 25500 | 0 | 25500
2a. Pharmaceuticals |  |  |  | Select |  | 16500 |  | 16500 |  |  |  |  | 16500 |  | 16500
2b. Health products, commodities and equipment |  |  |  | Select |  | 9000 |  | 9000 |  |  |  |  | 9000 |  | 9000
Program expenditures were used for the procurement of health products: |  |  |  | Select
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | Select
1 If the LFA makes a correction to the actual expenditures for the reporting period, the LFA should also make a corresponding correction to the PR's requested amount in LFA Section 4.A.1

## LFA_Section 1D
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: |  | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: |  | 4
D. LFA RATING AND COMMENTS ON PROGRAMMATIC AND FINANCIAL PROGRESS
1. LFA's Rating of PR's overall performance (1) |  | Select
2. Reasons for this Rating (including key issues and potential future risks):
3. LFA comments on PR planned changes in the program, if any (please refer to section 1.A.v of the PR's Progress Update / Disbursement Request):
4. LFA comments on data quality and reporting:
5. LFA comments on other program results, success stories, issues or lessons learned (please refer to section 1.A.vi of the PR's Progress Update / Disbursement Request):
1 - This rating should pertain to the cumulative progress (from the beginning of the Program to the end of the period covered by the Progress Update). It should take into consideration programmatic, financial and contextual factors.
- LFA ratings have been modified to be consistent with the Global Fund's new rating system. The new ratings relate to the previous ratings as follows:
New Scale |  | Old Scale
Rating | Description | Rating | Description
A | Expected or exceeding expectations | 5 | Exceptional
|  | 4 | Expected
B1 | Adequate | 3 | Minor adjustments needed
B2 | Inadequate but potential demonstrated | 2 | Major adjustments needed
|  | 1 | Little progress made
C | Unacceptable | 0 | Major program issues
Note on C10: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)

## LFA_Section 2
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number: | 2
Disbursement Request - Period Covered: | Beginning Date: | 2009-01-01 | End Date: | 2009-06-30
Disbursement Request - Number: | 2
Section 2: LFA Review and Verification of the Principal Recipient's Cash Reconciliation and Disbursement Request
LFA COMMENTS ON THE CASH RECONCILIATION AND DISBURSEMENT REQUEST
1. The PR cash reconciliation is calculated correctly and is supported by a detailed Statement of Sources and Uses of Funds (i.e., Cash Flow statement): |  |  |  |  | Select
Comments:
2. The PR Cash Request is calculated correctly and is supported by appropriate current budget forecasts: |  |  |  |  | Select
Comments:
3. The LFA has identified expenditures (incurred or forecasted) that should not be financed by the Global Fund: |  |  |  |  | Select
Comments:
4. The LFA has identified variance between the forecasted expenditures and the original budget for the disbursement period, including variance in line items: |  |  |  |  | Select
Comments:

## LFA_Section 3
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number: | 2
Disbursement Request - Period Covered: | Beginning Date: | 2009-01-01 | End Date: | 2009-06-30
Disbursement Request - Number: | 2
Section 3: LFA Recommendations and Review of Progress on Previous Recommendations
A. LFA RECOMMENDATIONS FOR THE CURRENT PROGRESS UPDATE AND DISBURSEMENT REQUEST
LFA Recommendations |  |  |  |  | Global Fund Decisions
B. LFA REVIEW OF PROGRESS ON PREVIOUS RECOMMENDATIONS CONFIRMED BY THE GLOBAL FUND
Previous Global Fund Decision |  |  |  |  | LFA Review of PR Progress

## LFA_Section 4
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | GROSS NATIONAL Happiness Commission, ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 4
Progress Update - Period Covered: |  |  | Beginning Date: | 2008-10-01 | End Date: | 2008-12-31
Progress Update - Number: |  |  | 4
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  |  | Cycle: | Semester | Number: | 2
Disbursement Request - Period Covered: |  |  | Beginning Date: | 2009-01-01 | End Date: | 2009-06-30
Disbursement Request - Number: |  |  | 2
Section 4: Disbursement Recommendation and Progress Review Summary
A. DISBURSEMENT RECOMMENDATION
1. Cash amount requested by the Principal Recipient form the Global Fund for next disbursement period plus one additional quarter (amount in: USD): | [6 empty] | 360086.17 |  | 360086.17
2. LFA disbursement recommendation (amount in: USD):
3. Reasons for the LFA's disbursement recommendation:
B. LFA RATING
LFA's rating of PR's overall progress |  |  |  | please select rating in 'LFA_Section 1.D.1'
C. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [7 empty] | Comments regarding verifications, if any:
| Select | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request
| Select | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable).
| Select | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement).
| Select | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress.
| Select | Exchange rate stated by Principal Recipient has been verified and is correct.
| Select | Bank account information provided on the face sheet of Grant Agreement (Grant No. / Mod. No.): |  |  |  |  | (or as otherwise
stated by the PR in its Progress Update / Disbursement Request) has been verified and is correct.
| Select | Current budget forecasts of the Principal Recipient for the next disbursement period plus one additional quarter have been reviewed for reasonableness
Signed on behalf of the LFA:
Name:
Title:
Date and Place:
Note on E34: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)
DRAFT

## LFA_Signature (image)
OPTIONAL - insert image of LFA signature here*: (the size should not exceed the limit of cells B2:D2)
* In every case, the LFA should provide a bona fide signature (in LFA_Section 4) on the original (paper-based) LFA report, sent to the Global Fund by mail.