## PR_Cover page
On-going Progress Update and Disbursement Request
Instructions to the Principal Recipient for completing the On-going Progress Update and Disbursement Request
Progress Update
The Progress Update part of this form requires the Principal Recipient (PR) to provide:
- Past expenditure and programmatic performance information for the reporting period just ended
- An update on the progress made towards satisfaction of the conditions precedent (if any) set forth in Annex A to the Grant Agreement applicable
to the period covered by the Progress Update
- A detailed Statement of Sources and Uses of Funds (Cash Flow Statement) for the reporting period just ended
For the Statement of Sources and Uses of Funds, the PR may use its own usual format and expenditure line items as derived from its budgeting and accounting records. The Global Fund does not prescribe specific expenditure line items, but prefers that the PR's reporting format is activity-based, in conformity with the proposal's objectives and service delivery areas. The PR is expected to clearly show actual expenditures as compared to budget for both its own expenditures as well as for disbursements to sub-recipients. The Statement of Sources and Uses of Funds should support the information disclosed in this form in Section 1.C (Program Expenditures) and Section 2.A (Cash Reconciliation for Period Covered by Progress Update).
Disbursement Request
The Disbursement Request part of this form requires the PR to state the cash requirement for meeting on-going program expenditures. The disbursement requested from the Global Fund normally covers the PR's cash requirements for one reporting period, plus one additional quarter as a cash buffer, to ensure the PR has adequate cash on hand for program expenses at all times. The period covered by the Disbursement Request is the period that immediately follows the Reporting Period covered by the Progress Update (as explained above).
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Section 1A (1)
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: |  | Bhutan
Disease: |  | HIV/AIDS
Grant Number: |  | BTN-607-G03-H
Principal Recipient: |  | Ministry of Health ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01
Currency: |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: |  | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: |  | 9
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 4
Disbursement Request - Period Covered: |  | Beginning Date: | 2010-05-01 | End Date: | 2010-10-31
Disbursement Request - Number: |  | 4
TERMS AND ACRONYMS USED IN THIS PROGRESS UPDATE AND DISBURSEMENT REQUEST HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: Programmatic and Financial Progress Update
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
Select
Select
Select
Select
Select
Select
Select
Select
Select
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Intended Yearly Targets | Actual Yearly Results | Reasons for deviation and any other comments
[6 empty] | Value | Year
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | 0.05% | 2006 | <0.1% | N/A | Sentinel surveillance will be conducted in the later half of the 2010, currently the surveillance protocol is being revised
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  |  | 0.20% | 2006 | <0.1% | N/A | Sentinel surveillance will be conducted in the later half of the 2010
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | 47% | 2009 | N/A | N/A | The next KAP survey will be conducted in the final year of the project
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | 53% | 2009 | NA | N/A | The next KAP survey will be conducted in the final year of the project
Select
Select
Select
Select
Select
Select
Select
Select
Formulas:
Quarter = IF([Cycle:, row below]="Select","",IF([Cycle:, row below]="N/A","",IF(F13="","",F13+1)))

## PR_Section 1A (2)
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: |  | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: |  | 9
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Directly Tied? | Level | Baseline (if applicable) |  | Intended Targets to date | Actual Results to date | Reasons for programmatic deviation and any other comments
[8 empty] | Value | Year
1 | Prevention: BCC - community outreach | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | Yes | 0 | 0 | 2006 | 35000 | 19580 | Additona; 6060 in school youths were reached with life skills based education this quarter, the report is only from 11 districts . 9 districts have not reported as they were busy with the mid term examination of the students. The reports from the remaining districts will be incorporated in the next report
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education |  |  |  | Yes | 1 | 0 | 2006 | 309 | 269 | The results reported are same as previous quarteras. Since the budget for Q9 was not released this hampered the implementation of the project
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  | Yes | 2 | 45 | 2009 | n/a | 45 | As per the findings of the KAP survey on HIV/AIDS
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings |  |  |  | Yes | 1 | N/A |  | 19950 | 18448 | Additional 1374 out of school youths has been reached with HIV messages during the World AIDS day celebration and the reports are from 4 districts to which the funds were released
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  | Yes | 1 | 0 | 2006 | 777 | 717 | The reports are same as the previous quarter as the budget for Q9 was not available to conduct the additional trainings
1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education |  |  |  | No | 0 | 100 | 2009 | 0 | 0 | This indicator will be met from subsequent quarters
1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) |  |  |  | Yes | 1 | 0 | 2006 | 0 | 0 | The activity is planned in Q10
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  | No | 1 | 6000 | 2006 | 7000 | 4388 | During the reporting quarter additional 874 children & women of the police force have been sensitized on HIV AIDS. The reports have not been received from the Royal Army and the same will be produced in the next reporting period.
1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  |  |  | Yes | 2 | 500 | 2005 | 6000 | 4284 | The results reported are same as previous quarteras. Since the budget for Q9 was not released this hampered the implementation of the project
2 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results |  |  |  | No | 2 | 1500 | 2005 | 26000 | 26975 | A total of 5132 people have been conseled and tested incuding the provision of results this quarter.
1
1
2
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment |  |  |  | No | 2 | 25%(19) | 2006 | 50 | 42 | 5 additional HIV patient have been put on ART this quarter

## PR_Section 1A & 1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: | 9
iv. Overall evaluation of performance
The available funds for Q8 was not able to meet the expenses for the Q9 and there was a shortage of funds to implement the planned activties.
v. Planned changes in the program, if any.
All the activties from Q9 has been moved into into the phase 1 with the type extension , the budget has not been disbursed for Q9 and it has to be implemented with the overall savings from phase 1 . This created some budgtary shortage and the same has to be requested with this new DR
vi. Other program results, success stories, issues or lessons learned
The results of the KAP survey has been finalized in theis quarter.
B. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? (Yes/No) | PR Comments
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  |  |  | Yes | M&E officer has been recruited at the Project Management Unit to monitor the the GF activties for a duration of 3 years starting April 2010
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country |  |  |  | Partially | PMT has now standardized the reporting format for GF HIV reporting ans trained all the SR's . There are still more reporting formats which needs to be standardised
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  |  |  | No
The Principal Recipient sahall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. |  |  |  | Yes | Updated PSM plan has been developed and submitted to GF
The written approval of the Global Fund of the updated PSM plan |  |  |  | No
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  |  |  | Yes | MOH will be new PR from phase 2 of this project
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of 1,program officer, 2 M&E Coordinator, 3 Finance Officer/Accoutant 4, Project Manager 5 Procurement & Supply management specialist |  |  |  | Yes | The PMU established to faciliate the coordination of GF grant have team comprising of Project Coordinator, M&E officer, 2 finance personel , 1 administrative assiatnt , 1 procurement officer to manage the grants
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  |  |  | In Progress | The detailed quarterly budget for year 4 &5 will be delivered as conditioned
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  |  | In Progress | The PQR shall be updated as & when the products are procured
Select

## PR_Section 1C
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: | 9
C. PROGRAM EXPENDITURES
All amounts are in: USD | Budget for Reporting Period | Actual for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | Reason for Variance | 12369.31
1. Total actual expenditures vs. budget | 170350 | 206886.86 | -36536.86 |  | 1672795.5 | 1221382.21 | 451413.29 |  |  | 12369.31
1a. PR's total expenditures | 65008 | 114623.6 | -49615.6 | There is huge variance seen here, the expenditure have been made as per the acce;eration plan and the budget has been reflected as per the original plan. As a aftermath of the acceleration many activties were carried out within the quarter and there is a hufg amount of expenditure incurred. | 917410 | 619149.2 | 298260.8 | in the quarter 8 expendtiure amounting to USD 5192.21 was incured and this was missed out and the same has been cinorporated in this quarter. The actual PR expenses for this quarter is USD 109,431.39 and with the addition of previously missed expenditure the total PR expenditure for his quarter comes to USD 114,623.60
1b. Disbursements to sub-recipients | 105342 | 92263.26 | 13078.74 | The reflected budget as per the original and expenditure as per the accelerations plan. The acceleration plan gave the SR's an avenue to spend more money which was not possible in the original plan but the targets have not been compromised. | 755385.5 | 602233.01 | 153152.49 | BCCI have not been able to absorb some of the funds in this quarter, RBA is yet to complete its planned activties, . The ICB component is still yet to utilized the capacity building money which is planned in the next quarter. The balance budget for the SR'S are planned to be utilized in the coming quarters.
2. Health product expenditures vs. budget (already included in '"Total actual" figures above) | 0 | 23521.44 | -23521.44 | No budget for Health products & Pharmaceuticals in Q9 | 264000 | 123807.6 | 140192.4 | The huge variance in the procurment budget was that as planned Elisa machine budgted for as USD 122,000 was not procured as it was done through other sources, the test kits were bought through the WB financing
2a. Pharmaceuticals | 0 | 0 | 0 | No procurement for pharmaceutical in this quarter | 49500 | 16927 | 32573 | Out of budgetary allocation of USD 49,500 for ARV & OI drugs only 16927 was utilized . The remaining money will be utilized in the subsequent quarters
2b. Health products, commodities and equipment | 0 | 23521.44 | -23521.44 | The expenditure incured was for the procurement of test kits & vacutainers & re agents for CD4 machine | 214500 | 106880.6 | 107619.4 | Out of budgetary allocation of USD 167,500 for procurement of CD 4 & ELISA machine only USD 57,497 was spent. Only CD 4 machine was biught as Elisa was already in ctock (USD 110,003) was not utilized. Test kits budget of USD 39,000 and exp of 17,165.13 USD made. USD 8000 for re agents not utilized
Program expenditures were used for the procurement of health products: |  |  |  | Yes
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | Yes

## PR_Section 2
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  |  | Cycle: |  | Semester | Number: | 4
Disbursement Request - Period Covered: |  |  | Beginning Date: |  | 2010-05-01 | End Date: | 2010-10-31
Disbursement Request - Number: |  |  | 4
Section 2: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 6 from Cash Reconciliation section of the period covered
by the previous Progress Update): | [10 empty] | 5491.18
Add: | 2. Cash disbursed to the PR by the Global Fund during the period covered by this progress update: (1) | [8 empty] | 263924
| 3. Interest received on bank account and other income received: | [8 empty] | 12298.87 | 276222.87
Less: | 4. Total program expenditures during period covered by Progress Update (value entered in Section 1C. "Total actual expenditures"): | [8 empty] | 206886.86
| 5. Other expenditures incurred (bank fees, other transaction costs, net exchange rate gains/losses): | [9 empty] | 206886.86
6. Cash Balance: End of period covered by Progress Update: | [10 empty] | 74827.19
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update (2, 3):
7. Period beginning date: |  | 2010-05-01 |  | end date: | 2010-10-31 |  | amount as originally budgeted: | 321590 | forecasted amount: | 491940
8. Additional quarter
(cash "buffer") beginning date (4): |  | 2010-11-01 |  | end date: | 2011-01-31 |  | amount as originally budgeted: | 86999 | forecasted amount: | 86999 | 578939
Please explain any variance between the forecasted amounts and the amounts as originally budgeted |  |  |  | Most of the activites for Q9 was not implemented as the DR was not requested as the phase 1 was coming to an end, therefore there was no disbursement of funds from GF, the budget of Q9 USD 170350 is requested in this request for the period startting 1/may 2010 and ending 31 October, therefore the forecasted amount comes to USD 491,940
\
Less: | Cash Balance: End of period covered by Progress Update (number 6 above): | [8 empty] | 74827.19
| 9. Cash received from the Global Fund after the period covered by Progress Update or cash "in transit" (5) (if any): | [8 empty] | 0 | 74827.19
10. PR's Disbursement Request from the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [10 empty] | 504111.81
11. Does the PR's Disbursement Request include funds for health product procurement? | [5 empty] | Yes
12. Exchange Rate (used to translate local currency into USD): |  |  |  | 46.04
Footnotes:
1 - Gross amount disbursed by the Global Fund (i.e., any associated bank fees or transaction costs should not be deducted in this line, but included in line 5. “Other expenditures incurred”
2 - Expenditures listed must be covered by current budget forecasts
3 - Total forecasted net cash expenditures should include any commitments made in the period covered by the Progress Update that are forecasted to be spent during the period covered by the Disbursement Request
4 - Additional period (cash "buffer"): disbursement of funds for Q9 is contingent upon the signing of Phase 2 or as otherwise stipulated per implementation letter
5 - “Cash in transit” includes amounts disbursed but not yet received by the PR and disbursement requests not yet approved by the Global Fund.

## PR_Section 3
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Bhutan
Disease: | HIV/AIDS
Grant number: | BTN-607-G03-H
Principal Recipient: | Ministry of Health ROYAL GOVERNMENT OF BHUTAN
Program Start Date: | 2008-02-01
Currency: | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: | 9
DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 4
Progress Update - Period Covered: | Beginning Date: | 2010-05-01 | End Date: | 2010-10-31
Progress Update - Number: | 4
Section 3: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from Section 2.B line 10, in: USD): |  | 504111.81
2. Amount requested in words (in: USD): |  | Five hundred four thousand one hundred six & twenty eight cents
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name: | Rinchen Wangdi
Title: | Chief Programme Coordinator
Date and Place: | 16/7/2010
Bank Account Details (if different than the account details specified on block 9 of the face sheet of the Grant Agreement) |  |  |  |  | Comments (e.g. changes to PR's bank account details, "split disbursements" to the PR and third parties etc.):
Owner of Bank Account:
Account Title:
Account number:
Bank name:
Bank address:
Bank SWIFT Code:
Bank Code:
Routing instructions:

## LFA_Cover page
LFA On-going Progress Review and Disbursement Recommendation
Instructions to the LFA for completing the LFA On-Going Progress Review and Disbursement Recommendation
The Principal Recipient (PR) is required, through the On-Going Progress Update and Disbursement Request, to:
1. Provide past expenditure and programmatic performance information for the Reporting Period just ended; and
2. State its cash requirement for meeting on-going program expenditures.
The LFA is required, using this form, to verify progress and make recommendations on the cash amount requested.
Progress Update
The PR will report past expenditure and programmatic performance information for the Reporting Period just ended as well as progress made towards fulfillment of any conditions precedent/special conditions. The LFA is required to review and verify this information and, in accordance with the information fields set out in this form, to comment on current and cumulative progress.
Disbursement Recommendation
The PR will normally make a disbursement request from the Global Fund covering the PR's cash requirements for one Reporting Period, plus one additional quarter as a cash buffer, to ensure that the PR has adequate cash on hand for program expenses at all times. The Reporting Period for which the Disbursement Request is being made should be the period that immediately follows the Reporting Period covered by the PR's progress update (as explained above). The LFA is required to verify the PR's Cash Reconciliation and to ensure that the cash request is properly calculated. The LFA should recognize that the cash request should be based on the most up-to-date budgets for the relevant periods which the LFA should review for reasonableness.
Documents to be attached/retained
When submitting this form to the Global Fund, the LFA should attach the following:
1. PR On-Going Progress Update and Disbursement Request form (by email with originals to follow by mail)
2. Any supplementary information, as appropriate, to inform the Global Fund of the review and verification process and to support the review and recommendation
The LFA should also retain the PR's detailed Statement of Uses of Funds (Cash Flow Statement) for the Reporting Period just ended as well as any additional relevant documentation of verifications performed (to be provided upon request by the Global Fund).

## LFA_Section 1A (1)
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office: |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  | Bhutan | [10 empty] | Bhutan
Disease: |  | HIV/AIDS | [10 empty] | HIV/AIDS
Grant Number: |  | BTN-607-G03-H | [10 empty] | BTN-607-G03-H
Principal Recipient: |  | Ministry of Health ROYAL GOVERNMENT OF BHUTAN | [10 empty] | Ministry of Health ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  | 2008-02-01 | [10 empty] | 39479
Currency: |  | USD | [10 empty] | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 9 | [7 empty] | Quarter | 9
Progress Update - Period Covered: |  | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30 | [7 empty] | 40210 | 40298
Progress Update - Number: |  | 9 | [10 empty] | 9
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 4 | [7 empty] | Semester | 4
Disbursement Request - Period Covered: |  | Beginning Date: | 2010-05-01 | End Date: | 2010-10-31 | [7 empty] | 40299 | 40482
Disbursement Request - Number: |  | 4 | [10 empty] | 4
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic and Financial Progress
A. PROGRAM PROGRESS
i. Program Objectives
Objective No. | Objective Description
1 | To increase access to prevention services for youth and other vulnerable populations | [9 empty] | 1 | To increase access to prevention services for youth and other vulnerable populations
2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country | [9 empty] | 2 | To increase national capacity in planning, implementation and monitoring HIV activities in the country
3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA | [9 empty] | 3 | To ensure a continued supply of ARV and OI drugs to sustain the treatment and care of PLHA
ii. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Intended Yearly Targets (from Attachment) | Actual Yearly Results (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on impact and outcome, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
Impact | Percent of women and men aged 15-49 who are HIV infected |  |  |  |  | <0.1% | N/A | PR On-site Visit | No change | This will be reported on completion of the sentinel survey which is planned to be conducted at the end of 2010. Currently the PR is revising the protocol for more effective and reliability of information collected. It will also be comparible to the baseline. | Impact | Percent of women and men aged 15-49 who are HIV infected | <0.1% | N/A
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  |  | <0.1% | N/A | PR On-site Visit | No change | This will be reported on completion of the sentinel survey which is planned to be conducted at the end of 2010. Currently the PR is revising the protocol for more effective and reliability of information collected. It will also be comparible to the baseline. | Impact | Percentage of uniformed personnel who are HIV infected | <0.1% | N/A
Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year |  |  |  |  | N/A | N/A | PR On-site Visit | NA | This will be reported after the second KAP survey which is will be done in the fifth year of the project | Outcome | Percentage of out-of-school youth aged 15-24 years reporting the consistent use of condom use with non-regular sexual partners in the last year | N/A | N/A
Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year |  |  |  |  | NA | N/A | PR On-site Visit | NA | This will be reported after the second KAP survey which is will be done in the fifth year of the project | Outcome | Percentage of uniformed personnel reporting the consistent use of condom with non-regular sexual partners in the last year | NA | N/A
Select
Select
Select
Select
Select
Select
Select
Select

## LFA_Section 1A (2)
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: |  | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: |  | 9
iii. Service Delivery Areas, Indicators, and Targets
Objective No. | Service Delivery Area | Indicator Description |  |  |  | Intended Targets to date (from Attachment) | Actual Results to date (as reported by PR) | Verification Method | Modified Results (after verification) | LFA analysis on progress to date, any variance between targets and results (this should not be a “Copy and Paste” of the reasons provided by the PR)
1 | Prevention: BCC - community outreach | Young people reached by life-skilled based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | 35000 | 19580 | PR On-site Visit | 19,560 [19.4 % of 100,924 (total youth grade 7 and above)] | Cumulative actual/target19,560/35,000, Cumulative achievment: 56%. This is a top ten indicator In this quarter, reports of this activity were received from 11 distircts which showed that 6,060 students had been reached by life skills based HIV/AIDS education. Reports from other nine districts have not been recieved and therefore the reach in this quarter should be actually much higher, however, the updated figures will be reported in the next quarter. The Department of Youth and Sports is the SR for this activity and they have been conducting other related activites for this indicator. The youth are committed and it is seen as an important activity in the schools. The number of schools covered is not provided. | 1 | Prevention: BCC - community outreach |  | 35000 | 19580
1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | #REF! | #REF! | #REF! | 309 | 269 | PR On-site Visit | No change | Cumulative actual/target: 269/309; Achievement: 87% This activity has not been conduced for Q9 and therefore the result is the same as for earlier quarters.Pl give reason why activity was not conducted?? | 1 | Prevention: BCC - community outreach | Number of teachers trained on life skill based HIV/AIDS education | 309 | 269
1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | #REF! | #REF! | #REF! | n/a | 45 | PR On-site Visit | No change | No target has been set for this indicator. The recently finalised KAP survey report shows that 45 % of young people in school correctly identify ways of preventing HIV AIDS. This is much lower than those reported for university students and out of school youths. However, the criteria used in the present survey was more stringent (know all five indicators as used in the survey) and this could be the reason for the low knowledge among in school youth. | 1 | Prevention: BCC - community outreach | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | n/a | 45
1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | #REF! | #REF! | #REF! | 19950 | 18448 | PR On-site Visit | No change | Cumulative actual/target18,448/19,950, Cumulative achievment: 92%. This is one of top ten indicators Funds were released to five districts to conduct this activity as part of the World AIDS day celebration on 1 st December 2009. The five districts reached 1,374 people with HIV/AIDS education and the breakup is as follows, Lhunthse-207, Sarpang-410, Dagana 157, Samdrup Jongkhar-400 and Trashigang-200. | 1 | Prevention: BCC - community outreach | People reached by HIV/AIDS education in out-of-school settings | 19950 | 18448
1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | #REF! | #REF! | #REF! | 777 | 717 | PR On-site Visit | No change | Cumulative actual/target 717/777, Cumulative achievment: 92 %. This is one of the top ten (training) indicators No instructors were trained in this quarter and therefore the figures are the same as for previous quarter. | 1 | Prevention: BCC - community outreach | Non Formal Education Instructors trained to provide HIV out-of-school education | 777 | 717
1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education | #REF! | #REF! | #REF! | 0 | 0 | PR On-site Visit | No change | As per PF, this activity will commense from Q10 | 1 | Prevention: BCC - community outreach | Number of Transport workers reached with HIV education | 0 | 0
1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) | #REF! | #REF! | #REF! | 0 | 0 | PR On-site Visit | No change | As per PF, this activity will commense from Q10 | 1 | Prevention: BCC - community outreach | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) | 0 | 0
1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | #REF! | #REF! | #REF! | 7000 | 4388 | PR On-site Visit | 4361 | Cumulative actual/target 4,361/7,000, Cumulative achievment: 63 % . This is one of the top ten indicators In this quarter 874 women and children of the police force were reached with HIV awareness program. In Q8, PR reported having reached 3,487 and therefore the correct number of people reached is 4,361. Although this activity has been carried out with Royal Bhutan Army personel and their families, there has been no reports. The PR will report on this in the next quarter. | 1 | Prevention: BCC - community outreach | Number of uniformed personnel and their families participating in HIV Awareness workshops | 7000 | 4388
1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | #REF! | #REF! | #REF! | 6000 | 4284 | PR On-site Visit | No change | Cumulative actual/target 4,284/6000, Cumulative achievment: 71 % . This is one of the top ten tindicators This activity was not carried out for Q9 and therefore the results are the same as for previous quarter. | 1 | Prevention: BCC - community outreach | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | 6000 | 4284
2 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | #REF! | #REF! | #REF! | 26000 | 26975 | PR On-site Visit | No change | Cumulative actual/target 26,975/26,000, Cumulative achievment: 104 % . This is one of the top ten tindicators A total of 5,132 people were counselled and tested during this quarter giving the cumulative figure of 26,975. The target for this quarter has been achieved. This is a routine activity carried out at all hospitals including the Health Information Service Centers (HISC) | 2 | Prevention: Testing and Counseling | Number of persons counseled and tested including provision of results | 26000 | 26975
[8 empty] | PR On-site Visit |  |  | 1
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 1
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 2
3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | #REF! | #REF! | #REF! | 50 | 42 | PR On-site Visit | No change | Cumulative actual/target 42/50, Cumulative achievment: 84 % This is one of the top ten tindicators In this quarter, 5 HIV people were put on treatment making the cumulative total at 42. The program continues to use the old standard of starting HAART with a CD4 count of 200. A team of doctors have been sent to Thailand for training on the new recommendations of starting with CD4 350 and on their return will revise the national treatment protocol. Thereafter it is expected that many more additional HIV positive people will be started HAART. | 3 | Treatment: Antiretroviral treatment (ARV) and monitoring | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | 50 | 42
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF! |  |  | Select |  |  | 0
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!

## Annexure 1
Indicators | Top 10 | Training | Target | Results | % Achievement
Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) | Top 10 |  | 35000 | 19560 | 55.89% |  | Top 10 |  |  | All Indicators
Number of teachers trained on life skill based HIV/AIDS education |  | Training | 309 | 269 | 87.06% |  | 56% | 80% | B1 | 81% | B1
% of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | Top 10 |  | na | 45 | no target set |  | 92%
People reached by HIV/AIDS education in out-of-school settings | Top 10 |  | 19950 | 18448 | 92.47% |  | 92%
Non Formal Education Instructors trained to provide HIV out-of-school education | Top 10 | Training | 777 | 717 | 92.28% |  | 63%
Number of Transport workers reached with HIV education |  |  | 0 | 0 |  |  | 71%
Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) |  | Training | 0 | 0 |  |  | 104%
Number of uniformed personnel and their families participating in HIV Awareness workshops | Top 10 | Training | 7000 | 4388 | 62.69% |  | 84%
Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | Top 10 | Training | 6000 | 4284 | 71.4%
Number of persons counseled and tested including provision of results | Top 10 |  | 26000 | 26975 | 103.8% | Training average of 5 in TOP 10 should be taken first and added to orhers
Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | Top 10 |  | 50 | 42 | 84%

## LFA_Section 1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: | 9
B. LFA COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
Conditions Precedent and/or other special conditions |  |  |  | Fulfilled? | LFA Analysis (this should not be a “Copy and Paste” of the comments provided by the PR)
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  |  |  | Yes | PR has recruited an M & E Officer who is attached with PMT to look after M & E component of all three diseases | Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country |  |  |  | Partially | PR has developed new reporting format and guidelines to be used by SRs to report the quarterly report. | Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  |  |  | No | Not done | Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units
The Principal Recipient sahall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. |  |  |  | Yes | Updated PSM plan was submitted to GF for approval | The Principal Recipient sahall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund.
The written approval of the Global Fund of the updated PSM plan |  |  |  | No | No written approval has been provided by GF | The written approval of the Global Fund of the updated PSM plan
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  |  |  | Yes | The PCM members during its 14th PCM meeting endorsed that hereafter the Ministry of Health shall be the PR and is responsible for implemenatation of the program. The Phase 2 documents were also signed both BY GNHC and MoH that reflected this arrangement | The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of 1,program officer, 2 M&E Coordinator, 3 Finance Officer/Accoutant 4, Project Manager 5 Procurement & Supply management specialist |  |  |  | Yes | Currently, Mr Tandin Dorji is the overall Program Manager for TB and HIV program. Mr Sonam Wangdi is the Program Officer. Mr Ugyen Tshewang as Finance Officer and Mr Dinash Rai as an Accountant. There is one M & E officer (newly recruited) who will be looking M & E component of all three diseases. Mr Tandin Dorji, Chief Program Officer will be looking after PSM. | The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of 1,program officer, 2 M&E Coordinator, 3 Finance Officer/Accoutant 4, Project Manager 5 Procurement & Supply management specialist
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  |  |  | N/A | Budget for Yr 4and Yr 5 to be submitted before 31 October 2010 | No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums.
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  |  | Yes | PR has agreed to abide by this CP | Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting.
Select
Select
Select

## LFA_Section 1C
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: | 9
C. PROGRAM EXPENDITURES
All amounts are in: Please select currency on Page 1 | Budget for Reporting Period | Actual for Reporting Period1 | Variance | LFA Verified (Y/N) | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR) | Cumulative Budget through period of Progress Update | Actual through period of Progress Update | Variance | LFA's Analysis of Variance (this should not be a “Copy and Paste” of the reasons provided by the PR)
1. Total actual expenditures vs. budget | 170350 | 206886.86 | -36536.86 |  |  | 1672795.5 | 1221382.21 | 451413.29 | v | 170350 | 206886.86 | -36536.86 | 1672795.5 | 1221382.21 | 451413.29
1a. PR's total expenditures | 65008 | 114623.6 | -49615.6 | Yes | Over all burn rate for this Quarter is 55 percent but all expenditures in this quarter pertains to all the backlog activities. Detailed analysis is shown in Annexure 3. | 917410 | 619149.2 | 298260.8 | The cumulative burn rate at Q9 end was 73%. The PR achieved 67% leaving 33% of the budget remained unspent. The main activities that remained unimplemented were non-recruitment of TA for M&E consultant (USD 60,000) as the PR could not get responses from the market. Another major activity not implemented was the purchase of ELISA machine which was budgeted USD 108,774. | 65008 | 114623.6 | -49615.6 | 917410 | 619149.2 | 298260.8
1b. Disbursements to sub-recipients | 105342 | 92263.26 | 13078.74 | Yes | Similar to PR, all the SR expenditure also pertain to the back log activities. Therefore, whole of Q9 budget remained unplemented. Details please see Annexure 3. | 755385.5 | 602233.01 | 153152.49 | The overall absorption rate achieved by SRs was 80% at Q9 end. Some SRs like Armed Forces, BCCI and Dratshang lack implementing capacity and also partly due to lack of awareness among SRs. However, the trend is picking up as and is expected to improve in future. | 105342 | 92263.26 | 13078.74 | 755385.5 | 602233.01 | 153152.49
2. Health product expenditures vs. budget (already included in "Total actual" figures above) | 0 | 23521.44 | -23521.44 | Yes | There were no procurement of Health Products expenditure pertaining to Q9 activity. | 264000 | 123807.6 | 140192.4 | There were no procurement of Health Products expenditure pertaining to Q9 activity. | 0 | 23521.44 | -23521.44 | 264000 | 123807.6 | 140192.4
2a. Pharmaceuticals | 0 | 0 | 0 | Yes | There were no procurement of Health Products expenditure pertaining to Q9 activity. | 49500 | 16927 | 32573 | The required pharmaceuticals have been procured through World Bank Funding. The amount represents saving. | 0 | 0 | 0 | 49500 | 16927 | 32573
2b. Health products, commodities and equipment | 0 | 23521.44 | -23521.44 | Yes | Th PR purchased Test Kits & Vacutioners USD 21,810.60 and Elisa Reader & CD $ Machine USD 1710.84 which is a back log activity. | 214500 | 106880.6 | 107619.4 | The variance pertains to the budget earmarked for purchase of Elisa Machines | 0 | 23521.44 | -23521.44 | 214500 | 106880.6 | 107619.4
Program expenditures were used for the procurement of health products: |  |  |  | No
If yes, information about procurements have been included in the Global Fund's Price Reporting Mechanism: |  |  |  | N/A
1 If the LFA makes a correction to the actual expenditures for the reporting period, the LFA should also make a corresponding correction to the PR's requested amount in LFA Section 4.A.1

## Annexure 2
Annexure 1
Cash Flow Statement for Q9 (FMA 2010)
Particulars | US$
Cash Inflow
Disbursement Received | 263924
Opening Bank Balance with MoH | 4609.11
Opening Cash in hand | 882.07
Advance refund | 12298.87
Total Inflow - A | 281714.05
Cash Outflow
Actual expenditure for the period (PR) | 114623.5997
Actual expenditure for the period (SR) | 92263.2558
Total Outflow - B | 206886.8555
Balance (A-B) | 74827.1945
Representation by
Balance at DPA | 65729.0252
Bank Balance at MoH | 16.8983
Cash Balance at MoH | 9081.2719
Total Fund available at the end of reporting period | 74827.1955

## Annexure 3
Annexure 2
Variance Analysis For Q9 (February,March, April 2010)
Activity Code (SDA) | Expenditure for the month | PR/SR | Budget | Actual Expenditure | Variance | % | LFA Comment
1.1.1 | TOT on Life Skill Education in 3 regions (Western, Central,Southern ) - 5 days training program each for region | SR | 10085 |  | 10085 | 100 | Q9 budget not implemented.
1.1.3 | Purchase of Television & DVD for the schools. - 30 sets required | SR | 12000 |  | 12000 | 100 | Q9 budget not implemented
1.1.4 | Purchase of sound system (Ahuja) | SR | 5850 |  | 5850 | 100 | Q9 budget not implemented
1.1.5 | Purchase of LCD Projector with desktop computer | SR | 4500 |  | 4500 | 100 | Q9 budget not implemented
1.1.7 | Purchase of wall mounted projector scerr 119" | SR | 450 |  | 450 | 100 | Q9 budget not implemented
1.1.8 | Purchase of Plasma TV | SR | 3150 |  | 3150 | 100 | Q9 budget not implemented
1.1.9 | Attend regional GFATM meetings | SR | 2250 |  | 2250 | 100 | Q9 budget not implemented
1.1.3 | Printing of training manuals | SR |  | 3806.6898 | -3806.6898 |  | Back log activities implemented
1.1.9 | Monitoring and evaluation | SR |  | 11500 | -11500 |  | Back log activities implemented
1.2.1 | Development & Printing of educational materials(TLM- teaching learning materials) | SR | 5000 |  | 5000 | 100 | Q9 budget not implemented
1.2.2 | Training of Teachers/Principals | SR | 18580 |  | 18580 | 100 | Q9 budget not implemented
1.2.4 | Attend regional GFATM meetings | SR | 2250 |  | 2250 | 100 | Q9 budget not implemented
1.2.5 | Refresher ToT for Vocational Centre teachers | SR | 5660 |  | 5660 | 100 | Q9 budget not implemented
1.2.7 | Attend regional GFATM meetings | SR | 2250 |  | 2250 | 100 | Q9 budget not implemented
1.2.6 | Community activities by youth NFE learners | SR |  | 2048.5447 | -2048.5447 |  | Back log activities implemented
1.2.8 | M&E | SR |  | 8598.3275 | -8598.3275 |  | Back log activities implemented
1.3.2 | Printing of education materials and products | SR | 5000 |  | 5000 | 100 | Q9 budget not implemented
1.3.2 | Sensitization of proprietors | SR |  | 4535.1868 | -4535.1868 |  | Back log activities implemented
1.3.3 | Ex-country training for the focal person on HIV programming | SR | 3610 |  | 3610 | 100 | Q9 budget not implemented
1.3.5 | Quarterly exchange of experience | SR |  | 7993.0495 | -7993.0495 |  | Back log activities implemented
1.4.2 | Print WHO guidelines | SR |  | 1240.4214 | -1240.4214 |  | Back log activities implemented
1.4.2 | Telephone line charges | SR | 474 |  | 474 | 100 | Q9 budget not implemented
1.4.4 | Training/refresher of staff about youth-issues | PR |  | 153.56 | -153.56 |  | Back log activities implemented
1.4.5 | Telephone line charges | PR |  | 1247.73 | -1247.73 |  | Back log activities implemented
1.4.7 | Training HIV Core Team at JDWNRH | PR |  | 5495.74 | -5495.74 |  | Back log activities implemented
1.5.1 | Development and Printing of HIV information package | SR | 3000 |  | 3000 | 100 | Q9 budget not implemented
1.5.2 | Capacity building of women police volunteers | SR | 4820 |  | 4820 | 100 | Q9 budget not implemented
1.5.2 | Printing of information package | SR |  | 819.85 | -819.85 |  | Back log activities implemented
1.5.4 | Sensitization program for RBA & RBG | SR | 2517.5 |  | 2517.5 | 100 | Q9 budget not implemented
1.5.7 | Attend regional GFATM meetings (for focal persons) | SR | 5000 |  | 5000 | 100 | Q9 budget not implemented
1.5.8 | M&E survey | SR |  | 787.26 | -787.26 |  | Back log activities implemented
1.6.2 | Purchase of 1 laptop and 1 projector | SR | 2669 |  | 2669 | 100 | Q9 budget not implemented
1.6.6 | Exchange programme | SR |  | 1132.93 | -1132.93 |  | Back log activities implemented
1.7.1 | IDU outreach services through sub grantee community organization | PR | 2000 |  | 2000 | 100 | Q9 budget not implemented
1.7.1 | substance user outreach services through sub grantee community organization | PR |  | 1020.81 | -1020.81 |  | Back log activities implemented
1.7.2 | SW outreach services through sub grantee community | PR | 8000 |  | 8000 | 100 | Q9 budget not implemented
1.8.1 | Rent two VCT centres | PR | 999 |  | 999 | 100 | Q9 budget not implemented
1.8.2 | Procurement of computers & printers for the two VCT centers | PR | 3982 |  | 3982 | 100 | Q9 budget not implemented
1.8.6 | Purchase Elisa readers and CD4 machine | PR |  | 1710.84 | -1710.84 |  | Back log activities implemented
1.8.8 | Test kits and vacutainers | PR |  | 21810.6 | -21810.6 |  | Back log activities implemented
1.9.1 | Consultative meeting to develop IEC materials for vulnerable groups | PR | 984 |  | 984 | 100 | Q9 budget not implemented
1.9.2 | Field testing of the materials | PR | 338 |  | 338 | 100 | Q9 budget not implemented
1.9.2 | BCC campaign ( tv, radio and print media ) | SR |  | 3207.97 | -3207.97 |  | Back log activities implemented
1.9.3 | BCC workshop for the MSTF members and health workers in the districts | SR |  | 1736.25 | -1736.25 |  | Back log activities implemented
1.9.4 | Contract with BBS(airtime charge ) and print media | SR |  | 15908.77 | -15908.77 |  | Back log activities implemented
1.9.5 | Monitoring & supervision visits | SR |  | 2985.27 | -2985.27 |  | Back log activities implemented
1.9.5 | Undertake supervision and monitoring visits | SR | 450 |  | 450 | 100 | Q9 budget not implemented
1.9.6 | Capacity building on communication & management skills | SR |  | 24302.99 | -24302.99 |  | Back log activities implemented
1.9.7 | Printing of brochures on how to use condoms | SR |  | 2809.95 | -2809.95 |  | Back log activities implemented
2.1.1 | Build up library resources | SR | 4000 |  | 4000 | 100 | Q9 budget not implemented
2.1.3 | Attend Global Fund meeting | SR | 2700 |  | 2700 | 100 | Q9 budget not implemented
2.2.1 | Hire M&E international consultant | PR |  | 868.81 | -868.81 |  | Back log activities implemented
2.2.1 | Hire M&E consultant in MOH | PR | 1950 |  | 1950 | 100 | Q9 budget not implemented
2.2.2 | Master in epidemiology | PR | 25000 |  | 25000 | 100 | Q9 budget not implemented
2.2.3 | Undertake supervision and monitoring visits | PR | 1251 |  | 1251 | 100 | Q9 budget not implemented
2.2.4 | Send program staff to international forum for information exchange and attend regional meetings of GFATM | PR | 8100 |  | 8100 | 100 | Q9 budget not implemented
2.2.6 | Quarterly meeting of stakeholders | PR | 270 |  | 270 | 100 | Q9 budget not implemented
2.2.7 | Train Health assistants on data reporting and analysis | PR |  | 6010.32 | -6010.32 |  | Back log activities implemented
2.2.10 | PCM meeting | PR |  | 191.79 | -191.79 |  | Back log activities implemented
2.2.11 | Undertake supervision and monitoring visits | PR |  | 3587.12 | -3587.12 |  | Back log activities implemented
2.2.12 | Quarterly meeting of stakeholders | PR |  | 1091.18 | -1091.18 |  | Back log activities implemented
2.2.13 | KAP Survey | PR |  | 16661.6 | -16661.6 |  | Back log activities implemented
2.3.1 | Diploma in finance management of HIV/AIDS project | PR | 11210 |  | 11210 | 100 | Q9 budget not implemented
2.3.6 | Adoc meeting and international seminars/workshops | PR |  | 17625.95 | -17625.95 |  | Back log activities implemented
2.4.1 | Proposal writing workshop/financial accounting | PR |  | 2308.74 | -2308.74 |  | Back log activities implemented
2.4.3 | Exchange programme for PLHA | PR |  | 6180.51 | -6180.51 |  | Back log activities implemented
2.4.4 | TA for NGO capacity building workshop | PR |  | 27508.1 | -27508.1 |  | Back log activities implemented
Total Expenditure |  |  | 170349.5 | 206886.8598 | -36537.3598 |  | Back log activities implemented
| Analysis | Total | %
| Overall burn rate | 206886.8598 | 121.4%
| PR Expenditure | 114623.6 | 55.4%
| SR Expenditure | 92263.26 | 44.6%
| Back log activities implemented in Q9 | 206886.86 | 100%
| Q9 Budget not implemented | 170349.5 | 100%
Note on B28: Desh Man Rai: New (SDA) activity added as per acceleration plan

## LFA_Section 1D
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: |  | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: |  | 9
D. LFA RATING AND COMMENTS ON PROGRAMMATIC AND FINANCIAL PROGRESS
1. LFA's Rating of PR's overall performance (1) |  | B1
2. Reasons for this Rating (including key issues and potential future risks):
The mean achievement with the 7 top ten indicators is 80 per cent , with three of the activities achieving over 90 percent. The mean achievement for all indicators is 81 per cent (see annexure 1). Although some of the activites could not be implemented at all. One indicator namely "Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage)" showed an achievement rate of below 60% that was inadequate. PR expenditure in this quarter is USD 114,623.60. However, all these expenditure pertains to implementation of backlog activities. Similarly, SR expenditure of USD 92,263.26 also pertains to backlog activities (see annuxure 3). Based on this, LFA provided "B1" rating.
3. LFA comments on PR planned changes in the program, if any (please refer to section 1.A.v of the PR's Progress Update / Disbursement Request):
The MoH is now the PR for phase 2, having taken over from GNHC on the recommendation of the CCM and the approval of GF.
4. LFA comments on data quality and reporting:
The quality of data was good although there needs to be better communication between the program, PMT and the SRs. The reports that are submitted by the SR to the PMT are often not sent or delayed in informing the program, which is mainly responsible for delay reporting on the PUDRs. In this quarter there were minor mistakes due to miscommunication between the PMT and the program.
5. LFA comments on other program results, success stories, issues or lessons learned (please refer to section 1.A.vi of the PR's Progress Update / Disbursement Request):
The KAP survey report has been finalised and important information has been collected which have contributed towards settting of targets for phase 2.
1 - This rating should pertain to the cumulative progress (from the beginning of the Program to the end of the period covered by the Progress Update). It should take into consideration programmatic, financial and contextual factors.
- LFA ratings have been modified to be consistent with the Global Fund's new rating system. The new ratings relate to the previous ratings as follows:
New Scale |  | Old Scale
Rating | Description | Rating | Description
A | Expected or exceeding expectations | 5 | Exceptional
|  | 4 | Expected
B1 | Adequate | 3 | Minor adjustments needed
B2 | Inadequate but potential demonstrated | 2 | Major adjustments needed
|  | 1 | Little progress made
C | Unacceptable | 0 | Major program issues
Note on C10: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)

## LFA_Section 2
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number: | 4
Disbursement Request - Period Covered: | Beginning Date: | 2010-05-01 | End Date: | 2010-10-31
Disbursement Request - Number: | 4
Section 2: LFA Review and Verification of the Principal Recipient's Cash Reconciliation and Disbursement Request
LFA COMMENTS ON THE CASH RECONCILIATION AND DISBURSEMENT REQUEST
1. The PR cash reconciliation is calculated correctly and is supported by a detailed Statement of Sources and Uses of Funds (i.e., Cash Flow statement): |  |  |  |  | Yes
Comments:
The PR has prepared the cash reconciliation statement correctly based on the books of accounts maintained as per the government financial rules and regulations. The LFA verified opening balances against the closing balances of Q8 PU report and also the Cash Book. The closing bank and cash balances for Q9 have been verified against the Bank Statement and the cash book maintained by the PR. All recorded expenditures are supported by relevant documents and all payments were approved by the appropriated approving authority. Cash reconciliation for Q9 is shown in Annexure 2.
2. The PR Cash Request is calculated correctly and is supported by appropriate current budget forecasts: |  |  |  |  | No
Comments:
The PR' cash request amounting to USD 504,111.81 has been arrived by taking budget forecast for Q9-Q12 amounting to USD 578,939 less cash balance Usd 74,827.19. The cash request should have been worked based on the budget forecast from Q10-12 less total cash balance at Q9 end. The total budget forecast for Q10-12 amounts to 408,588.54 (USD 321,589.54 plus one quarter buffer USD 86,999) less cash balance at Q9 end USD 74,827.19.
3. The LFA has identified expenditures (incurred or forecasted) that should not be financed by the Global Fund: |  |  |  |  | No
Comments:
The LFA has identified no expenditure which should not be financed by the Global Fund.
4. The LFA has identified variance between the forecasted expenditures and the original budget for the disbursement period, including variance in line items: |  |  |  |  | No
Comments:
The LFA identified no variances between forecasted expenditure and the corresponding original budget for the disbursement period, including line items.

## LFA_Section 3
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number: | 4
Disbursement Request - Period Covered: | Beginning Date: | 2010-05-01 | End Date: | 2010-10-31
Disbursement Request - Number: | 4
Section 3: LFA Recommendations and Review of Progress on Previous Recommendations
A. LFA RECOMMENDATIONS FOR THE CURRENT PROGRESS UPDATE AND DISBURSEMENT REQUEST
LFA Recommendations |  |  |  |  | Global Fund Decisions
PR and SRs have to accelarate their implementation since no expenditure for activities in Q9 were made |  |  |  |  | Not communicated to LFA
B. LFA REVIEW OF PROGRESS ON PREVIOUS RECOMMENDATIONS CONFIRMED BY THE GLOBAL FUND
Previous Global Fund Decision |  |  |  |  | LFA Review of PR Progress
It was noted that the submission of PUDRs is still delayed. We would like to urge all partners to work towards timely submission of any required documentation and reports. This is in particular necessary to also provide the program with the necessary support and timely funding. |  |  |  |  | The Q9 PUDR was delayed. The submission dateline was June 15, 2010 but LFA received it on 16 July 2010.

## LFA_Section 4
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office: |  |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | Ministry of Health ROYAL GOVERNMENT OF BHUTAN
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 9
Progress Update - Period Covered: |  |  | Beginning Date: | 2010-02-01 | End Date: | 2010-04-30
Progress Update - Number: |  |  | 9
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  |  | Cycle: | Semester | Number: | 4
Disbursement Request - Period Covered: |  |  | Beginning Date: | 2010-05-01 | End Date: | 2010-10-31
Disbursement Request - Number: |  |  | 4
Section 4: Disbursement Recommendation and Progress Review Summary
A. DISBURSEMENT RECOMMENDATION
1. Cash amount requested by the Principal Recipient form the Global Fund for next disbursement period plus one additional quarter (amount in: USD): | [6 empty] | 504111.81 |  | 504111.81
2. LFA disbursement recommendation (amount in: USD):
3. Reasons for the LFA's disbursement recommendation:
The LFA recommended USD 333,761.81 for disbursement which is 34% less than the disbursement requested by the PR. The reason being that the PR's disbursement request included four quarters budget from Q9-12 and as per normal procedure for DR, LFA included three quarters (Q10-Q12).
B. LFA RATING
LFA's rating of PR's overall progress |  |  |  | B1
C. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [7 empty] | Comments regarding verifications, if any:
| Yes | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request | [5 empty] | Verified and found to be correct
| Yes | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable). | [5 empty] | CPs for this disbursement has been met
| Yes | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement). | [5 empty] | Verified and found to be correct
| Yes | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress. | [5 empty] | Verified and found to be correct
| Yes | Exchange rate stated by Principal Recipient has been verified and is correct. | [5 empty] | The exchange rates are: First disbursement= 1 USD= Nu. 39.25; Second disbursement =1 USD =Nu. 47.841; third disbursement 1 USD= Nu. 46.04
| Yes | Bank account information provided on the face sheet of Grant Agreement (Grant No. / Mod. No.): |  |  |  | BTN-607-G03-H | (or as otherwise | correct
stated by the PR in its Progress Update / Disbursement Request) has been verified and is correct.
| Yes | Current budget forecasts of the Principal Recipient for the next disbursement period plus one additional quarter have been reviewed for reasonableness | [5 empty] | verified and is correct
Signed on behalf of the LFA:
Name: |  |  | Chhewang Rinzin
Title: |  |  | Finance
Date and Place: |  |  | 26 July 2010, Thimphu
Note on E34: Ratings from the New Scale roughly correspond to the Old Scale as follows: New Scale (Old Scale) Rating Description A Expected or exceeding expectations (5 or 4) (Exceptional or Expected) B1 Adequate (3) (Minor adjustments needed) B2 Inadequate but potential demonstrated (2 or 1) (Major adjustments needed or Little progress made) C Unacceptable (0) (Major program issues)

## LFA_Signature (image)
OPTIONAL - insert image of LFA signature here*: (the size should not exceed the limit of cells B2:D2)
* In every case, the LFA should provide a bona fide signature (in LFA_Section 4) on the original (paper-based) LFA report, sent to the Global Fund by mail.