## Cover Sheet
On-going Progress Update and Disbursement Request and LFA On-going Progress Review and Disbursement Recommendation
In completing this report, please refer to the detailed "Guidelines for completing the PR “ongoing progress update and disbursement request”, and LFA “ongoing progress review and disbursement recommendation”
During the lifetime of a grant, the Global Fund periodically disburses funds to the Principal Recipient (PR) based on demonstrated program performance and financial needs for the following period of implementation. The PR’s ongoing progress update and disbursement request (PU/DR) is both a progress report on the latest completed period of program implementation and a request for funds for the following period of implementation. Its purpose is to provide an update of the programmatic and financial progress of a Global Fund-financed grant, as well as an update on fulfillment of conditions precedent, management actions and other requirements. The PU/DR, alongside the Local Fund Agent (LFA) ongoing progress review and disbursement recommendation (short-form: LFA-verified PU/DR), forms the basis for the Global Fund’s disbursement decision by linking historical and expected program performance with the level of financing to be provided to the PR. One Excel file contains both the PR’s PU/DR and the LFA-verified PU/DR. The PR should only complete the worksheets of the file pertaining to the PU/DR (the worksheet tabs color-coded in green), whereas the LFA should complete the worksheets of the file pertaining to the LFA-verified PU/DR (the worksheet tabs color-coded in blue). The Excel file also includes a reference checklist of supporting documents for the PU/DR review (the worksheet tab color-coded in yellow). This checklist is included for information and not for completion. The PU/DR should be completed by the PR of a Global Fund grant for every period in which a progress update is required, usually either on a quarterly, semiannual or annual basis, regardless of whether or not a disbursement is being requested. Once a year, the PR is expected to submit the Enhanced Financial Report (EFR) as part of the PU/DR (there is a dedicated tab for EFR in the Excel file). The PR is required to submit the PU/DR to the LFA within 45 calendar days from the closing date of the relevant progress update period when the report does not contain the EFR (as indicated in the performance framework of Annex A of the grant agreement) and within 60 calendar days when the report contains the EFR (once a year). The LFA should complete and submit a signed copy of the LFA-verified PU/DR to the Global Fund within ten working days after receiving the final signed version of the PU/DR from the PR and within 13 working days when the PU/DR report contains the EFR (once a year), unless agreed otherwise with the FPM (The LFA does not need to submit original/hard copies of each PU/DR reports. However, these documents should be available at the LFA’s offices for any audit/reviews. Also, the LFA should be ready at all times to submit these originals to the Secretariat upon request). In this report the LFA should provide an analysis and comments based on verification of the PR-reported information, document grant risks and recommendations for improving program implementation, and finally, provide a performance rating to the grant and disbursement recommendation for the Global Fund’s consideration. In defining the performance rating and recommending a disbursement amount, the LFA should use the Grant Rating Methodology of the Global Fund (as described in Annex 2 and communicated at various regional meetings and LFA training events) along with the Excel version of the Grant Rating Tool (to be provided to LFAs) to support the calculation of Indicator Rating.
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Programmatic Progress_1A
On-going Progress Update and Disbursement Request | [13 empty] | Select
AIS (AIDS Indicator Survey)
BSS (Behavioral and Surveillance Survey)
GENERAL GRANT INFORMATION | [13 empty] | Census
Country: |  | Bhutan | [11 empty] | Clinical cohort follow-up studies
Disease: |  | HIV/AIDS | [11 empty] | DHS/DHS+ (Demographic and Health Survey)
Grant Number: |  | BTN-607-G03-H | [11 empty] | MICS (Multiple Indicator Cluster Survey)
Principal Recipient: |  | Ministry of Health | [11 empty] | MIS (Malaria Indicator Survey)
Program Start Date: |  | 2008-02-01 | [11 empty] | WHO Global report/estimates
Currency: |  | USD | [11 empty] | Other (type as appropriate)
PROGRESS UPDATE
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: |  | 14
DISBURSEMENT REQUEST
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number:
Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  | N/A
Section 1: Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Year of Target | Intended Target | Report Due Date | Actual Result | Data Source of Results | Comments on results on Impact/Outcome indicators and data sources, and any other comments
[6 empty] | Value | Year
Impact | Percentage of Men & Women aged 15-49 who are HIV infected |  |  |  |  | 0.05% | 2006 | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey) | sentinel surveiialnce is planned to be conducted towards end of 2011
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  |  | 0.20% | 2006 | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey) | sentinel surveiialnce is planned to be conducted towards end of 2011
Outcome | Percentage of out of school youths aged 15-24 reporting the consistent use of condoms with non regular sexual partners in last year |  |  |  |  | 47% | 2009 | 2011 | N/A | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey) | The results will be determined through the KAP end line survey is expected to take place in March 2012
Outcome | Percentage of uniformed personnel reporting the consistent use of condoms with non regular sexual partners in the last year |  |  |  |  | 53% | 2009 | 2011 | NA | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey) | The results will be determined through the KAP end line survey is expected to take place March 2012
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select

## PR_Programmatic Progress_1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: |  |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: |  |  | 14
Note: All programmatic indicators contained in the current Performance Framework should be listed, regardless of whether there are targets/results for the period covered by the Progress Update or whether the targets have been met in previous periods.
B. Programmatic Indicators
Objective No. | * Indicator No. | Indicator Description |  |  |  | Tied To | Targets cumulative? | Top 10 indicator? | Baseline (if applicable) |  | Intended Target to date | Actual Result to date | % achievement (Please calculate as appropriate) | Reasons for programmatic deviation from intended target and deviations from the related workplan activities
[9 empty] | Value | Year
1 | 1.1 | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | GF | Y-over program term | Yes - Top 10 | 0 | 2006 | 62100 | 45528 | 73.31% | The results for the Q14 could not be update in this report as the focal person is still on medical leave. However the same will be incorporated in the next quarter report
1 | 1.2 | Number of teachers trained on life skill based HIV/AIDS education |  |  |  | GF | Y-over program term | No | 0 | 2006 | 629 | 1379 | 219.2% | No additional teachers have been trained in thsi quarters . the results have far exceeded the target this is mainly becuase of the fact that at the time of project conception there were only few shools in the country from grade 7 to 12 in 2006. Now the no of schools have increased and as a result the no of teachers have also increased . Also the traing was planned in January during the winter break . Also duirng this quarter, the focal person from DYS was away for a month long training in Phillipines and due to domestic reasons she has availed leave of 2 months
1 | 1.3 | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  | National Program | N-not cumulative | Yes - Top 10 | 45 | 2009 | N/A | 0 |  | This value will be determined through the KAP survey which is ecpected to take place in March 2012
1 | 1.4 | People reached by HIV/AIDS education in out-of-school settings |  |  |  | GF | Y-over program term | Yes - Top 10 | N/A | 2008 | 21350 | 48843 | 228.8% | Additional out of school youths will be reached during the world AIDS day celebration in december 2011. The additional out of school youths reached is at no additional budget and is within the approved budget allocated by The Global Fund for the proposed activity
1 | 1.5 | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  | GF | Y-over program term | Yes - Top 10 | 0 | 2006 | 887 | 816 | 92% | The minsitry of education has conduted refresher course to the NFE learners as per the approved work plan . The funds were released to all 20 districts during the month of June 2011. The reports have been received and a total of 727 NFE instructors were given the refreshers course. At the time of proposal development, there were only 688 NFE centers in the country, however now the total no of NFE center in the country stands at 883
1 | 1.6 | Number of Transport workers reached with HIV education |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 100 | 2009 | 880 | 1442 | 163.9% | the results reported are same as previous quarter. IEC materails were distributed to the transport workers during the world AIDS day celebration with no additional cost to the project. Reaching out to more people with the same cost
1 | 1.7 | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) |  |  |  | GF and other donors | Y-over program term | No | 0 | 2006 | 200 | 667 | 333.5% | The results reported are same as the previous , the IEC materials have been developed through World Bank Funding
1 | 1.8 | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 6000 | 2006 | 15000 | 14972 | 99.81% | During the reporting, funds were released to District Health Officer of Thimphu to conduct sensitization on HIV/AIDS to the Royal Body guard troops and their families in the month of May 2011 as a result of this , they have been able to reach out to 643 troops and their families with HIV messages. Further the RBA hospital conducted a mass sensitization on HIV/AIDS at Samtse, Dagepela , wangdi, Chukha and Lungthen phu. They have also conducted TOT on the HIV/AIDS curicullum which was developed and printed . The TOT was conducted in all the military training institutes . As a result they have reached out to a total of 6821 troops and their familiies with HIV education
1 | 1.9 | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 500 | 2005 | 7500 | 6434 | 85.79% | conducted 2 days highlevel advocacy programme on HIV/AIDS for the senior monks in the month of June and the programme was able to reach out to 30 senior monks with limited budget of USD 1000 for this purpose
2 | 2.2 | Number of persons counseled and tested including provision of results |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 1500 | 2005 | 28000 | 38486 | 137.5% | During theis reporting quarter a total of 3510 people were reacahed with VCT services with no additonal cost to the project
2 | 2.3 | Number of people with advanced HIV infection receiving antiretroviral treatment |  |  |  | GF and other donors | N-not cumulative | Yes - Top 10 | 25 percent (19) | 2006 | 85 | 59 | 69.41% | NACP follows the WHO guidelines for putting people on ARV treatment which mean CD 4 count of less than 350. During this quarter 2 additonal people put on treatment . With the initiation of revised WHO guidelines we expect more people to be given ART
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
* Indicator No. should correspond to the indicator number listed in the approved Performance Framework of the grant (1.1, 1.2, etc.)
C. Analysis of data quality and reporting issues (!) This section should contain (1) a summary of issues related to data quality and reporting on programmatic indicators, and any relevant issues which are not covered in 'Reasons for programmatic deviation', and (2) remedial actions that are underway or planned to address these issues.
One of the reasons for delayed implementation particularly in this reporting period could be accounted for the local government elections during which all the trainings were frozen. Also this period conincides with the closing of the financial year and the release of funds from the Ministry of Fiance has stopped as early as June 1st week 2011 this has resulted in back log activties.
Th

## PR_Grant Management_2
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: | 14
Section 2: Grant Management
A. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
! Please include in this table the CP number as per Grant Agreement and full text of CPs and/or other special conditions due for fulfilment during this period or outstanding from previous periods. ! Some Special Conditions may apply to more than one period of grant implementation. Their fulfilment during one period does not automatically imply fulfilment in subsequent periods. The LFA should verify that the status of such conditions is reported by the PR during each period concerned.
Conditions Precedent and/or other special conditions |  |  | Status | PR Comments on Progress of Implementation
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  |  | Yes | M&E officer has been recruited at the Project Management Unit to monitor the the GF activties for a duration of 3 years starting April 2010
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country; and |  |  | Yes | PMT has now standardized the reporting format for GF HIV reporting ans trained all the SR's . There are still more reporting formats which needs to be standardised
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  |  | Partially | The SR supervison plan has been developed and the M&E training has been conducted
The disbursement by the GF or use by PR of global funds to finance the procurement of Health products (as defined in Article 19 of the Standard Terms and Condition of this Agreement), is subject to the following conditions: |  |  | Yes | Updated PSM plan has been developed and submitted to GF
(a) The Principal Recipient shall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. The Updated PSM shall: |  |  | Yes | The PSM plan has been submitted to GF
(i) address the deficiencies identified during the Phase 1 review in consultation with the GF, particularly those deficiencies relating to procurement process, quality assurance systems, storage and distribution as well as inventory mangement; and |  |  | Yes | The dediciencies and gaps identified during the pashe 1 review process are being taken into account especially on the logistics and supply managagement
(ii) include assumptions on forecasting for ARVs and testing products in order to ensure alignment with the performance framework and work plan and budget, where appropriate; and |  |  | Yes | Appropriate forcasting for the ARV & diagnostic products have been done in close consultation with the Drug procurment division. The forcasting was based on the past consumption of the drugs and test kits from various service delivery points
(b) The written approval of the Global Fund of the updated PSM plan |  |  | Yes | PSM plan has been submitted since June 2010 and the plan has been approved in March 2011, the delay in approval of PSM plan has casued a major hitch to the implementation rate of project
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  |  | Yes | MOH has been designated as the new PR after the signing of the phase 2 agreement of the project.
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of (1) program officer, (2) M& E Coordinator, (3) Finance Officer/Accoutant (4) Project Manager |  |  | Yes | The PMU established to faciliate the coordination of GF grant have team comprising of Project Coordinator, M&E officer, 2 finance personel , 1 administrative assiatnt , 1 procurement officer dealing with the procurement of health products to manage the grants
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  |  | Yes | The detailed quarterly budget for year 4 &5 has been delivered and been approved by GF
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  | In Progress | The PQR shall be updated as & when the health products products & equipments are procured
Select
Select
Select
B. PR REVIEW OF PROGRESS ON IMPLEMENTATION OF OUTSTANDING MANAGEMENT ACTIONS FROM PREVIOUS DISBURSEMENTS
! Please list all issues raised in the last Management Letter from the Global Fund or outstanding from previous Management Letters, and comment on the progress. Please include the date of the management letter and the item number. Reference: management letter dated 10 February 2011
Global Fund Management Actions |  | PR Comments on Progress of Implementation
We would very much encourage the team to submit the PDUR on time. This would faciliate the process of timely disbursement from the Global Fund to your ministry |  | Repeated reminder letters are being sent to the SR's for timely submission of the reports. Telephone calls and personal visit to the respective SR offices is now taking place to collect the reports on time
Submission of Annual Training Plan for approval from The Global Fund |  | The Annual Training Plan for the year 3 has been submitted and approved by Global Fund. There was delay in approval of the training plan which has hindered the implementation of the training activties thus resulting in many back log activties for implementation
We would like to request the PR to complete the recruitment of M&E consultant for implementing M&E training and development of supervision plan for the reporting units. |  | M&E consultant have been recruited for a duration of 2 months. She has developed the supervision plan for the reporting units. M&E training has been conducted to the reporting units
The coordination between PMT and NACP and SRs requires further strengthening for effective implementation of the grant . Regularize the coordination meeting |  | To strengthen the coordination amongst the key players in the project, regular & adhoc quarterly meetings are being organized by PMT. During the QPR we discuss a lot of issues and challenges confronting the implementation of the project. Representatives of GNHC are also invited as a part of their monitoring role. PMT has now initiated onsite monitoring visit to the project implementation sites at the time of conduct of the activties. Till now we have record of meeting till the 13th Quarter. The 14th Quarterly meeting is planned towards 3rd week of september
The reporting templates have been developed for the SR's to report on the activties. The report needs to be submitted on the agreed reporting format. The focal persons from each SR has to be trained on the new format |  | As a part of the TOR for the M&E consultant, the reporting toll has been customized to meet the requirements of the revised PUDR. The SR's have been trained on the operation of the tool. The tool is in its pilot phase and we would expect by Q15 all the SR's would report on the agreed reporting tool which is in electronic version
The newly recruited personnel in PMT & CCM secreteriat are required to have adequate information on the Global Fundguidelines for an effective coordination and reporting |  | PMT & CCM secreteriat have regular meetings on Global Fund issues. We make an attempt to educate the new recruits on the Global Fund guidelines
C. PR COMMENTS ON ANNUAL GRANT REPORTING REQUIREMENTS
! Please indicate a date for the report due for submission. If a report is overdue, indicate the original due date and explain the reason for delay.
Required Documentation |  | Due date (dd-mmm-yy) | Status | Comments
PR Audit Report |  | 2011-12-31 | Preparation on track | Currently the year 3 of HIV grant is being audited
Enhanced Financial Reporting (EFR) |  | 2011-01-31 | Submitted to GF | The EFR has been duly submitte to Global Fund

## PR_Total PR Cash Outflow_3A
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: |  | 14
Currency: |  | USD
Section 3A: Total PR Cash Outflow
! For RCC grants the cumulative section of the table below should contain cumulative amount from the start of the RCC and not from the start of Phase 1 of the program.
| Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
1. Total PR cash outflow vs. budget | 244572 | 185602.95 | 58969.05 |  |  | 2371517.5 | 1687018.36 | 684499.14
1a. PR's total expenditures | 62422 | 89132.94 | -26710.94 | The excess expenditure pertains to the payment of bills and other expenditure from the previous quarter. The excess payment also pertians to 50% payment made to PO ,NAPC for undergoing long term study in Australia for a duration of 2 years |  | 1207512.5 | 831837.32 | 375675.18 | Most of the unspent balances from the PR pertains to the Procurement budget about USD 140,192. The other unexpended budget allocated for the PR include the long terms study for NACP PO, with budgetary allocations of USD 50,000.
1b. Disbursements to sub-recipients | 182150 | 96470.01 | 85679.99 | SR's could not implement its planned activties for the quarter due to the delayed approval of the training plan. The training plan was approved only in May 2nd week and by June 15th the Ministry of Finance has stopped the release of funds to the ministries as it was nearing the financial year closing in June. 47,910 USD allocated for DYS for procurement of AV equipment was not utilized in this quaretr |  | 1164005 | 855181.04 | 308823.96 | The unspent balance from SR is mostly from training activitites . USD 47,910 unspent from DYS as procurement of av equipment in the year 4 q 14
| Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
2. Total pharmaceutical & health product expenditures vs. budget | 0 | 13613 | -13613 |  |  | 264000 | 137420.6 | 126579.4
2a. Medicines and pharmaceutical products | 0 | 0 | 0 |  |  | 49500 | 16927 | 32573 | The year 3 approved budgett for prpcurement of ARV drugs fr year 3 USD 16,162 has not been utilized yeat as the bills for the sa,me has not been passed for payment
2b. Health products and health equipment | 0 | 13613 | -13613 | payment made for the procurement of re agents for CD count machine. The budget was reflected in Q13 but procurement affected only in this quarter |  | 214500 | 120493.6 | 94006.4 | Total budget of USD 35,000 for the procurement of CD re agents and test kits & vacutianers t were not utilized from year 3 budget

## EFR HIV AIDS Financial Data_3B
SECTION 3B: HIV/AIDS FINANCIAL REPORTING FORM
Country |  | Bhutan |  |  | PLEASE REFER TO THE "GUIDANCE FOR COMPLETION OF THE ENHANCED FINANCIAL REPORTING TEMPLATE" DOCUMENT TO ASSIST YOU IN COMPLETING THE TEMPLATE
Grant No. |  | BTN-607-G03-H
PR |  | Ministry of Health |  |  | TO BE COMPLETED ONLY ONCE A YEAR EXCEPT AT MONTH 18 FOR PURPOSES OF PHASE 2 REVIEW
Currency |  | USD
[6 empty] | dd-mm-yyyy |  |  |  | dd-mm-yyyy
|  |  |  | Current Reporting Period | Start Date: |  |  | Cumulative Reporting Period | Start Date:
[5 empty] | End Date: |  |  |  | End Date:
The end date for the current reporting period and cumulative reporting period must be the same
The "TOTAL" rows in Table A, B and C will have a RED background if the amounts in each table do not agree. If the Totals for each Table agrees, these rows will have a YELLOW background.
A- BREAKDOWN* BY EXPENDITURE CATEGORY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period |  |  |  | All amounts are in: | Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
# | Category |  |  | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance | 1. Total PR cash outflow vs. budget | 244572 | 185602.95 | 58969.05 |  | 2371517.5 | 1687018.36 | 684499.14
1 | Human Resources |  |  | 6000 |  | 6000 | [5 empty] | 1a. PR's total expenditures | 62422 | 89132.94 | -26710.94 |  | 1207512.5 | 831837.32 | 375675.18
2 | Technical Assistance |  |  | 0 | [7 empty] | 1b. Disbursements to sub-recipients | 182150 | 96470.01 | 85679.99 |  | 1164005 | 855181.04 | 308823.96
3 | Training |  |  | 141354 |  | 141354
4 | Health Products and Health Equipment |  |  | 0 | [8 empty] | Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
5 | Medicines and Pharmaceutical Products | [10 empty] | 2. Total pharmaceutical & health product expenditures vs. budget | 0 | 13613 | -13613 |  | 264000 | 137420.6 | 126579.4
6 | Procurement and Supply Management Costs |  |  | 0 | [7 empty] | 2a. Medicines and pharmaceutical products | 0 | 0 | 0 |  | 49500 | 16927 | 32573
7 | Infrastructure and Other Equipment |  |  | 47910 |  | 47910 | [5 empty] | 2b. Health products and health equipment | 0 | 13613 | -13613 |  | 214500 | 120493.6 | 94006.4
8 | Communication Materials |  |  | 45375 |  | 45375
9 | Monitoring & Evaluation |  |  | 2460 |  | 2460
10 | Living Support to Clients/Target Populations |  |  | 0
11 | Planning and Administration |  |  | 0
12 | Overheads |  |  | 1473 |  | 1473
13 | Other |  |  | 0
|  |  | TOTAL | 244572 | 0 | 244572 |  | 0 | 0 | 0
B- BREAKDOWN* BY PROGRAM ACTIVITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | Macro-category | Objectives | Service Delivery Area | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
TOTAL |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 39 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
C- BREAKDOWN* BY IMPLEMENTING ENTITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | PR/SR | Name | Type of Implementing Entity | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
|  |  | TOTAL | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 51 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
* The sum of all three breakdowns should be equal (A- Budget Line-item, B- Program Activity, C- Implementing Entity).
** For the purposes of this report, the SDA Program management and administration should be included in the Supportive Environment Macro Category.
D- ADDITIONAL INFORMATION
Please disclose any relevant information concerning the information in the above tables. Refer to the Guidelines for Completing the Template if required.
E- DISBURSEMENTS BREAKDOWN BY IMPLEMENTING ENTITY |  |  |  | Cumulative Reporting Period
# | Name | Type of Implementing Entity | Cumulative Disbursements | Comments
Please Select…
Please Select…
Please Select…
Please Select…
Please Select…
|  | TOTAL | 0
Note on A34: Insert Number
Note on A46: Insert Number
Note on A69: Insert Number
Note on B29: This category should only be used as a last resort if there is a type of cost that absolutely cannot be allocated to another cost category
Note on C34: Please remember to include the full name of the objective. If an objective has more than 1 SDA, repeat the objective name on each row for the relevant SDA
Note on C69: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D46: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D75: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on E40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on E52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E68: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on E69: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on F30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on F40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on F52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on G8: Start date for current period cannot be earlier than cumulative period
Note on G30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on G40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on G52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on H16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on I15: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I20: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I21: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I30: Please ensure that: -the figure here agrees with the figure in the corresponding cells in Tables B and C (in this tab). If they do not the background color will be RED; and -the figure also agrees with the cumulative budget figure in the corresponding cell (H11) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I33: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on I45: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on J20: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J21: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on J40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on J52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on K8: Start date for current period cannot be earlier than cumulative period
Note on K30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on K40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on K52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on L16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.

## PR_Procurement Info_4
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: | 14
Section 4: Procurement and Supply Management
Comments
1a. Have you updated the Price Quality Reporting (PQR) with the required information on the pharmaceuticals and health products received during the period covered by this PU/DR’ (if applicable)? If health products procurement information has not been entered into the PQR, please explain why. ! For further guidance on PQR data entry, please refer to the guidelines. |  |  | N/A | During the reporting period no procurment of health products were made . However we update the PQR as a mandate by The Global Fund as and when procurment of health products are made
2. Based on the most up-to-date stock situation, are there any risks of stockouts of key pharmaceuticals & health products at the central level in the next period of implementation? If yes, please comment. |  |  | No | There are no risk of stock outs of ARV drugs for the people on treatment as of most up to date stock situation. The DVED responsible for the procurement and forecasting of drugs ensures that there are no stock out of ARV drugs. Through the approved year 3 budget they have procured one consignment of ARV drugs and the stocks are expected to last for atleast 6 months.
3. Comment on additional issues related to the procurement and supply management of pharmaceuticals and health products
Due limited staffs in DVED to deal with the procurement of drugs and also with the stringetn rules on drugs procurement of Drug Regulatory Authrity there has been stock out of some of the drugs. But this has not affedted the drugs supply of ARV DRUGS

## PR_Cash Reconciliation_5A
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  | BTN-607-G03-H |  |  |  | ! A Statement of Sources and Uses of Funds (SSUF) is to be provided by PR along with the PUDR form
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: |  | 14
Currency: |  | USD
Section 5: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 10 from Cash Reconciliation section of the period covered by the previous Progress Update):
276182.77
Add: | 2. Cash received by the PR from the Global Fund during the period covered by this progress update: | [5 empty] | 0
| 3. Cash disbursed to third parties by the Global Fund on behalf of the PR during the period covered by this progress update: | [5 empty] | 0
4. Interest received on bank account
| 5. Revenue from income-generating activities (if applicable) | [5 empty] | 0
| 6. Other income, if applicable (e.g. income from disposal of fixed assets, tax refunds) | [5 empty] | 39717.41 | 39717.41
Less: | 7. Total cash outflow during period covered by Progress Update (value entered in Section 3A "Total cash outflow"): | [5 empty] | 185602.95
8. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign)
| 9. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) | [6 empty] | 185602.95
10. Cash Balance: End of period covered by Progress Update: | [7 empty] | 130297.23
Explanation of reconciliation adjustments (line 9)
! An explanation must be provided if there have been any adjustments.

## PR_Disbursement Request_5B
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  |  | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: |  |  |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: |  |  |  | 14
Currency: |  |  | USD
Section 5: Cash Reconciliation and Disbursement Request
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update:
1. Period beginning date: |  |  |  |  | end date: |  |  | approved budget amount: | forecasted amount:
2a. Cash buffer period (by default)
(cash "buffer") beginning date: |  |  |  |  | end date: |  |  | approved budget amount: | forecasted amount:
PR Total Forecast
2b. Additional "buffer" (discretionary, select only if there is a prior agreement with the FPM) (1) | [10 empty] | 0
cash "buffer" agreed with FPM (2) |  | Select
(cash "buffer") beginning date |  |  |  |  | end date: |  |  | approved budget amount: | forecasted amount:
(1) Additional Cash buffer can be requested if the next PU/DR report will contain a completed EFR report or a completed Annex on SR financials, requested by the Secretariat, or if there are any additional GF-specific requirements that cannot be delivered within 45 days. An agreement in principal from the FPM should be obtained prior to requesting an additional cash buffer.
(2) When the additional (cash "buffer" ) period is 1 or 2 months, the approved budget and forecasted amounts should be calculated as prorated values for the period following the regular buffer period.
Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. NB. Consider the following items when providing the analysis. - Expected timing of payments for any significant budgetary items, - Impact of existing cash balance at SR levels - Current confirmed commitments to be paid during disbursement request period - Current/expected unit prices compared to those in the budget - Change in quantities compared to budget - Exchange rates and inflation - Linkage between budget absorption and programmatic performance to-date. ! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the disbursement period
Less: | 3. Cash Balance: End of period covered by Progress Update (number 10 from PR Cash Reconciliation sheet): | [8 empty] | 130297.23
4. Cash "in transit" disbursed to the PR:
| 5. Cash "in transit" disbursed to third parties by the Global Fund on behalf of the PR | [9 empty] | 130297.23
6. PR's Disbursement Request to the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [10 empty] | 0
7. Does the PR's Disbursement Request include funds for health product procurement? | [6 empty] | Select
8. Exchange Rate (used to translate local currency into grant currency) | [6 empty] | Name of local currency, date and source of the exchange rate, and other comments (if appropriate)
| - used to convert Opening Cash Balance |  |  |  | 45.7 |  | Ngultrums, Royal Monetary Authrotity of Bhutan
| - used to convert Closing Cash Balance |  |  |  | 45.7 |  | Ngultrums, Royal Monetary Authrotiy of Bhutan
| - used to convert Total Cash Outflow for the Progress Update Period |  |  |  | 45.7 |  | Ngultrum, Royal Monetary Authority of Bhutan

## PR_Overall Performance_6
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: | 14
Section 6: Overall Performance
A. PR's Overall Self-Evaluation of Grant Performance (including a summary of how financial performance is linked to programmatic achievements)
! The self-evaluation should be undertaken by taking into account programmatic achievements, financial performance and program issues in various functional areas (M&E, Finance, Procurement, and Program Management, including management of sub-recipients). See Guidelines for more detailed guidance.
The performance of the grant during this quarter is staisfactory as it has met many of the planned targets. In terms of funds absoprtion SR's has failed to absorp the allocated bugdet again due to delayed approval of the training plan from the Global Fund. The financial achievement stand at 75%
B. Planned Changes in the Program, if any
No changes in planned activty . All the activities carried out as per the approved work plan .
C. External factors beyond the control of the Principal Recipient that have impacted or may impact the Program
Delayed approval of PSM plan and the training plan has slowed the progress of grant implementation to a certain extent. The quarter coincided with the financial year closing of the government and the government financial transaction stopped the flow of funds from mid june . Also during this quarter, there was local government elections which hindered the implementation of many activties as there was directive from the government no to conudt any activity during the local government elections

## PR_Cash Request_7A&B
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Bhutan
Disease: | HIV/AIDS
Grant number: | BTN-607-G03-H
Principal Recipient: | Ministry of Health
Program Start Date: | 2008-02-01
Currency: | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: | 14
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: | Cycle: | Semester | Number: | 0
Disbursement Request - Period Covered: | Beginning Date: |  | End Date:
Disbursement Request - Number: | N/A
Section 7: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from line 14 – “PR's Disbursement Request” in the tab “PR_Disbursement Request_4B”), in grant currency |  | 0
2. Amount requested in words (in: USD): |  | 0
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name:
Title:
Date and Place:
NB: Please ensure that section 7C Bank Details on the following page is completed, if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.

## PR_Bank Details_7C
On-going Progress Update and Disbursement Request
NB: This page should be completed if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.
7C: Bank Account Details
Disbursement Request Period
Summary
|  | Beneficiary Name | Amount in grant currency
| Payee 1 - Principal Recipient: | Ministry of Health | 0
| Payee 2: | 0 | 0
| Payee 3: | 0 | 0
| Payee 4: | 0 | 0
| Total |  | 0
Payee 1:
| Beneficiary Name: | Ministry of Health |  | Owner of Bank Account: | Royal Government of Bhutan
| Currency in which beneficiary should receive the funds | USD |  | Owner of Bank Account: | Federal Reserve Bank of New York
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | 2108337
| Amount in Words: |  |  | Bank Address | 33 Liberty Street , NY 1004 ,USA
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | FRNYUS33
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 2:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 3:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 4:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:

## PR_Annex_SR-Financials
On-going Progress Update and Disbursement Request
Annex to PU/DR - Sub-recipient financial information - FOR DISCRETIONARY COMPLETION, UPON THE SECRETARIAT'S REQUEST
Has the Secretariat requested the PR to complete this Annex for this reporting period?
Grant number: |  |  |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  |  |  | Cycle: | Quarter |  | Number: | 14
Progress Update - Period Covered: |  |  |  |  | Beginning Date: | 2011-05-01 |  | End Date: | 2011-07-31
Progress Update - Number: |  |  |  |  | 14
Currency: |  |  | USD
Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR |  | Budget for Reporting Period* | Disbursed during Reporting Period* |  | Cumulative Budget through period of this Progress Update* | Cumulative Disbursed through period of this Progress Update* | Cumulative Actual Expenditure through period covered by this Progress Update | Cash balance at the end of the period covered by this Progress Update | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (1) between cumulative budget and cumulative expenditure and (2) between cumulative disbursement and cumulative expenditure (mandatory for amounts above $50,000 or equivalent and with more than 10% variance)
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | Yes
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
TOTAL |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0
*TOTAL amount for these columns should reconcile with relevant amounts under "1b Disbursed to Sub Recipients" in Section 3A"
** Where the number of SRs is significant (over 10), SRs with small budgets (less than $50,000 cumulative each) do not need to be reported separately and the figures can be aggregated in a group called "Other Minor SRs"

## Checklist
List of supporting documents for PU/DR review
This checklist is included for information and not for completion.
List of Latest Approved Documents by functional area | To be made available to the LFA by the PR | To be submitted by the LFA to the Secretariat | Comments
M&E
Performance Framework | x
M&E Plan | x
Survey results | x |  | For Impact/Outcome indicators
M&E Systems Strengthening Assessment | x |  | If newly available during the reporting period.
Other M&E assessments done by partners to assess data quality and M&E system issues. | x |  | If newly available during the reporting period.
Procurement
Consumption reports for pharmaceuticals and health products | x
Supplier invoices | x
PSM Plan | x
Stock level reports | x
Finance
Approved budgets | x |  | For the periods covered by Progress Update and Disbursement Request, including the buffer period.
Statement of sources and uses of funds (Cash flow statement) | x | x | See guidance on SSUF content and format in the guidelines.
Cash books | x
General Ledger | x
Cash forecasts | x
Bank statements | x
Bank Reconciliations | x
Annual PR Audit Report, Financial Statements, Management Letters and Responses (if Due) | x | x
Annual SR Audit Report, Financial Statements, Management Letters and Responses (if Due) | x
General Management
Grant Agreement (including Annex A and subsequent implementation letters) | x
Workplan | x

## LFA_Programmatic Progress_1A
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  | Bhutan
Disease: |  | HIV/AIDS
Grant Number: |  | BTN-607-G03-H
Principal Recipient: |  | Ministry of Health
Program Start Date: |  | 2008-02-01
Currency: |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: |  | 14
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 0
Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  | N/A
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators | [12 empty] | A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  | Year of Target | Intended Target (from Attachment) | Report Due Date | Actual Result (as reported by PR) | Data Source of Results | Verification Method | Verified Result | LFA comments on (a) verified result, (b) source of information used by the PR to report results, including the status of completion of surveys and other methods to measure Impact/Outcome, as applicable, | Impact / Outcome | Indicator Description | Year of Target | Intended Target (from Attachment) | Report Due Date | Actual Result (as reported by PR) | Data Source of Results
Impact | Percentage of Men & Women aged 15-49 who are HIV infected |  |  |  | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey) |  |  |  | Impact | Percentage of Men & Women aged 15-49 who are HIV infected | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey)
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey) |  |  |  | Impact | Percentage of uniformed personnel who are HIV infected | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey)
Outcome | Percentage of out of school youths aged 15-24 reporting the consistent use of condoms with non regular sexual partners in last year |  |  |  | 2011 | N/A | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey) |  |  |  | Outcome | Percentage of out of school youths aged 15-24 reporting the consistent use of condoms with non regular sexual partners in last year | 2011 | N/A | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey)
Outcome | Percentage of uniformed personnel reporting the consistent use of condoms with non regular sexual partners in the last year |  |  |  | 2011 | NA | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey) |  |  |  | Outcome | Percentage of uniformed personnel reporting the consistent use of condoms with non regular sexual partners in the last year | 2011 | NA | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey)
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select

## LFA_Programmatic Progress_1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: |  |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: |  |  | 14
Note: All programmatic indicators contained in the current Performance Framework should be listed, regardless of whether there are targets/results for the period covered by the Progress Update or whether the targets have been met in previous periods.
B. Programmatic Indicators | [15 empty] | B. Programmatic Indicators
Objective No. | Indicator No. | Indicator Description |  |  |  |  | Tied to | Targets cumulative? | Top 10 indicator? | Intended Target to date (from PF) | Actual Result to date (as reported by PR) | Verification Method | Verified Result | % achievement (Please calculate as appropriate) | LFA analysis on progress to date and any variance between targets and results, and any other comments (this should not be a “Copy and Paste” of the reasons provided by the PR) | Objective No. | Indicator No. | Indicator Description | Tied to | Targets cumulative? | Top 10 indicator? | Intended Target to date (from PF) | Actual Result to date (as reported by PR)
1 | 1.1 | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  |  | GF | Y-over program term | Yes - Top 10 | 62100 | 45528 |  |  |  |  | 1 | 1.1 | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) | GF | Y-over program term | Yes - Top 10 | 62100 | 45528
1 | 1.2 | Number of teachers trained on life skill based HIV/AIDS education |  |  |  |  | GF | Y-over program term | No | 629 | 1379 |  |  |  |  | 1 | 1.2 | Number of teachers trained on life skill based HIV/AIDS education | GF | Y-over program term | No | 629 | 1379
1 | 1.3 | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  |  | National Program | N-not cumulative | Yes - Top 10 | N/A | 0 |  |  |  |  | 1 | 1.3 | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | National Program | N-not cumulative | Yes - Top 10 | N/A | 0
1 | 1.4 | People reached by HIV/AIDS education in out-of-school settings |  |  |  |  | GF | Y-over program term | Yes - Top 10 | 21350 | 48843 |  |  |  |  | 1 | 1.4 | People reached by HIV/AIDS education in out-of-school settings | GF | Y-over program term | Yes - Top 10 | 21350 | 48843
1 | 1.5 | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  |  | GF | Y-over program term | Yes - Top 10 | 887 | 816 |  |  |  |  | 1 | 1.5 | Non Formal Education Instructors trained to provide HIV out-of-school education | GF | Y-over program term | Yes - Top 10 | 887 | 816
1 | 1.6 | Number of Transport workers reached with HIV education |  |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 880 | 1442 |  |  |  |  | 1 | 1.6 | Number of Transport workers reached with HIV education | GF and other donors | Y-over program term | Yes - Top 10 | 880 | 1442
1 | 1.7 | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) |  |  |  |  | GF and other donors | Y-over program term | No | 200 | 667 |  |  |  |  | 1 | 1.7 | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) | GF and other donors | Y-over program term | No | 200 | 667
1 | 1.8 | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 15000 | 14972 |  |  |  |  | 1 | 1.8 | Number of uniformed personnel and their families participating in HIV Awareness workshops | GF and other donors | Y-over program term | Yes - Top 10 | 15000 | 14972
1 | 1.9 | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 7500 | 6434 |  |  |  |  | 1 | 1.9 | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | GF and other donors | Y-over program term | Yes - Top 10 | 7500 | 6434
2 | 2.2 | Number of persons counseled and tested including provision of results |  |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 28000 | 38486 |  |  |  |  | 2 | 2.2 | Number of persons counseled and tested including provision of results | GF and other donors | Y-over program term | Yes - Top 10 | 28000 | 38486
2 | 2.3 | Number of people with advanced HIV infection receiving antiretroviral treatment |  |  |  |  | GF and other donors | N-not cumulative | Yes - Top 10 | 85 | 59 |  |  |  |  | 2 | 2.3 | Number of people with advanced HIV infection receiving antiretroviral treatment | GF and other donors | N-not cumulative | Yes - Top 10 | 85 | 59
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
C LFA comments on data quality and reporting issues (!) This section should contain any common issues and/or additional information related to data quality and reporting on the programmatic indicators which are not covered in 'LFA analysis on progress to date and any variance between targets and results'

## LFA_Grant Management_2
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: | 14
Section 2: Grant Management
A. PR & LFA COMMENTS ON THE FULFILLMENT OF OUTSTANDING CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
! This table should contain a full text of the CP and/or other special conditions due for fulfilment during this period or outstanding from previous periods.
! Some Special Conditions may apply to more than one period of grant implementation. Their fulfilment during one period does not automatically imply fulfilment in subsequent periods. The LFA should verify that the status of such conditions is reported by the PR during each period concerned.
! If a Condition Precedent that was previously fulfilled is re-opened due to new circumstances, and the issue addressed by this condition is considered critical, the issue should be disclosed by the LFA in the Section 4 LFA Findings and Recommendations. At the discretion of the Fund Portfolio Manager, the issue may be followed up through the management actions assigned by the Global Fund to the PR.
|  | PR SECTION | LFA SECTION
Conditions Precedent and/or other special conditions |  | Status | Status | Analysis (this should not be a "Copy and Paste" of the comments provided by the PR)
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  | Yes
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country; and |  | Yes
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  | Partially
The disbursement by the GF or use by PR of global funds to finance the procurement of Health products (as defined in Article 19 of the Standard Terms and Condition of this Agreement), is subject to the following conditions: |  | Yes
(a) The Principal Recipient shall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. The Updated PSM shall: |  | Yes
(i) address the deficiencies identified during the Phase 1 review in consultation with the GF, particularly those deficiencies relating to procurement process, quality assurance systems, storage and distribution as well as inventory mangement; and |  | Yes
(ii) include assumptions on forecasting for ARVs and testing products in order to ensure alignment with the performance framework and work plan and budget, where appropriate; and |  | Yes
(b) The written approval of the Global Fund of the updated PSM plan |  | Yes
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  | Yes
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of (1) program officer, (2) M& E Coordinator, (3) Finance Officer/Accoutant (4) Project Manager |  | Yes
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  | Yes
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting.
Select
Select
Select
B. PR & LFA REVIEW OF PROGRESS ON IMPLEMENTATION OF OUTSTANDING MANAGEMENT ACTIONS FROM PREVIOUS DISBURSEMENTS
! This table should contain all issues raised in the last Management Letter from the Global Fund or outstanding from previous Management Letters, and comment on the progress.
Global Fund Management Actions |  | LFA Review of PR Progress on Global Fund Management Actions
We would very much encourage the team to submit the PDUR on time. This would faciliate the process of timely disbursement from the Global Fund to your ministry
Submission of Annual Training Plan for approval from The Global Fund
We would like to request the PR to complete the recruitment of M&E consultant for implementing M&E training and development of supervision plan for the reporting units.
The coordination between PMT and NACP and SRs requires further strengthening for effective implementation of the grant . Regularize the coordination meeting
The reporting templates have been developed for the SR's to report on the activties. The report needs to be submitted on the agreed reporting format. The focal persons from each SR has to be trained on the new format
The newly recruited personnel in PMT & CCM secreteriat are required to have adequate information on the Global Fundguidelines for an effective coordination and reporting
C. PR & LFA COMMENTS ON ANNUAL GRANT REPORTING REQUIREMENTS
This table should contain the due date for the report due for submission. If a report is overdue, indicate the original due date and explain the reason for delay.
| PR SECTION |  | LFA SECTION
Required Documentation | Due date | Status | Due date | Status | Comments
PR Audit Report | 2011-12-31 | Preparation on track
Enhanced Financial Reporting (EFR) | 2011-01-31 | Submitted to GF

## LFA_Total PR Cash Outflow_3A
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter |  | Number: | 14
Progress Update - Period Covered: | Beginning Date: | 2011-05-01 |  | End Date: | 2011-07-31
Progress Update - Number: | 14
Currency: | USD
Section 3A: Total PR Cash Outflow
LFA-VERIFIED TABLES ON TOTAL PR CASH OUTFLOW
! For RCC grants the cumulative section of the table below should contain cumulative amount from the start of the RCC and not from the start of Phase 1 of the program.
| LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance |  | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance | All amounts are in: | LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance
1. Total cash outflow vs. budget | 244572 | 185602.95 | 58969.05 |  |  | 2371517.5 | 1687018.36 | 684499.14 |  | 1. Total cash outflow vs. budget | 244572 | 185602.95 | 58969.05 |  | 2371517.5 | 1687018.36 | 684499.14
1a. PR's total expenditures | 62422 | 89132.94 | -26710.94 |  |  | 1207512.5 | 831837.32 | 375675.18 |  | 1a. PR's total expenditures | 62422 | 89132.94 | -26710.94 |  | 1207512.5 | 831837.32 | 375675.18
1b. Disbursements to sub-recipients | 182150 | 96470.01 | 85679.99 |  |  | 1164005 | 855181.04 | 308823.96 |  | 1b. Disbursements to sub-recipients | 182150 | 96470.01 | 85679.99 |  | 1164005 | 855181.04 | 308823.96
| LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance |  | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance |  | LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance
2. Pharmaceuticals & health product expenditures vs. budget | 0 | 13613 | -13613 |  |  | 264000 | 137420.6 | 126579.4 |  | 2. Pharmaceuticals & health product expenditures vs. budget | 0 | 13613 | -13613 |  | 264000 | 137420.6 | 126579.4
2a. Medicines and pharmaceutical products | 0 | 0 | 0 |  |  | 49500 | 16927 | 32573 |  | 2a. Medicines and pharmaceutical products | 0 | 0 | 0 |  | 49500 | 16927 | 32573
2b. Health products and health equipment | 0 | 13613 | -13613 |  |  | 214500 | 120493.6 | 94006.4 |  | 2b. Health products and health equipment | 0 | 13613 | -13613 |  | 214500 | 120493.6 | 94006.4
* If LFA-entered data differs from PR's figures, the respective cells will change colour automatically
3. Indicate any expenditures (incurred or forecasted) that should not be financed by the Global Fund

## LFA_EFR Review_3B
LFA review of Enhanced Financial Reporting template
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | Ministry of Health
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
Section 3B: ENHANCED FINANCIAL REPORTING PERIOD
Current Period |  |  | Beginning Date: | End Date:
Cumulative Period |  |  | Beginning Date: | End Date:
1. CHECKLIST
The following information provided by the Principal Recipient in its EFR has been checked. |  |  |  |  | Comments if any:
| Select | The template has been fully completed.
1
| Select | The total figures in Tables A, B and C are equal.
2
| Select | The reporting dates are correct for both current period and cumulative period.
3
| Select | The total budget figure is accurate based on existing approved budgets.
4
| Select | The PR expenditure in Table C is consistent with PR expenditure for the same period as provided in the Progress Updates/Disbursements Request (PU/DR).
5
| Select | The total expenditure is supported by appropriate documentation ( PR expenditure reports, bank reconciliations, SR expenditure reports to PR etc.) or reasonable assumptions.
6
2. COMPLETION OF THE TEMPLATE
Comments on the process, assumptions and supporting documentation used by the PR to complete the template. (If space is insufficient, please provide comments in an addendum)
3. VARIANCE ANALYSIS
Comments on the explanations for variances provided by the PR (LFA can also provide comment directly on the EFR template completed by the PR)
Signed on behalf of the LFA:
Name:
Title:
Date and Place:

## LFA_Procurement Info_4
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter |  | Number: |  | 14
Progress Update - Period Covered: | Beginning Date: | 2011-05-01 |  | End Date: |  | 2011-07-31
Progress Update - Number: | 14
Section 4: LFA-verified Procurement and Supply Management Information
| PR's response | LFA's response | LFA Comments/Analysis
1a. Has the PR updated the Price Quality Reporting (PQR) with the required information on the pharmaceuticals and health products received during the period covered by this PU/DR’ (if applicable)? (If health products procurement information has not been entered into the PQR, please explain why in comments box) | N/A | Select
1b. Value of Pharmaceuticals and Health Products in the PQR (6 categories only)
(!) This table is included in the PU/DR form with the aim to improve completeness of information in the PQR system and not for comparing PQR amounts vis-à-vis expenditure per se. NB: PQR and expenditure amounts on health products may not be equal due to a timelag between payments and delivery of pharmaceuticals/health products. (!) For further guidance on PQR data entry, please refer to the guidelines.
Reporting Currency
PQR Product Categories | Value of products received during reporting period | Value of products entered by the PR and verified as correct by the LFA in the PQR during reporting period | Variance | Reason for Variance | Cumulative value of products received since Jan 2011 | Cumulative value of products verified as correct by the LFA in the PQR since Jan 2011 | Variance | Reason for Variance
1. Anti-malaria medicines
2. Bed nets
3. Rapid Diagnostic Tests
4. Condoms
5. Anti-retrovirals
6. Anti-TB Medicines
Total | 0 | 0 | 0 |  | 0 | 0 | 0
2. Based on best information available to the LFA, are there any risks of drug stockout at the central level in the next period of implementation? (If yes, please explain in comments box) ! This section should be completed by the LFA based on best information on stock levels at the central level available to the LFA and should not require dedicated visits for on-site checks of stocks. | No | Select
3. PR comments on issues related to the procurement and supply management of pharmaceuticals and health products |  |  |  | LFA analysis on issues related to the procurement and supply management of pharmaceuticals and health products
Due limited staffs in DVED to deal with the procurement of drugs and also with the stringetn rules on drugs procurement of Drug Regulatory Authrity there has been stock out of some of the drugs. But this has not affedted the drugs supply of ARV DRUGS

## LFA_Findings&Recommendations
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: | 14
LFA-specific section: LFA Findings & Recommendations
! Based on the information provided in the previous sections and your understanding of the grant, please summarise any important management issues, proposing a recommendation for each. NB: an issue is considered as 'important' if it impacts or is likely to impact program implementation and results. ! Instead of repeating detailed descriptions of issues covered in other sections, it is acceptable to state the issue and reference the section containing the details.
Functional Areas | Description of Identified Issues (in order of importance) |  |  | LFA Recommendations (in order of importance) | FPM Comments (to be completed upon receipt of the LFA-verified form)
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
LFA_Findings & Recommendations
Select
Yes
No
Select
Program management (including SR management)
Financial management and systems
Monitoring and evaluation
Pharmaceutical & health product management
Other management issues, including: PR capacity to develop quality programmatic and financial reports

## LFA_Cash Reconciliation_5A
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 0
Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  | N/A
Section 5: LFA-verified Cash Reconciliation & Disbursement Recommendation
A. LFA-VERIFIED CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
|  |  |  | PR-reported amounts | LFA-verified amounts | LFA Comments on verified amounts (if they are different from those reported by the PR) and PR's explanation of reconciliation adjustments (line 9)
1. Cash Balance: Beginning of period covered by Progress Update (line 10 from Cash Reconciliation section of the period covered by the previous Progress Update): |  |  |  | 276182.77
Add: |  |  |  | 0
2. Cash received by the PR from the Global Fund during the period covered by this progress update: (1)
| 3. Cash disbursed to third parties by the Global Fund on behalf of the PR during the period covered by this progress update: (1) |  |  | 0
| 4. Interest received on bank account |  |  | 0
| 5. Revenue from income-generating activities (if applicable) |  |  | 0
| 6. Other income, if applicable (e.g. income from disposal of fixed assets, tax refunds) |  |  | 39717.41
Less: | 7. Total PR cash outflow during period covered by Progress Update (value entered in Section 3A "Total cash outflow"): |  |  | 185602.95
| 8. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign) |  |  | 0
| 9. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) |  |  | 0
10. Cash Balance: End of period covered by Progress Update: |  |  |  | 130297.23 | 0

## LFA_Disbursement Recommend_5B
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 0
Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Disbursement Request - Number: |  | N/A
Currency: |  | USD
Section 5: LFA-verified Cash Reconciliation & Disbursement Recommendation
B. LFA-RECOMMENDED DISBURSEMENT AMOUNT AND EXPLANATIONS
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update:
1. Period beginning date: |  |  | end date: |  |  | Approved budget amount (reported by PR): |  | 0 | Forecasted amount (reported by PR): | 0
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount:
2a. Cash buffer period (by default)
(cash "buffer") beginning date: |  |  | end date: |  |  | Approved budget amount (reported by PR): |  | 0 | Forecasted amount (reported by PR): | 0
PR Total Forecast
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount: |  | 0
2b. Additional "buffer" (discretionary, select only if there is a prior agreement with the FPM) (1) | [10 empty] | LFA Total Forecast
0
(cash "buffer") beginning date |  |  | end date: |  |  | approved budget amount: |  | 0 | forecasted amount: | 0
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount:
(1) Upon agreement with the FPM, additional Cash buffer can be requested if the PU/DR report contains a completed EFR report or a completed Annex on SR financials, requested by the Secretariat, or if there are any additional GF-specific requirements that cannot be delivered within 45 days. However such requests may or may not be satisfied based on the review of the current PUDR
(2) When the additional (cash "buffer" ) period is 1 or 2months, the approved budget and forecasted amounts should be calculated as prorated values for the period following the regular buffer period.
PR's explanation of any significant variance between forecasted amounts and amounts as originally budgeted.
LFA's explanation of any significant variance between forecasted amounts and amounts as originally budgeted. Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. NB. Consider the following items when providing the analysis. - Expected timing of payments for any significant budgetary items, - Impact of existing cash balance at SR levels - Current confirmed commitments to be paid during disbursement request period - Current/expected unit prices compared to those in the budget - Change in quantities compared to budget - Exchange rates and inflation - Linkage between budget absorption and programmatic performance to-date. ! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the disbursement period
Less: | 3. Cash Balance: End of period covered by Progress Update (number 10 from LFA or PR Cash Reconciliation sheet): |  |  |  | PR-reported amounts | LFA-verified amounts | LFA Comments
[5 empty] | 130297.23 | 0
| 4. Cash "in transit" disbursed to the PR: |  |  |  | 0
| 5. Cash "in transit" disbursed to third parties by the Global Fund on behalf of the PR : |  |  |  | 0
[5 empty] | PR-requested amount | LFA-recommended amount
6. Disbursement Request to the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): |  |  |  |  | 0 | 0
7. Does the PR's Disbursement Request include funds for health product procurement? |  |  |  |  | Select
8. Exchange Rate (used to translate local currency into grant currency)
|  | Rates used by the PR | LFA-verified rates |  | Name of local currency and LFA comments on the exchange rates used by the PR
| - used to convert Opening Cash Balance | 45.7
| - used to convert Closing Cash Balance | 45.7
| - used to convert Total PR Cash Outflow for the Progress Update Period | 45.7

## LFA_Overall Performance_6
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 14
Progress Update - Period Covered: |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31
Progress Update - Number: |  | 14
Section 6: LFA EVALUATION AND COMMENTS ON OVERALL PERFORMANCE
A. Overall Evaluation and Rating of Grant Performance (including a summary of how financial performance is linked to programmatic achievements)
! The evaluation should be undertaken by taking into account programmatic achievements, financial performance and program issues in various functional areas (M&E, Finance, Procurement, and Program Management, including management of sub-recipients). See Guidelines for more detailed guidance on the completion of this section. ! For RCC grants, this section should cover the period from the RCC start date through the end date of the current Progress Update period. ! For guidance on the methodology for rating overall performance, refer to Annex 2 of Guidelines.
Indicator rating | Select |  | Any major management issues resulting in downgrade? | Select |  | Overall Grant Rating | Select
B. LFA comments on PR planned changes in the program, if any
C. LFA Comments on External Factors Beyond Control of the Principal Recipients that have impacted or may impact program

## LFA_DisbursementRecommendation7
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | Ministry of Health
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
PROGRESS UPDATE PERIOD | [7 empty] | DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 14 |  | Disbursement Request - Disbursement Period: |  | Cycle: | Semester | Number: | 0
Progress Update - Period Covered: |  |  | Beginning Date: | 2011-05-01 | End Date: | 2011-07-31 |  | Disbursement Request - Period Covered: |  | Beginning Date: |  | End Date:
Progress Update - Number: |  |  | 14 |  |  |  |  | Disbursement Request - Number: |  | N/A
Section 7: Disbursement Recommendation
A. DISBURSEMENT RECOMMENDATION
| Overall Rating | Select
Indicative disbursement ranges by performance rating (included as a reference)
Performance rating |  |  | Range for cumulative disbursement amount (after the currently recommended disbursement)
A1 | Exceeding expectations |  | Above 95% of cumulative budget through the next reporting period
A2 | Meeting expectations |  | Between 85-105% of cumulative budget through the next reporting period
B1 | Adequate |  | Between 55-95% of cumulative budget through the next reporting period
B2 | Inadequate but potential demonstrated |  | Between 25-65% of cumulative budget through the next reporting period
C | Unacceptable |  | Below 35% of cumulative budget through the next reporting period
1. Cash amount requested by the Principal Recipient from the Global Fund for next disbursement period plus one additional quarter (amount in: USD): | [6 empty] | 0 |  | 0
2. LFA disbursement recommendation (amount in: USD): | [6 empty] | 0
State the amount in words
Cumulative budget through the next period of implementation (including the buffer) |  |  | Cumulative disbursed amount to date (*) |  | Cumulative disbursed after recommended disbursement (including the buffer) |  | % range |  | Is the recommended disbursement within the range?
| 2371517.5 |  |  |  | 0 |  | 0% |  | Select
(*)This data can be obtained from the "Disbursements in detail report (PDF)" (http://www.theglobalfund.org/documents/disbursementdetails.pdf)
3. Rationale for the LFA's disbursement recommendation (if resulting in cumulative disbursement outside the indicative ranges):
B. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [8 empty] | Comments regarding verifications, if any:
| Select | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request
| Select | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable).
| Select | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement).
| Select | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress.
| Select | Exchange rate stated by Principal Recipient has been verified and is correct.
| Select | PR Bank details verified/corrected by LFA
| Select | Current budget forecasts of the Principal Recipient for the next disbursement period plus buffer period have been reviewed for reasonableness
| Select | LFA has debriefed the Principal Recipient on the key findings (comment on the format of this debriefing)
NB: Please ensure that section 7C Bank Details on the following page is completed if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.
D. Summary of the LFA's approach used for verification of financial, programmatic and procurement data and Quality Assurance undertaken by the LFA
In this section the LFA should indicate, as applicable, what percentage of expenditures was verified at PR level, if any expenditures were verified at SR level, how many site visits were made, what tender documentation was verified, and any other material parts of verification procedures in line with the verification approach agreed upfront between the LFA and GF Secretariat based on country/grant risks. As a good practice, the verification approach needs to be reviewed jointly by the LFA and the Secretariat annually.
NB: The LFA should sign a printed version of the verified PU/DR and send it to the Secretariat as a pdf file by email, or include an electronic signature in the Excel file to be submitted to the Global Fund.
Signed on behalf of the LFA:
Name:
Title:
Date and Place:

## LFA_Bank Details_7C
LFA On-going Progress Review and Disbursement Recommendation
Note for LFAs: This page should be completed by the PR if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement. The amounts and bank details below are displayed as entered by the PR. If any of this information is incorrect, please correct them by overwriting with correct information.
7C: LFA-verified Bank Account Details
| Disbursement Request Period | 0
| Summary |  |  |  |  | Summary
|  | Beneficiary Name | Amount in grant currency |  |  |  | Beneficiary Name | Amount in grant currency
| Payee 1 - Principal Recipient: | Ministry of Health |  |  |  | Payee 1 - Principal Recipient: | Ministry of Health
| Payee 2: |  |  |  |  | Payee 2:
| Payee 3: |  |  |  |  | Payee 3:
| Payee 4: |  |  |  |  | Payee 4:
| Total |  | 0 |  |  | Total |  | 0
| Payee 1: |  |  |  |  | Payee 1:
| Beneficiary Name: | Ministry of Health |  | Owner of Bank Account: | Royal Government of Bhutan | Beneficiary Name: | Ministry of Health |  | Owner of Bank Account: | Royal Government of Bhutan
| Currency in which beneficiary should receive the funds | USD |  | Owner of Bank Account: | Federal Reserve Bank of New York | Currency in which beneficiary should receive the funds | USD |  | Owner of Bank Account: | Federal Reserve Bank of New York
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | 2108337 | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | 2108337
| Amount in Words: |  |  | Bank Address | 33 Liberty Street , NY 1004 ,USA | Amount in Words: |  |  | Bank Address | 33 Liberty Street , NY 1004 ,USA
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | FRNYUS33 | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | FRNYUS33
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): |  | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  |  | Routing Instructions:
| Payee 2: |  |  |  |  | Payee 2:
| Beneficiary Name: |  |  | Owner of Bank Account: |  | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: |  | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: |  | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address |  | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: |  | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): |  | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  |  | Routing Instructions:
| Payee 3: |  |  |  |  | Payee 3:
| Beneficiary Name: |  |  | Owner of Bank Account: |  | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: |  | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: |  | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address |  | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: |  | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): |  | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  |  | Routing Instructions:
| Payee 4: |  |  |  |  | Payee 4:
| Beneficiary Name: |  |  | Owner of Bank Account: |  | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: |  | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: |  | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address |  | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: |  | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): |  | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  |  | Routing Instructions:

## LFA_Annex-SR Financials
LFA On-going Progress Review and Disbursement Recommendation
Annex to PU/DR - LFA-reviewed Sub-recipient financial information ! Completion of this table by the PR and verification by the LFA are discretionary, and should be done upon the Secretariat's request.
Grant number: |  |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  |  | Cycle: | Quarter |  | Number: | 14
Progress Update - Period Covered: |  |  |  | Beginning Date: | 2011-05-01 |  | End Date: | 2011-07-31
Progress Update - Number: |  |  |  | 14
Currency: |  |  |  | USD
Note for LFAs: The information below is displayed as entered by the PR. If any of this information is incorrect, please correct them by overwriting with correct information.
Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR | Budget for Reporting Period* | Disbursed during Reporting Period* |  | Cumulative Budget through period of Progress Update* | Cumulative Disbursed through period of Progress Update* | Cumulative Actual Expenditure through period covered by this Progress Update | Cash balance at the end of the period covered by this Progress Update | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (1) between cumulative budget and cumulative expenditure and (2) between cumulative disbursement and cumulative expenditure (mandatory for amounts above $50,000 or equivalent and with more than 10% variance) | LFA Comments on the PR's overall verification efforts of SR expenditure and the explanations of variance provided | Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR | Budget for Reporting Period* | Disbursed during Reporting Period* | Cumulative Budget through period of Progress Update* | Cumulative Disbursed through period of Progress Update* | Latest Cumulative Actual Expenditure (as per most recent SR reports available at PR level) | End date of period covered in most recent SR report | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (mandatory for amounts above $50,000 and with more than 10% variance)
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
TOTAL |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | TOTAL |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
*TOTAL amount for these columns should reconcile with relevant amounts under "1b Disbursed to Sub Recipients" in Section 3A"
** Where the number of SRs is significant (over 10), SRs with small budgets (less than $50,000 or EUR equivalent cumulative each) do not need to be reported separately and the figures can be aggregated in a group called "Other Minor SRs"

## Annex for additional info
Annex 1 | Use these worksheets to provide more detailed information on EFR variances if necessary

## Memo HIV (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
Please select… | Please select… | Please select… | Please select… | Please select… |  | Please select…
Prevention: Behavioral Change Communication - Mass media | % of young women and men aged 15-24 who are HIV infected | impact | % of young people aged 15-24 who had sex with more than one partner in the last year | National Health Accounts | Please enter a corresponding indicator here… | Please select disease and Impact/Outcome first
Prevention: Behavioral Change Communication - community outreach | % of adults aged 15-49 who are HIV infected | outcome | % of young people aged 15-19 who have never had sex | DHS/DHS+ (Demographic and Health Survey) | Please enter a data source here…
Prevention: Condom distribution | % of adults and children with HIV still alive 12 months after initiation of antiretroviral therapy (extend to 2, 3, 5 years as program matures) |  | % of young people aged 15-24 who never had sex in the last year of those who ever had sex | MICS (Multiple Indicator Cluster Survey) | Please enter a SDA here…
Prevention: Counseling and Testing | % of infants born to HIV infected mothers who are infected |  | % of young people aged 15-24 reporting the consistent use of a condom with non-regular sexual partners in the last year | AIS (AIDS Indicator Survey)
Prevention: PMTCT | % of most-at-risk population(s) (sex workers, clients of sex workers, men who have sex with men, injecting drug users) who are HIV infected |  | % of young women and men who had sex before the age of 15 | SAMS (Service Availibility Mapping Survey)
Prevention: Post-exposure prophylaxis (PEP) | % of HIV seroprevalence among all newly registered TB patients |  | % of adults and children who are still on treatment after 6 months, 1, 2, 3, 5 years from the initiation of treatment | BSS (Behavioral and Surveillance Survey)
Prevention: STI diagnosis and treatment |  |  | % of injecting drug users who have adopted behaviors that reduce transmission of HIV. | Sentinel surveillance
Prevention: Blood safety and universal precaution |  |  | % of orphaned children compared to non-orphaned children aged 10-14 who are currently attending school | Serological surveys
Treatment: Antiretroviral treatment (ARV) and monitoring |  |  | % of young people aged 15-24 reporting the use of a condom the last time they had sex with a non-regular sexual partner | Prevalence surveys
Treatment: Prophylaxis and treatment for opportunistic infections |  |  | % of people expressing accepting attitudes towards PLWHA, of all people surveyed aged 15-49 | Facility-based survey
Care and support: Care and support for the chronically ill |  |  | % of female sex workers reporting the use of a condom with every client in the last month | Key informant survey
Care and support: Support for orphans and vulnerable children |  |  | % of men who have had sex with a female sex worker in the last year | Specific surveys (to be defined)
TB/HIV collaborative activities: HIV care and support for HIV-positive TB patients | TB/HIV collaborative activities: Intensified case-finding among PLWHA |  | % of men reporting the use of condom the last time they had anal sex with a male partner in the last 6 months | Civil registration systems (vital/disease specific registration)
Supportive environment: Policy development including workplace policy | TB/HIV collaborative activities: Prevention of TB disease in PLWHA |  |  | Census
Supportive environment: Strengthening of civil society and institutional capacity building | TB/HIV collaborative activities: Prevention of HIV in TB patients |  |  | Health service statistics
Supportive environment: Stigma reduction in all settings | TB/HIV collaborative activities: Prevention of opportunistic infections in PLWHA with TB |  |  | Patient register
Supportive environment: Program management and administration |  |  |  | Clinical cohort follow-up studies
HSS: Service delivery | TB/HIV collaborative activities: Provision of antiretroviral treatment for TB patients during TB treatment |  |  | Community services assessment
HSS: Human resources | HSS: PAL (Practical Approach to Lung Health) |  |  | Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
HSS: Community Systems Strengthening |  |  |  | Operational research
HSS: Information system & Operational research
HSS: Infrastructure
HSS: Procurement and Supply management
HSS: Other, specify

## Memo TB (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
please select… | please select… | please select… | please select… | please select…
Improving diagnosis | TB prevalence rate | impact | Case detection | National Health Accounts
Standardized treatment, patient support and patient charter | TB incidence rate | outcome | Treatment success rate | DHS/DHS+ (Demographic and Health Survey)
Procurement and supply management | TB mortality rate |  | Smear conversion rate | MICS (Multiple Indicator Cluster Survey)
M&E |  |  |  | AIS (AIDS Indicator Survey)
TB/HIV |  |  |  | SAMS (Service Availibility Mapping Survey)
MDR-TB |  |  |  | BSS (Behavioral and Surveillance Survey)
High-risk groups |  |  |  | Sentinel surveillance
HSS (beyond TB) |  |  |  | Serological surveys
PAL (Practical Approach to Lung Health) |  |  |  | Prevalence surveys
PPM / ISTC (Public-Public, Public-Private Mix (PPM) approaches and International standards for TB care) |  |  |  | Facility-based survey
ACSM (Advocacy, communication and social mobilization) |  |  |  | Key informant survey
Community TB care |  |  |  | Specific surveys (to be defined)
Programme-based operational research
Other:Specify
Supportive environment: Program management and administration |  |  |  | Civil registration systems (vital/disease specific registration)
Census
Health service statistics
Patient register
Clinical cohort follow-up studies
Community services assessment
Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
Operational research
R&R TB system, quarterly report
R&R TB system, yearly management report
Other Surveillance reports, specify

## Memo Malaria (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
please select… | please select… | please select… | please select… | please select…
Prevention: Behavioral Change Communication - Mass media | Death rates associated with Malaria: all-cause under-5 mortality rate in highly endemic areas | impact | % of U5 children (and other target groups) with malaria/fever receiving appropriate treatment within 24 hours (community/health facility) | National Health Accounts
Prevention: Behavioral Change Communication - community outreach | Incidence of clinical malaria cases (estimated and/or reported) | outcome | % of U5 children (and other target group) with uncomplicated malaria correctly managed at health facilities | DHS/DHS+ (Demographic and Health Survey)
Prevention: Insecticide-treated nets (ITNs) | Anaemia prevalence in children under 5 years of age |  | % of U5 children (and other target groups) admitted with severe malaria and correctly managed at health facilities | MICS (Multiple Indicator Cluster Survey)
Prevention: Malaria prevention during pregnancy | Prevalence of malaria parasite infection |  | % of children U5 sleeping under an ITN the previous night | MIS (Malaria Indicator Survey)
Prevention: Vector control (other than ITNs) | Laboratory-confirmed malaria cases seen in heath facilities |  | % of households with at least one ITN | SAMS (Service Availibility Mapping Survey)
Prevention: other - specify | Laboratory-confirmed malaria deaths seen in health facilities |  | % of pregnant women (and other target groups) sleeping under an ITN the previous night | BSS (Behavioral and Surveillance Survey)
Treatment: Prompt, effective anti-malarial treatment | Malaria-attributed deaths in sentinel demographic surveillance sites |  | % of pregnant women on Intermittent preventive treatment (IPT) according to national policy (specific to Sub-Saharian Africa) | Sentinel surveillance
Treatment: Home based management of malaria | API (Annual Parasite Index) (specific to Latin America and Asia) |  | % of households in malaria areas protected by IRS | MOH (routine HIS or HMIS)
Treatment: Diagnosis |  |  |  | RBM (Roll Back Malaria)
Treatment: other - specify |  |  |  | Serological surveys
Supportive environment: Monitoring drug resistance |  |  |  | Prevalence surveys
Supportive environment: Monitoring insecticide resistance |  |  |  | Facility-based survey
Supportive environment: Coordination and partnership development (national, community, public-private) |  |  |  | Key informant survey
Supportive environment: other - specify |  |  |  | Specific surveys (to be defined)
Supportive environment: Program management and administration |  |  |  | Civil registration systems (vital/disease specific registration)
HSS: Service delivery |  |  |  | Census
HSS: Human resources |  |  |  | Health service statistics
HSS: Community Systems Strengthening |  |  |  | Patient register
HSS: Information system & Operational research |  |  |  | Clinical cohort follow-up studies
HSS: Infrastructure |  |  |  | Community services assessment
HSS: Procurement and Supply management |  |  |  | Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
HSS: other - specify |  |  |  | Operational research
Questionnaire

## Definitions-lists-EFR (hidden)
Please Select…
Prevention
Treatment
Care and Support
TB/HIV Collaborative Activities
Supportive Environment
Health System Strengthening (HSS)
Please Select…
Prevention
Treatment
Supportive Environment
Health System Strengthening (HSS)
Please Select…
Prevention: Behavioral Change Communication - Mass Media
Prevention: Behavioral Change Communication - Community Outreach
Prevention: Insecticite-treated nets (ITNs)
Prevention: Malaria in pregnancy
Prevention: Vector control (other than ITNs)
Prevention: Other - specify
Treatment: Prompt, effective antimalatial treatment
Please Select…
TB Detection
TB Treatment
TB/HIV Collaborative Activities
Supportive Environment
Health System Strengthening
Please Select…
Improving diagnosis
Standardized treatment, pation support and patient charter
Procurement and Supply management
M&E
TB/HIV
MDR-TB
High-risk groups
Please Select…
FBO
NGO/CBO/Academic
Private Sector
Ministry Health (MoH)
Other Government
UNDP
Other Multilateral Organization