## Cover Sheet
On-going Progress Update and Disbursement Request and LFA On-going Progress Review and Disbursement Recommendation
In completing this report, please refer to the detailed "Guidelines for completing the PR “ongoing progress update and disbursement request”, and LFA “ongoing progress review and disbursement recommendation”
During the lifetime of a grant, the Global Fund periodically disburses funds to the Principal Recipient (PR) based on demonstrated program performance and financial needs for the following period of implementation. The PR’s ongoing progress update and disbursement request (PU/DR) is both a progress report on the latest completed period of program implementation and a request for funds for the following period of implementation. Its purpose is to provide an update of the programmatic and financial progress of a Global Fund-financed grant, as well as an update on fulfillment of conditions precedent, management actions and other requirements. The PU/DR, alongside the Local Fund Agent (LFA) ongoing progress review and disbursement recommendation (short-form: LFA-verified PU/DR), forms the basis for the Global Fund’s disbursement decision by linking historical and expected program performance with the level of financing to be provided to the PR. One Excel file contains both the PR’s PU/DR and the LFA-verified PU/DR. The PR should only complete the worksheets of the file pertaining to the PU/DR (the worksheet tabs color-coded in green), whereas the LFA should complete the worksheets of the file pertaining to the LFA-verified PU/DR (the worksheet tabs color-coded in blue). The Excel file also includes a reference checklist of supporting documents for the PU/DR review (the worksheet tab color-coded in yellow). This checklist is included for information and not for completion. The PU/DR should be completed by the PR of a Global Fund grant for every period in which a progress update is required, usually either on a quarterly, semiannual or annual basis, regardless of whether or not a disbursement is being requested. Once a year, the PR is expected to submit the Enhanced Financial Report (EFR) as part of the PU/DR (there is a dedicated tab for EFR in the Excel file). The PR is required to submit the PU/DR to the LFA within 45 calendar days from the closing date of the relevant progress update period when the report does not contain the EFR (as indicated in the performance framework of Annex A of the grant agreement) and within 60 calendar days when the report contains the EFR (once a year). The LFA should complete and submit a signed copy of the LFA-verified PU/DR to the Global Fund within ten working days after receiving the final signed version of the PU/DR from the PR and within 13 working days when the PU/DR report contains the EFR (once a year), unless agreed otherwise with the FPM (The LFA does not need to submit original/hard copies of each PU/DR reports. However, these documents should be available at the LFA’s offices for any audit/reviews. Also, the LFA should be ready at all times to submit these originals to the Secretariat upon request). In this report the LFA should provide an analysis and comments based on verification of the PR-reported information, document grant risks and recommendations for improving program implementation, and finally, provide a performance rating to the grant and disbursement recommendation for the Global Fund’s consideration. In defining the performance rating and recommending a disbursement amount, the LFA should use the Grant Rating Methodology of the Global Fund (as described in Annex 2 and communicated at various regional meetings and LFA training events) along with the Excel version of the Grant Rating Tool (to be provided to LFAs) to support the calculation of Indicator Rating.
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Programmatic Progress_1A
On-going Progress Update and Disbursement Request | [13 empty] | Select
AIS (AIDS Indicator Survey)
BSS (Behavioral and Surveillance Survey)
GENERAL GRANT INFORMATION | [13 empty] | Census
Country: |  | Bhutan | [11 empty] | Clinical cohort follow-up studies
Disease: |  | HIV/AIDS | [11 empty] | DHS/DHS+ (Demographic and Health Survey)
Grant Number: |  | BTN-607-G03-H | [11 empty] | MICS (Multiple Indicator Cluster Survey)
Principal Recipient: |  | Ministry of Health | [11 empty] | MIS (Malaria Indicator Survey)
Program Start Date: |  | 2008-02-01 | [11 empty] | WHO Global report/estimates
Currency: |  | USD | [11 empty] | Other (type as appropriate)
PROGRESS UPDATE
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: |  | 19
DISBURSEMENT REQUEST
Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 1
Disbursement Request - Period Covered: |  | Beginning Date: | 2013-02-01 | End Date: | 2014-01-31
Disbursement Request - Number: |  | 1st under TFM
Section 1: Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Year of Target | Intended Target | Report Due Date | Actual Result | Data Source of Results | Comments on results on Impact/Outcome indicators and data sources, and any other comments
[6 empty] | Value | Year
Impact | Percentage of Men & Women aged 15-49 who are HIV infected |  |  |  |  | 0.05% | 2006 | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey) | sentinel surveiialnce is planned to be conducted towards end of 2011 as in the past
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  |  | 0.20% | 2006 | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey) | sentinel surveiialnce is planned to be conducted towards end of 2011
Outcome | Percentage of out of school youths aged 15-24 reporting the consistent use of condoms with non regular sexual partners in last year |  |  |  |  | 47% | 2009 | 2011 | N/A | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey) | The results will be determined through the KAP end line survey is expected to take place in March 2012
Outcome | Percentage of uniformed personnel reporting the consistent use of condoms with non regular sexual partners in the last year |  |  |  |  | 53% | 2009 | 2011 | NA | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey) | The results will be determined through the KAP end line survey is expected to take place March 2012
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select

## PR_Programmatic Progress_1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: |  |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: |  |  | 18
Note: All programmatic indicators contained in the current Performance Framework should be listed, regardless of whether there are targets/results for the period covered by the Progress Update or whether the targets have been met in previous periods.
B. Programmatic Indicators
Objective No. | * Indicator No. | Indicator Description |  |  |  | Tied To | Targets cumulative? | Top 10 indicator? | Baseline (if applicable) |  | Intended Target to date | Actual Result to date | % achievement (Please calculate as appropriate) | Reasons for programmatic deviation from intended target and deviations from the related workplan activities
[9 empty] | Value | Year
1 | 1.1 | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  | GF | Y-over program term | Yes - Top 10 | 0 | 2006 | 85050 | 75197 | 88.42% | No update on the indicators in this reporting quarter, the number is expected to increase once the DYS carries out the last round of TOT this winter.
1 | 1.2 | Number of teachers trained on life skill based HIV/AIDS education |  |  |  | GF | Y-over program term | No | 0 | 2006 | 729 | 578 | 79.29% | As per the Ministry of Education policy, all the trainings are now rescheduled to be carried out during the winter vacations. Hence no updates
1 | 1.3 | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  | National Program | N-not cumulative | Yes - Top 10 | 45 | 2009 | N/A | 0 |  | This value will be determined through the KAP survey. The KAP survey has been awarded to Ms Kyingkhor Consultancy service and is under way.
1 | 1.4 | People reached by HIV/AIDS education in out-of-school settings |  |  |  | GF | Y-over program term | Yes - Top 10 | N/A | 2008 | 23750 | 23365 | 98.38% | No updates on the indicator in this reporting quarter.
1 | 1.5 | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  | GF | Y-over program term | Yes - Top 10 | 0 | 2006 | 879 | 816 | 92.83% | The acitivity is not reflected in the year 5 work plan. And because there is no budget, no further training was carried out. However, the SR- Nonformal education division have reqest reprograming of world Aids day celebration so that the remaining targets tied to this incidicator could be achived. awaiting approval.
1 | 1.6 | Number of Transport workers reached with HIV education |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 100 | 2009 | 2180 | 1721 | 78.94% | result same as that of the previous quarter, due to the closing of financial year, acitivity was not carried out.
1 | 1.7 | Number of Most at Risk individuals reached with HIV education materials (primary substance users and sex workers) |  |  |  | GF and other donors | Y-over program term | No | 0 | 2006 | 400 | 435 | 108.7% | in this reporting period 2 sex worker and 4 injecting drug users were reached with VCT services with no additonal cost to the project
1 | 1.8 | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 6000 | 2006 | 23500 | 17488 | 74.42% | No updates on the indicator in this reporting quarter, since there was there was no budget with the PR, Now that the PR have received the disbursement, PR will be disbursing funds to carry out the acitivity.
1 | 1.9 | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 500 | 2005 | 8500 | 6654 | 78.28% | No updates on the indicator in this reporting quarter, since there was there was no budget with the PR, Now that the PR have received the disbursement, PR will be disbursing funds to carry out the acitivity.
2 | 2.2 | Number of persons counseled and tested including provision of results |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 1500 | 2005 | 29600 | 45403 | 153.4% | During this reporting period a total of 3090 people were reached with VCT services with no additonal cost to the project
2 | 2.3 | Number of people with advanced HIV infection receiving antiretroviral treatment |  |  |  | GF and other donors | N-not cumulative | Yes - Top 10 | 25 percent (19) | 2006 | 95 | 99 | 104.2% | The no of people on ART is same as that of the previous quarter
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
* Indicator No. should correspond to the indicator number listed in the approved Performance Framework of the grant (1.1, 1.2, etc.)
C. Analysis of data quality and reporting issues (!) This section should contain (1) a summary of issues related to data quality and reporting on programmatic indicators, and any relevant issues which are not covered in 'Reasons for programmatic deviation', and (2) remedial actions that are underway or planned to address these issues.
Th

## PR_Grant Management_2
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: | 19
Section 2: Grant Management
A. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
! Please include in this table the CP number as per Grant Agreement and full text of CPs and/or other special conditions due for fulfilment during this period or outstanding from previous periods. ! Some Special Conditions may apply to more than one period of grant implementation. Their fulfilment during one period does not automatically imply fulfilment in subsequent periods. The LFA should verify that the status of such conditions is reported by the PR during each period concerned.
Conditions Precedent and/or other special conditions |  |  | Status | PR Comments on Progress of Implementation
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  |  | Yes | M&E officer has been recruited at the Project Management Unit to monitor the the GF activties for a duration of 3 years starting April 2010
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country; and |  |  | Yes | PMT has now standardized the reporting format for GF HIV reporting ans trained all the SR's . There are still more reporting formats which needs to be standardised
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  |  | Partially | The SR supervison plan has been developed and the M&E training has been conducted
The disbursement by the GF or use by PR of global funds to finance the procurement of Health products (as defined in Article 19 of the Standard Terms and Condition of this Agreement), is subject to the following conditions: |  |  | Yes | Updated PSM plan has been developed and submitted to GF
(a) The Principal Recipient shall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. The Updated PSM shall: |  |  | Yes | The PSM plan has been submitted to GF
(i) address the deficiencies identified during the Phase 1 review in consultation with the GF, particularly those deficiencies relating to procurement process, quality assurance systems, storage and distribution as well as inventory mangement; and |  |  | Yes | The dediciencies and gaps identified during the pashe 1 review process are being taken into account especially on the logistics and supply managagement
(ii) include assumptions on forecasting for ARVs and testing products in order to ensure alignment with the performance framework and work plan and budget, where appropriate; and |  |  | Yes | Appropriate forcasting for the ARV & diagnostic products have been done in close consultation with the Drug procurment division. The forcasting was based on the past consumption of the drugs and test kits from various service delivery points
(b) The written approval of the Global Fund of the updated PSM plan |  |  | Yes | PSM plan has been submitted since June 2010 and the plan has been approved in March 2011, the delay in approval of PSM plan has casued a major hitch to the implementation rate of project
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  |  | Yes | MOH has been designated as the new PR after the signing of the phase 2 agreement of the project.
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of (1) program officer, (2) M& E Coordinator, (3) Finance Officer/Accoutant (4) Project Manager |  |  | Yes | The PMU established to faciliate the coordination of GF grant have team comprising of Project Coordinator, M&E officer, 2 finance personel , 1 administrative assiatnt , 1 procurement officer dealing with the procurement of health products to manage the grants
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  |  | Yes | The detailed quarterly budget for year 4 &5 has been delivered and been approved by GF
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  | In Progress | The PQR shall be updated as & when the health products products & equipments are procured
Select
Select
Select
B. PR REVIEW OF PROGRESS ON IMPLEMENTATION OF OUTSTANDING MANAGEMENT ACTIONS FROM PREVIOUS DISBURSEMENTS
! Please list all issues raised in the last Management Letter from the Global Fund or outstanding from previous Management Letters, and comment on the progress. Please include the date of the management letter and the item number. Reference: management letter dated 10 February 2011
Global Fund Management Actions |  | PR Comments on Progress of Implementation
The reporting templates have been developed for the SR's to reports on the activties. However, the SR's are not using the templates consistently. The report should be submitted on agreed reporting format. The focal persons from each SR should be trained to report using the new format |  | The reporting template have been developed in microsoft access , the SR s were trained on the reporting tool in June 2011 at Paro. However the tool was first piloted and there were feedbacks on the tool. Now with the incorporation of the feed back from the SR , the tool have been re designed to meet the gound requirements. The PMT is planning to once again train the SR's on the usgae of the tools and from Q16, all the SR will report on the new tool. But some time SRS themselves are non complaint but PMT will find measures for them to report on time
We noted that the coordination between PMT, NACP & SRs has improved and regular quarterly meeting is taking place. Nevertheless, the SRs continue to underperform and there is delay in submission of preogress reports |  | Some of the SR's that underperform include BCCI and army. This is mainly because of the fact that they are not part of government entity and becomes difficult to get them to implement the work plan. We requested the CCM oversight committee to make an intervantion and a comprehensive review and analysis was carried out. The main reason in SR is also due to shortages of HR to implement the activties and due to different financial regulations they reports are incomplete and had to be sent to SRs time and again for complete documenttion and thus in the process the implementation is delayed. GF is their secondary responsibility and thus they give less importance to the implementation
During the reporting period one indicator “Number of people with advanced HIV infection currently receiving antiretroviral therapy” achieved only 69% of the target. We noted that the program has started using the new criteria for starting treatment as recommended by WI-IO which is to start ART with a CD4 count of 350. We have been informed that the treatment manual has been revised to incorporate this new recommendation and is now ready for printing. Officially the implementation of new treatment criteria has been initiated, but the awareness among the service providers and people living with HIV (PLWHIV) is not optimum. We would like to request NACP to initiate the awareness among the service providers and PLWHIV |  | The up gradation of new CD4 requirement from 200 to 350 has been discussed with the service providers. Departmental meetings were also held with the service providers including Medical specialists, Gynecologists, pediatricians and pharmacists. Based on the recommendation of the meeting, new guidelines were distributed to all the 20 district hospitals and 3 referral hospitals with office memo to adhere with new CD4 requirement. During the meeting Lhak-Sam was also in picture and PLHIV community is well aware of the new requirement and the frequency of CD4 monitoring.
Targets In reference to the indicator ‘Number of teachers trained on life skill based HIV/AIDS education’ have been overachieved. We have been informed that the result was not correctly reported for this indicator. We would like to request NACP to segregate the training data and report with the Progress Update for the Quarter 15. In addition, we would also like to request to review the results for other training related indicators and conñrm the accuracy of the reported result. No disbursement for training will be made until the correct results are submitted. |  | As of now 395 teachers were trained as TOT on LSE in the 5 districts of samtse, pemagatsel , sarpang, Gasa &dagana. From the Q 12 report the actual result was reported as 1110 however upon vvertifcation and validation of reports , the DYS focal person made a mistake in reporting and made a double reporting both the ToT & Cascade training. However after segregation of the reports it is found that the TOT through the Global Fund supports as of now from the 5 districts stand at 395teachers. in the phase 1 they have trained 269 teachers and in the year 3 they have trained 126 teachers which adds up to cumulatively 395 TEACHERS. The results have been segregated and only the TOT is being reported for the purpose of reporting to Global Fund. We have also been able to seggregate the indicators reported through donors such as UNFPA who also funded this activity |  | As of now 395 teachers were trained as TOT on LSE in the 5 districts of samtse, pemagatsel , sarpang, Gasa &dagana. From the Q 12 report the actual result was reported as 1110 however upon vvertifcation and validation of reports , the DYS focal person made a mistake in reporting and made a double reporting both the ToT & Cascade training. However after segregation of the reports it is found that the TOT through the Global Fund supports as of now from the 5 districts stand at 395teachers. in the phase 1 they have trained 269 teachers and in the year 3 they have trained 126 teachers which adds up to cumulatively 395 TEACHERS. In the year year they are now planning to train about 220 teachers in the month of january 2012 | As of now 395 teachers were trained as TOT on LSE in the 5 districts of samtse, pemagatsel , sarpang, Gasa &dagana. From the Q 12 report the actual result was reported as 1110 however upon vvertifcation and validation of reports , the DYS focal person made a mistake in reporting and made a double reporting both the ToT & Cascade training. However after segregation of the reports it is found that the TOT through the Global Fund supports as of now from the 5 districts stand at 395teachers. in the phase 1 they have trained 269 teachers and in the year 3 they have trained 126 teachers which adds up to cumulatively 395 TEACHERS. In the year year they are now planning to train about 220 teachers in the month of january 2012 | As of now 395 teachers were trained as TOT on LSE in the 5 districts of samtse, pemagatsel , sarpang, Gasa &dagana. From the Q 12 report the actual result was reported as 1110 however upon vvertifcation and validation of reports , the DYS focal person made a mistake in reporting and made a double reporting both the ToT & Cascade training. However after segregation of the reports it is found that the TOT through the Global Fund supports as of now from the 5 districts stand at 395teachers. in the phase 1 they have trained 269 teachers and in the year 3 they have trained 126 teachers which adds up to cumulatively 395 TEACHERS. In the year year they are now planning to train about 220 teachers in the month of january 2012
During the reporting period a high number for achievement has been reported for the indicator ‘Number of most at risk individuals reached with education materials (primarily substance users and sex workers)’. We would like to request your good office to share the information with the Global Fund on the mapping of MARP. |  | NACP has conducted a rapid assessment in the form of mapping of the MARPS such as the CSW and IDU , this report is available and the information on the mapping on the MARPS will be shared with the Global Fund as requested
The analysis of cumulative variances from Q9 to Q14 shows that there is still a need for strengthening the ñnance management for this grant. There are instances, where expenditure overshoot budget and the NACP is not fully aware of this situation. In case the variances are known, they are not in a position to give proper explanations and justifications. The Global Fund provided training for finance personnel in 2010. We would like to request your good office to look into this and request the PMT for better coordination with finance and program units. |  | PMT ensures that henceforth there will be enhanced coosrindation between the NACP, PMT & Finance unit through the involvement of the finance personnel during the quarterly PR -SR coordination meeting and keep the finance personnel on the loop
Surveillance strategy has not included armed forces personnel as one of the target groups although they are one of the high risk groups. We would like to encourage both NACP and PMT to initiate the discussion of inclusion of armed forces in the surveillance strategy. We would like to request your good to discuss this issue with armed forces. In addition, the technical partners (WHO, UNAIDS) can be also be consulted. |  | NACP has now included the armed forces under the surveillance strategy
Reporting on most at risk individuals reached with education materials needs to be improved. Data is not segregated according to risk groups. All people who visit the HISC's are reported as most at risk individuals. We would recommend the program to strengthen the reporting system and segregate data accordingly. This would help the program to design an effective implementation |  | This indicators is collected through the quarterly VCT reports, where the district health officer compiles the report every quarter and submits to the NACP. If we review the form carefully, there is data segregation on MARPs which include the CSW, MSM & IDU. However in VCT form armed forces and migrant workers have also been recoreded under the MARPs. But when PMT reports to Global Fund we donot include the armed forces and migrant workers, we only compile the traditional MARPs globally defined and accepted. As a measure to review the data from the VCT centers, M&E visit to supervise the quality of data is planned to be jointly carried out by PMT & NACP in the month of January 2012 and we would expect that we get seggregated data on MARP's . Also the HISC maintian a register when they reach out to the MARPs through advocacy
Capacity of the PHPM needs to be strengthened. The Program unit (NACP) and the DVED should coordinate on regular basis for procurement. In this case PMT needs to be more proactive for an effective coordination. |  | In all the PR -SR quarterly meeting an effort is made to engage the DVED staffs to attend the meeting, however due to too thinly stretched staffs they have not been able to make to several meetings. Henceforth in the Q15 meeting, PMT will ensure that DVED staffs are attending the regular meetings and if need be set aside other emergency meetings also.
C. PR COMMENTS ON ANNUAL GRANT REPORTING REQUIREMENTS
! Please indicate a date for the report due for submission. If a report is overdue, indicate the original due date and explain the reason for delay.
Required Documentation |  | Due date (dd-mmm-yy) | Status | Comments
PR Audit Report |  | 2012-12-31 | Preparation on track | The year 3 of the Global Fund programmes has been audited and the reports have not yet been issued by the Royal Audit . Once we get the reports we will forward to Global Fund secretariat
Enhanced Financial Reporting (EFR) |  | 2012-01-31 | Preparation on track

## PR_Total PR Cash Outflow_3A
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: |  | 19
Currency: |  | USD
Section 3A: Total PR Cash Outflow
! For RCC grants the cumulative section of the table below should contain cumulative amount from the start of the RCC and not from the start of Phase 1 of the program.
| Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
1. Total PR cash outflow vs. budget | 78545 | 8833 | 69712 |  |  | 2844101.07 | 2321650.11 | 522450.96
1a. PR's total expenditures | 78545 | 8833 | 69712 | The variance of USD 69712 was observed, because though the KAPB survey is under way, payments will be made only after submission of reports. |  | 1360155 | 1125098.76 | 235056.24
1b. Disbursements to sub-recipients | 0 | 0 | 0 |  |  | 1483946.07 | 1196551.35 | 287394.72
| Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
2. Total pharmaceutical & health product expenditures vs. budget | 0 | 0 | 0 |  |  | 317474 | 169585.37 | 147888.63
2a. Medicines and pharmaceutical products | 0 | 0 | 0 |  |  | 66179 | 32352.7 | 33826.3
2b. Health products and health equipment | 0 | 0 | 0 |  |  | 251295 | 137232.67 | 114062.33

## EFR HIV AIDS Financial Data_3B (hidden)
SECTION 3B: HIV/AIDS FINANCIAL REPORTING FORM
Country |  | Bhutan |  |  | PLEASE REFER TO THE "GUIDANCE FOR COMPLETION OF THE ENHANCED FINANCIAL REPORTING TEMPLATE" DOCUMENT TO ASSIST YOU IN COMPLETING THE TEMPLATE
Grant No. |  | BTN-607-G03-H
PR |  | Ministry of Health |  |  | TO BE COMPLETED ONLY ONCE A YEAR EXCEPT AT MONTH 18 FOR PURPOSES OF PHASE 2 REVIEW
Currency |  | USD
[6 empty] | dd-mm-yyyy |  |  |  | dd-mm-yyyy
|  |  |  | Current Reporting Period | Start Date: |  |  | Cumulative Reporting Period | Start Date:
[5 empty] | End Date: |  |  |  | End Date:
The end date for the current reporting period and cumulative reporting period must be the same
The "TOTAL" rows in Table A, B and C will have a RED background if the amounts in each table do not agree. If the Totals for each Table agrees, these rows will have a YELLOW background.
A- BREAKDOWN* BY EXPENDITURE CATEGORY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period |  |  |  | All amounts are in: | Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
# | Category |  |  | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance | 1. Total PR cash outflow vs. budget | 78545 | 8833 | 69712 |  | 2844101.07 | 2321650.11 | 522450.96
1 | Human Resources |  |  | 6000 |  | 6000 | [5 empty] | 1a. PR's total expenditures | 78545 | 8833 | 69712 |  | 1360155 | 1125098.76 | 235056.24
2 | Technical Assistance |  |  | 0 | [7 empty] | 1b. Disbursements to sub-recipients | 0 | 0 | 0 |  | 1483946.07 | 1196551.35 | 287394.72
3 | Training |  |  | 141354 |  | 141354
4 | Health Products and Health Equipment |  |  | 0 | [8 empty] | Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
5 | Medicines and Pharmaceutical Products | [10 empty] | 2. Total pharmaceutical & health product expenditures vs. budget | 0 | 0 | 0 |  | 317474 | 169585.37 | 147888.63
6 | Procurement and Supply Management Costs |  |  | 0 | [7 empty] | 2a. Medicines and pharmaceutical products | 0 | 0 | 0 |  | 66179 | 32352.7 | 33826.3
7 | Infrastructure and Other Equipment |  |  | 47910 |  | 47910 | [5 empty] | 2b. Health products and health equipment | 0 | 0 | 0 |  | 251295 | 137232.67 | 114062.33
8 | Communication Materials |  |  | 45375 |  | 45375
9 | Monitoring & Evaluation |  |  | 2460 |  | 2460
10 | Living Support to Clients/Target Populations |  |  | 0
11 | Planning and Administration |  |  | 0
12 | Overheads |  |  | 1473 |  | 1473
13 | Other |  |  | 0
|  |  | TOTAL | 244572 | 0 | 244572 |  | 0 | 0 | 0
B- BREAKDOWN* BY PROGRAM ACTIVITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | Macro-category | Objectives | Service Delivery Area | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
TOTAL |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 39 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
C- BREAKDOWN* BY IMPLEMENTING ENTITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | PR/SR | Name | Type of Implementing Entity | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
|  |  | TOTAL | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 51 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
* The sum of all three breakdowns should be equal (A- Budget Line-item, B- Program Activity, C- Implementing Entity).
** For the purposes of this report, the SDA Program management and administration should be included in the Supportive Environment Macro Category.
D- ADDITIONAL INFORMATION
Please disclose any relevant information concerning the information in the above tables. Refer to the Guidelines for Completing the Template if required.
E- DISBURSEMENTS BREAKDOWN BY IMPLEMENTING ENTITY |  |  |  | Cumulative Reporting Period
# | Name | Type of Implementing Entity | Cumulative Disbursements | Comments
Please Select…
Please Select…
Please Select…
Please Select…
Please Select…
|  | TOTAL | 0
Note on A34: Insert Number
Note on A46: Insert Number
Note on A69: Insert Number
Note on B29: This category should only be used as a last resort if there is a type of cost that absolutely cannot be allocated to another cost category
Note on C34: Please remember to include the full name of the objective. If an objective has more than 1 SDA, repeat the objective name on each row for the relevant SDA
Note on C69: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D46: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D75: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on E40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on E52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E68: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on E69: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on F30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on F40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on F52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on G8: Start date for current period cannot be earlier than cumulative period
Note on G30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on G40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on G52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on H16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on I15: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I20: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I21: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I30: Please ensure that: -the figure here agrees with the figure in the corresponding cells in Tables B and C (in this tab). If they do not the background color will be RED; and -the figure also agrees with the cumulative budget figure in the corresponding cell (H11) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I33: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on I45: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on J20: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J21: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on J40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on J52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on K8: Start date for current period cannot be earlier than cumulative period
Note on K30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on K40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on K52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on L16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.

## PR_Procurement Info_4
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: | 19
Section 4: Procurement and Supply Management
Comments
1a. Have you updated the Price Quality Reporting (PQR) with the required information on the pharmaceuticals and health products received during the period covered by this PU/DR’ (if applicable)? If health products procurement information has not been entered into the PQR, please explain why. ! For further guidance on PQR data entry, please refer to the guidelines. |  |  | No | During the reporting period no procurment of health products were made . However we update the PQR as a mandate by The Global Fund as and when procurment of health products are made
2. Based on the most up-to-date stock situation, are there any risks of stockouts of key pharmaceuticals & health products at the central level in the next period of implementation? If yes, please comment. |  |  | No | There are no risk of stock outs of ARV drugs for the people on treatment as of most up to date stock situation. The DVED responsible for the procurement and forecasting of drugs ensures that there are no stock out of ARV drugs. Through the approved year 3 budget they have procured one consignment of ARV drugs and the stocks are expected to last for atleast 6 months.
3. Comment on additional issues related to the procurement and supply management of pharmaceuticals and health products

## PR_Cash Reconciliation_5A
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  | BTN-607-G03-H |  |  |  | ! A Statement of Sources and Uses of Funds (SSUF) is to be provided by PR along with the PUDR form
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: |  | 19
Currency: |  | USD
Section 5: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 10 from Cash Reconciliation section of the period covered by the previous Progress Update):
6738.12
Add: | 2. Cash received by the PR from the Global Fund during the period covered by this progress update: | [5 empty] | 0
| 3. Cash disbursed to third parties by the Global Fund on behalf of the PR during the period covered by this progress update: | [5 empty] | 0
4. Interest received on bank account
| 5. Revenue from income-generating activities (if applicable) | [5 empty] | 0
| 6. Other income, if applicable (e.g. income from disposal of fixed assets, tax refunds) | [6 empty] | 0
Less: | 7. Total cash outflow during period covered by Progress Update (value entered in Section 3A "Total cash outflow"): | [5 empty] | 8833
8. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign)
| 9. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) | [5 empty] | 0 | 8833
10. Cash Balance: End of period covered by Progress Update: | [7 empty] | -2094.88
Explanation of reconciliation adjustments (line 9)
! An explanation must be provided if there have been any adjustments.
balance figure un USD account due to exchange rate fluctuation

## PR_Disbursement Request_5B
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  |  |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  |  |  | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: |  |  |  |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: |  |  |  |  | 19
Currency: |  |  | USD
Section 5: Cash Reconciliation and Disbursement Request
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update:
1. Period beginning date: |  |  |  | 2013-02-01 |  | end date: | 2014-01-31 |  | approved budget amount: | 333177.17 | forecasted amount: | 333177.17
2a. Cash buffer period (by default)
(cash "buffer") beginning date: |  |  |  | 2014-02-01 |  | end date: | 2014-04-30 |  | approved budget amount: |  | forecasted amount:
PR Total Forecast
2b. Additional "buffer" (discretionary, select only if there is a prior agreement with the FPM) (1) | [12 empty] | 333177.17
cash "buffer" agreed with FPM (2) |  | Select
(cash "buffer") beginning date |  |  |  | 2014-05-01 |  | end date: |  |  | approved budget amount: |  | forecasted amount:
(1) Additional Cash buffer can be requested if the next PU/DR report will contain a completed EFR report or a completed Annex on SR financials, requested by the Secretariat, or if there are any additional GF-specific requirements that cannot be delivered within 45 days. An agreement in principal from the FPM should be obtained prior to requesting an additional cash buffer.
(2) When the additional (cash "buffer" ) period is 1 or 2 months, the approved budget and forecasted amounts should be calculated as prorated values for the period following the regular buffer period.
Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. NB. Consider the following items when providing the analysis. - Expected timing of payments for any significant budgetary items, - Impact of existing cash balance at SR levels - Current confirmed commitments to be paid during disbursement request period - Current/expected unit prices compared to those in the budget - Change in quantities compared to budget - Exchange rates and inflation - Linkage between budget absorption and programmatic performance to-date. ! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the disbursement period
Less: | 3. Cash Balance: End of period covered by Progress Update (number 10 from PR Cash Reconciliation sheet): | [10 empty] | -2094.88
4. Cash "in transit" disbursed to the PR:
| 5. Cash "in transit" disbursed to third parties by the Global Fund on behalf of the PR | [11 empty] | -2094.88
6. PR's Disbursement Request to the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [12 empty] | 335272.05
7. Does the PR's Disbursement Request include funds for health product procurement? | [7 empty] | Yes
8. Exchange Rate (used to translate local currency into grant currency) | [7 empty] | Name of local currency, date and source of the exchange rate, and other comments (if appropriate)
| - used to convert Opening Cash Balance |  |  |  |  | 45.7 |  | Ngultrums, Royal Monetary Authrotity of Bhutan
| - used to convert Closing Cash Balance |  |  |  |  | 45.7 |  | Ngultrums, Royal Monetary Authrotiy of Bhutan
| - used to convert Total Cash Outflow for the Progress Update Period |  |  |  |  | 45.7 |  | Ngultrum, Royal Monetary Authority of Bhutan

## PR_Overall Performance_6
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: | 19
Section 6: Overall Performance
A. PR's Overall Self-Evaluation of Grant Performance (including a summary of how financial performance is linked to programmatic achievements)
! The self-evaluation should be undertaken by taking into account programmatic achievements, financial performance and program issues in various functional areas (M&E, Finance, Procurement, and Program Management, including management of sub-recipients). See Guidelines for more detailed guidance.
The overall performance is satsifactory during the reporting quarter
B. Planned Changes in the Program, if any
No changes in planned activty . All the activities carried out as per the approved work plan .
C. External factors beyond the control of the Principal Recipient that have impacted or may impact the Program

## PR_Cash Request_7A&B
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Bhutan
Disease: | HIV/AIDS
Grant number: | BTN-607-G03-H
Principal Recipient: | Ministry of Health
Program Start Date: | 2008-02-01
Currency: | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: | 19
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: | Cycle: | Annual | Number: | 1
Disbursement Request - Period Covered: | Beginning Date: | 2013-02-01 | End Date: | 2014-01-31
Disbursement Request - Number: | 1st under TFM
Section 7: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from line 14 – “PR's Disbursement Request” in the tab “PR_Disbursement Request_4B”), in grant currency |  | 335272.05
2. Amount requested in words (in: USD): |  | 0
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name: | Mr. Nima Wangdi
Title: | Secretary, Ministry of Health.
Date and Place: | 19/12/2012, Thimphu
NB: Please ensure that section 7C Bank Details on the following page is completed, if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.

## PR_Bank Details_7C
On-going Progress Update and Disbursement Request
NB: This page should be completed if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.
7C: Bank Account Details
Disbursement Request Period
Summary
|  | Beneficiary Name | Amount in grant currency
| Payee 1 - Principal Recipient: | Ministry of Health | 0
| Payee 2: | 0 | 0
| Payee 3: | 0 | 0
| Payee 4: | 0 | 0
| Total |  | 0 | The total does not match requested amount on PR signature page
Payee 1:
| Beneficiary Name: | Ministry of Health |  | Owner of Bank Account: | Royal Government of Bhutan
| Currency in which beneficiary should receive the funds | USD |  | Owner of Bank Account: | Federal Reserve Bank of New York
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | 2108337
| Amount in Words: |  |  | Bank Address | 33 Liberty Street , NY 1004 ,USA
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | FRNYUS33
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 2:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 3:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 4:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:

## PR_Annex_SR-Financials
On-going Progress Update and Disbursement Request
Annex to PU/DR - Sub-recipient financial information - FOR DISCRETIONARY COMPLETION, UPON THE SECRETARIAT'S REQUEST
Has the Secretariat requested the PR to complete this Annex for this reporting period?
Grant number: |  |  |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  |  |  | Cycle: | Quarter |  | Number: | 19
Progress Update - Period Covered: |  |  |  |  | Beginning Date: | 2012-08-01 |  | End Date: | 2012-10-31
Progress Update - Number: |  |  |  |  | 19
Currency: |  |  | USD
Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR |  | Budget for Reporting Period* | Disbursed during Reporting Period* |  | Cumulative Budget through period of this Progress Update* | Cumulative Disbursed through period of this Progress Update* | Cumulative Actual Expenditure through period covered by this Progress Update | Cash balance at the end of the period covered by this Progress Update | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (1) between cumulative budget and cumulative expenditure and (2) between cumulative disbursement and cumulative expenditure (mandatory for amounts above $50,000 or equivalent and with more than 10% variance)
Department of Youth & Sports, MoE | 0 |  |  | 0 |  |  | 318609 | 0 | 225097.78 |  | 93511.22 | Yes
Department of Adult & Higher Learning, MoE | 0 |  |  | 0 | 0 |  | 303430 | 0 | 218135.01 |  | 85294.99 | 0
Ministry of Labour & Human Resource | 0 |  |  | 0 | 0 |  | 35465 | 0 | 37040.91 |  | -1575.91 | 0
Bhutan Chamber of Commerce & Industries | 0 |  |  |  | 0 |  | 97975 | 0 | 78440.98 |  | 19534.02 | 0
Armed Forces | 0 | [5 empty] | 140815 | 0 | 85801.71 |  | 55013.29 | 0
Dratshang Lhengtshog | 0 | [5 empty] | 66945 | 0 | 58142.86 |  | 8802.14 | 0
Royal Institute of Health Sciences | 0 |  |  | 0 | 0 |  | 61250 | 0 | 51109.6 |  | 10140.4 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
TOTAL |  |  |  | 0 | 0 |  | 1024489 | 0 | 753768.85 |  | 270720.15
*TOTAL amount for these columns should reconcile with relevant amounts under "1b Disbursed to Sub Recipients" in Section 3A"
** Where the number of SRs is significant (over 10), SRs with small budgets (less than $50,000 cumulative each) do not need to be reported separately and the figures can be aggregated in a group called "Other Minor SRs"

## Checklist
List of supporting documents for PU/DR review
This checklist is included for information and not for completion.
List of Latest Approved Documents by functional area | To be made available to the LFA by the PR | To be submitted by the LFA to the Secretariat | Comments
M&E
Performance Framework | x
M&E Plan | x
Survey results | x |  | For Impact/Outcome indicators
M&E Systems Strengthening Assessment | x |  | If newly available during the reporting period.
Other M&E assessments done by partners to assess data quality and M&E system issues. | x |  | If newly available during the reporting period.
Procurement
Consumption reports for pharmaceuticals and health products | x
Supplier invoices | x
PSM Plan | x
Stock level reports | x
Finance
Approved budgets | x |  | For the periods covered by Progress Update and Disbursement Request, including the buffer period.
Statement of sources and uses of funds (Cash flow statement) | x | x | See guidance on SSUF content and format in the guidelines.
Cash books | x
General Ledger | x
Cash forecasts | x
Bank statements | x
Bank Reconciliations | x
Annual PR Audit Report, Financial Statements, Management Letters and Responses (if Due) | x | x
Annual SR Audit Report, Financial Statements, Management Letters and Responses (if Due) | x
General Management
Grant Agreement (including Annex A and subsequent implementation letters) | x
Workplan | x

## LFA_Programmatic Progress_1A
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office: |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  | Bhutan
Disease: |  | HIV/AIDS
Grant Number: |  | BTN-607-G03-H
Principal Recipient: |  | Ministry of Health
Program Start Date: |  | 2008-02-01
Currency: |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: |  | 19
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 1
Disbursement Request - Period Covered: |  | Beginning Date: | 2013-02-01 | End Date: | 2014-01-31
Disbursement Request - Number: |  | 1st under TFM
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators | [12 empty] | A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  | Year of Target | Intended Target (from Attachment) | Report Due Date | Actual Result (as reported by PR) | Data Source of Results | Verification Method | Verified Result | LFA comments on (a) verified result, (b) source of information used by the PR to report results, including the status of completion of surveys and other methods to measure Impact/Outcome, as applicable, | Impact / Outcome | Indicator Description | Year of Target | Intended Target (from Attachment) | Report Due Date | Actual Result (as reported by PR) | Data Source of Results
Impact | Percentage of Men & Women aged 15-49 who are HIV infected |  |  |  | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey) | PR on site visit | NA as survey was not done | As per the PF, sentinel survey is to be conducted on a yearly basis in 2010 (Year 3), 2011 (Year 4) & 2012 (Year 5). However, the PR has not been able to conduct the survey in Year 3 because of lack of funds. A new surveillance strategy (draft titled: STI and HIV/AIDS Surveillance Strategy for Bhutan 2010-2013) has been developed, which outlines the strategy of collecting and managing the data on prevalence and risk behavior of different population groups. The data collected will be comparable with the baseline information of 2007. The PR expects to undertake the survey in the next quarter and report on the results. Since funds are available it will not be difficult for the PR to undertake this acitvity and so it is expected that the results will be reported in the beginning of 2012. The current prevalence is reported as 0.2 % with a range of 0.1-0.3 % in 2009 (Source UNAIDS 2009), however this needs to be confirmed through the next surveillance report. | Impact | Percentage of Men & Women aged 15-49 who are HIV infected | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey)
Impact | Percentage of uniformed personnel who are HIV infected |  |  |  | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey) | PR on site visit | NA as survey was not done | As per the PF, sentinel survey is to be conducted on a yearly basis for 2010, 2011 & 2012. However, the PR has not been able to conduct the survey as per schedule in 2010 because of lack of funds. A new surveillance strategy (draft titled: STI and HIV/AIDS Surveillance Strategy for Bhutan 2010-2013) has been developed which incorporates sero behavior surveillance among drug users, transport workers and sex workers. Surprisingly armed forces personal have not been included in the group although the focus of this impact indicator and the target in the PF is directed towards armed forces. PR has been advised to include armed forces in the strategy. The PR expects to undertake the survey in the next quarter and report on the results. Since funds are available, it will not be difficult for the PR to undertake this acitvity and it is expected that the results will be reported in the beginning of 2012. The current prevalence is reported as less than 0.1 % (Source UNAIDS, 2009), however this needs to be confirmed through valid reports. | Impact | Percentage of uniformed personnel who are HIV infected | 2011 | <0.1% | - | - | BSS (Behavioral and Surveillance Survey)
Outcome | Percentage of out of school youths aged 15-24 reporting the consistent use of condoms with non regular sexual partners in last year |  |  |  | 2011 | N/A | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey) | PR on site visit | Not due for reporting | This is not due for reporting and will be reported after the second KAP survey which is scheduled to be done in the fifth (2012) year of the project. The baseline data as per the 2009 KAP survey shows that 47 % of out of school youth aged 15-24 years reported the consistent use of condoms. | Outcome | Percentage of out of school youths aged 15-24 reporting the consistent use of condoms with non regular sexual partners in last year | 2011 | N/A | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey)
Outcome | Percentage of uniformed personnel reporting the consistent use of condoms with non regular sexual partners in the last year |  |  |  | 2011 | NA | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey) | PR on site visit | Not due for reporting | This is not due for reporting and will be reported after the second KAP survey which will be done in the fifth (2012) and last year of the project. Baseline data from the 2009 KAP survey shows that 53 % of uniformed personnel reported consistent use of condoms with non regular sexual partner. | Outcome | Percentage of uniformed personnel reporting the consistent use of condoms with non regular sexual partners in the last year | 2011 | NA | Q2 of 2012 | N/A | AIS (AIDS Indicator Survey)
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select

## LFA_Programmatic Progress_1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: |  |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: |  |  | 19
Note: All programmatic indicators contained in the current Performance Framework should be listed, regardless of whether there are targets/results for the period covered by the Progress Update or whether the targets have been met in previous periods.
B. Programmatic Indicators | [15 empty] | B. Programmatic Indicators
Objective No. | Indicator No. | Indicator Description |  |  |  |  | Tied to | Targets cumulative? | Top 10 indicator? | Intended Target to date (from PF) | Actual Result to date (as reported by PR) | Verification Method | Verified Result | % achievement (Please calculate as appropriate) | LFA analysis on progress to date and any variance between targets and results, and any other comments (this should not be a “Copy and Paste” of the reasons provided by the PR) | Objective No. | Indicator No. | Indicator Description | Tied to | Targets cumulative? | Top 10 indicator? | Intended Target to date (from PF) | Actual Result to date (as reported by PR)
1 | 1.1 | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) |  |  |  |  | GF | Y-over program term | Yes - Top 10 | 85050 | 75197 | PR On-site Visit | 55829 | 74% | Cumulative achievement: 74 %. Cumulative actual/target 55,829/75,600. This result shows under-achievement. This is a top ten indicator. Results reported over program term. In this quarter, no young people were reached with HIV education and therefore the results are the same as for the previous quarters. The Department of Youth and Sports who is the SR for this activity has not implemented this activity for 3 consecutive quarters. This activity should be implemented routinely in the schools as the teachers guide is already distributed and life skills education is now part of the school curriculum. However with school final examination preparation followed by school holidays mean that this activity is unlikely to take place in the next two quarters. A new Focal person has been appointed in the school health program, Department of Youth and Sports. With three dedicated staff ,it is expected that the SR will now provide focus and accelerate activities to achieve targets. Source of information: Report by SR (DYS) submitted to PR | 1 | 1.1 | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) | GF | Y-over program term | Yes - Top 10 | 85050 | 75197
1 | 1.2 | Number of teachers trained on life skill based HIV/AIDS education |  |  |  |  | GF | Y-over program term | No | 729 | 578 | PR On-site Visit | 395 | 54.18% | Cumulative achievment: 58 % Cumulative actual/target 395/679. This result shows under-achievement. Results reported over program term. There was wrong reporting which was found out during the OSDV. We have requested SR/PR to recalculate the actual results for TOT where as SR had been reporting both TOT and cascade training. In the approved work plan and budget, there is budget to train (SDA 1.1.1: TOT on LSE) 120 teachers in Year 3, 226 teachers in Year 4, and 132 teachers in Year 5 and also budget to Train (SDA 1.1.2: Support to TOT in the implementation of further training of teachers in their communities/districts) 240 teachers in Year 3, 1529 Teachers in Year 4 and 773 teachers in Year 5. However this support to TOT is not reflected in PF and is not require to report as there is no indicator set for this. During the PU/DR reporting, SR/PR has combined both results thereby showing very high achievement. LFA received the corrected information and has cross checked the information and found that only 126 Teachers has been trained for SDA 1.1.1 in Year 3 and no budget has been released for Year 4. Although, SR is supposed (as per approved work plan) to train the teachers in Q13 but SR defer to Q16 which is for winter holidays. This is not to disturb the students during the academic session. This change in achievement should be use for previous quarters (Q12-14). Source of information: Interview with Project Manager of Project Management Team which manages the SR's for HIV program and quarterly report submitted by SR. DYS letter number: DYS/CSHD/GFATM/2011/2103 dated 4/3/2011 | 1 | 1.2 | Number of teachers trained on life skill based HIV/AIDS education | GF | Y-over program term | No | 729 | 578
1 | 1.3 | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) |  |  |  |  | National Program | N-not cumulative | Yes - Top 10 | N/A | 0 | PR On-site Visit | NA | Not due for reporting | No target has been set for this indicator. Here results are not due for reporting. Results are not cumulative The target set is at 60% and the result is due to be reported by quarter ending (Q19) in October 2012, which should result from another KAP survey in 2012. As per the KAP survey report of 2009, 45 % of young people in schools correctly identified ways of preventing HIV AIDS. This is much lower than that reported for university students and out of school youths (>60 %) however the criteria used in the KAP survey was more stringent (knowledge on all five indicators as used in the survey) and this could be the reason for reporting the low knowledge among school youth. There are 66,212 students studying in classes IX-XII which is an approximate number of young people 15-24 years of age. | 1 | 1.3 | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | National Program | N-not cumulative | Yes - Top 10 | N/A | 0
1 | 1.4 | People reached by HIV/AIDS education in out-of-school settings |  |  |  |  | GF | Y-over program term | Yes - Top 10 | 23750 | 23365 | PR On-site Visit | 22846 | 105% | Cumulative achievement: 105 % Cumulative actual/target 22,846/21,850. This result shows over-achievement. Results reported over program term. The PR has undertaken a review of the reported results and accordingly revised the figures for people reached in out of school setting. As pointed out by the LFA, only those people who are not in school and reached by the NFE centers is included. Accordingly it has been found that a total of 17,047 people were reached during phase 1 and a further 4,525 people were reached in year 3. Since most of these people were reached during World AIDS day celebration, the possibility of same people being repeatedly counted is still present, although it will be difficult to verify. The PR has also categorized people reached according to age (15-24 years) which is not in line with the PF. Reaching out to this group of young people is not appropriate because most of the out of school people are likely to be above 25 years of age especially in the NFE setting. Imparting HIV education to all NFE learners will be more appropriate. The Ministry of Labour and Human Resources (MoLHR) is the other SR which has reached 1,274 new graduates with HIV awareness in year 3. The total number of people reached in out of school setting is thus 22,846. The targets have been reached. The target is underestimated because there is a potentital of reaching more people as specified in the PF such as vocational training institutes and job seekers. The MoLHR should give more effort in reaching out to this group of people in out of school setting. Source of information: Quarterly reports submitted by Non Formal Division, Ministry of Education (SR), Interview with PMT. | 1 | 1.4 | People reached by HIV/AIDS education in out-of-school settings | GF | Y-over program term | Yes - Top 10 | 23750 | 23365
1 | 1.5 | Non Formal Education Instructors trained to provide HIV out-of-school education |  |  |  |  | GF | Y-over program term | Yes - Top 10 | 879 | 816 | PR On-site Visit | 816 | 92% | Cumulative achievement: 92 %. Cumulative actual/target 816/887. This result shows under-achievement. This is one of the top ten (training) indicators. Results reported over program term. No new instructors were trained in this quarter and the results are the same as reported for the previous quarters. Although the targets has not been reached, the PR has carried out refresher training for majority of trainers and has also trained 99 principals. The number of existing NFE centers in the country as reported in the previous quarter is currently 894 centers with 913 Instructors (Source of information: Telephonic interview with SR) and not 816 as reported by the PR. It is expected that the SR will train the new NFE instructors in the next quarter. The target is expected to be reached. Source of Information: Intervewwith PMT manager, reports submitted by the SR. | 1 | 1.5 | Non Formal Education Instructors trained to provide HIV out-of-school education | GF | Y-over program term | Yes - Top 10 | 879 | 816
1 | 1.6 | Number of Transport workers reached with HIV education |  |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 2180 | 1721 | PR On-site Visit | 1442 | 134% | Cumulative achievement 134%. Cumulative actual/target 1,442/880. This result shows overachievement. Results are reported over program term. In this quarter no additional transport workers were reached and the results are the same as that reported in Q13. The targets have already been reached for year 4. Transport workers are one of the high risk groups and the success of this activity is expected to reduce the risks among this group. The effectiveness of this program on the transport workers will be seen from the sero-behavior surveillance to be conducted annually in year 4 & 5. There are sudden increases in purchase of trucks and Lorries in Bhutan due to hydro-power constructions which has increased the number of transport workers (drivers and assistant). PR has included all the volunteers to partake in the awareness which has increase the target reached. The target set was based on the 2009 data provided by Road Safety and Transport Authority. However there is not much budget implication as same resource persons were used with larger audiences. | 1 | 1.6 | Number of Transport workers reached with HIV education | GF and other donors | Y-over program term | Yes - Top 10 | 2180 | 1721
1 | 1.7 | Number of Most at Risk individuals reached with HIV education materials (primary substance users and sex workers) |  |  |  |  | GF and other donors | Y-over program term | No | 400 | 435 | PR On-site Visit | 142 | 57% | Cumulative achievement: 57 %. Cumulative actual/target 142/250. This result shows underachievement. Results reported are cumulative over program term. As per the recommendations the PR has finally included only those people who are high risk in reporting the results in this quarter. A total of 22 people (15 commercial sex workers-CSW, 2 intravenous drug users and 5 clients of sex workers) were reached by the health inforamtion centers. The revised total is thus 142 most ar risk population (MARP) reached with HIV education material. There is still under reporting because the target group (Drug users and sex workers) remains largely hidden and there is very little information on the actual numbers. Nevertheless the PR should undertake more active measures to reach out to this group using peers and through contact tracing to achieve the targets. Source of Information: Quarterly report submitted by HISC to PMT; Interview with Project Manager PMT. | 1 | 1.7 | Number of Most at Risk individuals reached with HIV education materials (primary substance users and sex workers) | GF and other donors | Y-over program term | No | 400 | 435
1 | 1.8 | Number of uniformed personnel and their families participating in HIV Awareness workshops |  |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 23500 | 17488 | PR On-site Visit | 17461 | 103% | Cumulative achievement: 103 % Cumulative actual/target 17,461/17,000. The target is nearly achieved. This is one of the top ten (training) indicators. Results reported over program term. In this quarter the Royal Bhutan Army (RBA) has reached 2,516 soldiers and their families in 7 army wings across the country. The awareness campaigns are conducted by personnel from the Army Medical Unit based in Thimphu. As reported during the OSDV, the reporting by the SR is irregular and difficult to verify because of sensitive information. The targets have been reached. The variance is the result of mathematical error as reported in Q 9 (Feb-Apr 2010). No reports of awareness campaigns by the Royal Bhutan Police and Royal Body Guards in this quarter. Source of Information: Report of RBA submitted to the PMT on 25 June 2011; Review of HIV AIDS booklet for Armed forces developed by RBA; Interview with Project Manager PMT. | 1 | 1.8 | Number of uniformed personnel and their families participating in HIV Awareness workshops | GF and other donors | Y-over program term | Yes - Top 10 | 23500 | 17488
1 | 1.9 | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education |  |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 8500 | 6654 | Desk Review | 6434 | 86% | Cumulative achievement: 83 % Cumulative actual/target 6,434/7,750. This result shows under-achievement. This is one of the top10 equivalent indicators. Results reported over program term. In this quarter no religous persons were reached by HIV education and the results remain the same as reported in the previous quarter. This target has been underachieved. The numbers of monks are large and PR should ensure that the SR conducts this activity on time and that targets are reached. The monks play an important role in Bhutanese communities and can be an important person for advocacy and raising awareness. There are also few monks who have been detected as HIV positives and are therefore included as being at risk. The SR for this activity (Dratshang Lhentshog) has not been reporting this activity in a timely manner and there is limited oversight and monitoring by the PR. Source of Information: Quarterly Report of Dratshang Lhentshog submitted to the PMT; Interview with Project Manager PMT. | 1 | 1.9 | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | GF and other donors | Y-over program term | Yes - Top 10 | 8500 | 6654
2 | 2.2 | Number of persons counseled and tested including provision of results |  |  |  |  | GF and other donors | Y-over program term | Yes - Top 10 | 29600 | 45403 | PR On-site Visit | 42230 | 149% | Cumulative achievement: 149 % Cumulative actual/target 42,230/28,400. This result shows over-achievement. This is one of the top ten indicators. Results report cumulative over program term. In this quarter, 3,744 people (990 males and 2754 females) were counseled, tested and provided with results. The high number of females is because of testing during pregnancy which is offered to all pregnant women. The target for this activity is over achieved as it is a routine activity carried out at all hospitals including the Health Information Service Centers (HISC) and is routinely reported by all VCT health centers. The PR has reported the same figure as last quarter and has not added the new figures as reported by the NACP. The achievement of 149 % as compared to the target. The target has been underestimated The target was set in 2009 based on the experience of the revious year (2008) and is underestimated. However, there is not much budget implication as the same health workers do it routinely. Source of information: Quarterly VCT report compiled by the NACP, Interview with Program manager NACP. | 2 | 2.2 | Number of persons counseled and tested including provision of results | GF and other donors | Y-over program term | Yes - Top 10 | 29600 | 45403
2 | 2.3 | Number of people with advanced HIV infection receiving antiretroviral treatment |  |  |  |  | GF and other donors | N-not cumulative | Yes - Top 10 | 95 | 99 | PR On-site Visit | 63 | 74% | Cumulative achievement: 74 % Cumulative actual/target 63/85.This result shows under-achievement. This is a top ten indicator. Results report cumulative over program term. In this quarter 4 more people were started on ART taking the total to 63. The program has started using the new criteria for starting treatment as recommended by WHO which is to start ART with a CD4 count of 350. Although this has been officially implemented, people living with HIV (PLWHIV) and service providers are not aware and not many have come to receive treatment. There are only three centers in the country where CD4 count is done and therefore as PLWHIV come for their tests, more number of them is expected to be identified for starting treatment. The PR has also ordered the procurement of more anti retroviral medications and is ready to provide treatment to the expected higher numbers. With this the target is expected to be achieved. Source of information: Quarterly report submitted by Pharmacy department of JDWNRH (Treatment and care unit for PLHIV) to the NACP. Interview with Program Manager NACP. | 2 | 2.3 | Number of people with advanced HIV infection receiving antiretroviral treatment | GF and other donors | N-not cumulative | Yes - Top 10 | 95 | 99
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
C LFA comments on data quality and reporting issues (!) This section should contain any common issues and/or additional information related to data quality and reporting on the programmatic indicators which are not covered in 'LFA analysis on progress to date and any variance between targets and results'
There is no major variances between PR and LFA verified data

## ANNEXURE A (RATING)
Grant Rating Tool in Excel
Important: Please start entering the Data in the first row/field "B5" |  |  |  |  | Target |  | Result
Top 10 | Training indicator | Reverse Indicator? | Indicator Number | Indicator Name | Period | Value | R_Period | R_Value | Result % (*) | Q9 | q9
Yes | No | No | 1.1 | Young people reached by life-skill based HIV/AIDS education in schools-grade 7 and above (number and percentage) | 15 | 75600 | 15 | 55829 | 73.85%
No | Yes | No | 1.2 | Number of teachers trained on life skill based HIV/AIDS education | 15 | 679 | 15 | 395 | 58.17%
Yes | No | No | 1.3 | % of young people 15-24 in school who both correctly identify ways of preventing sexual transmission of HIV and who reject the major misconceptions about HIV transmission (UNGASS) | 15 |  | 15
Yes | No | No | 1.4 | People reached by HIV/AIDS education in out-of-school settings | 15 | 21850 | 15 | 22846 | 104.6%
Yes | Yes | No | 1.5 | Non Formal Education Instructors trained to provide HIV out-of-school education | 15 | 887 | 15 | 816 | 92%
No | No | No | 1.6 | Number of Transport workers reached with HIV education | 15 | 1080 | 15 | 1442 | 120%
No | Yes | No | 1.7 | Number of Most at Risk individuals reached with education materials (primary substance users and sex workers) | 15 | 250 | 15 | 142 | 56.8%
Yes | Yes | No | 1.8 | Number of uniformed personnel and their families participating in HIV Awareness workshops | 15 | 17000 | 15 | 17461 | 102.7%
Yes | Yes | No | 1.9 | Number of monks, nuns and members of non-formal religious groups reached by HIV/AIDS education | 15 | 7500 | 15 | 6434 | 85.79%
Yes | No | No | 2.2 | Number of persons counseled and tested including provision of results | 15 | 28000 | 15 | 42230 | 120%
Yes | No | Yes | 3.1 | Number and Percentage of people with advanced HIV infection receiving antiretroviral treatment | 15 | 85 | 15 | 63 | 120%
* The % of target reached for individual indicators is capped at 120% (to avoid over-performing indicators skewing the mean disproportionally )
| Calculation Table |  |  | Quantitative Indicator Rating
Performance Rating |  |  |  |  | ALL indicators rating
A1 |  | > 100% |  | Top 10 Indicators Rating | A1 | A2 | B1 | B2 | C
A2 |  | 100-90% |  | A1 | A1 | A1 | A2 | A2 | A2
B1 |  | 60-89% |  | A2 | A2 | A2 | A2 | B1 | B1
B2 |  | 30-59% |  | B1 | A2 | B1 | B1 | B1 | B2
C |  | <30% |  | B2 | B1 | B1 | B2 | B2 | B2
Top TEN indicators & Training |  | 3
Training indicators non Top 10 |  | 2
AVG performance on Top 10 TRAINING Indicators only |  | 93.5% |  | C | B2 | B2 | B2 | C | C
SUM perf Top ten Not Training |  | 418.4%
COUNT Top ten Not Training |  | 5
AVG performance on TOP TEN indicators (including TRAINING) |  | 85.32% |  | Important: The calculated INDICATOR RATING for a grant cannot equal A1 or A2 if one or more “Top 10 Indicator” or “Top 10 equivalent Indicator” is rated B2 or C (i.e., less than 60% achievement). Please fill in the Intermediate Result given by the Matrix in the box below, in order to get the final Quantitative Rating.
Number of TOP TEN indicators with B2 or C Rating |  | 0
TOP TEN indicators rating |  | B1 |  | Intermediate Quantitative Rating result from the Matrix above | B1
AVG performance ALL indicators |  | 93.39%
ALL indicators rating |  | A2 |  | Final Quantitative Rating | B1
Intermediary Result for Quantitative Indicator rating |  | See Rating highlighted in the Matrix

## LFA_Grant Management_2
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: | 19
Section 2: Grant Management
A. PR & LFA COMMENTS ON THE FULFILLMENT OF OUTSTANDING CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
! This table should contain a full text of the CP and/or other special conditions due for fulfilment during this period or outstanding from previous periods.
! Some Special Conditions may apply to more than one period of grant implementation. Their fulfilment during one period does not automatically imply fulfilment in subsequent periods. The LFA should verify that the status of such conditions is reported by the PR during each period concerned.
! If a Condition Precedent that was previously fulfilled is re-opened due to new circumstances, and the issue addressed by this condition is considered critical, the issue should be disclosed by the LFA in the Section 4 LFA Findings and Recommendations. At the discretion of the Fund Portfolio Manager, the issue may be followed up through the management actions assigned by the Global Fund to the PR.
|  | PR SECTION | LFA SECTION
Conditions Precedent and/or other special conditions |  | Status | Status | Analysis (this should not be a "Copy and Paste" of the comments provided by the PR)
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has recruited or assigned a Monitoring & Evalaution (M&E) coordinator |  | Yes | Met | M & E Officer has been recruited since 2010 and is working for M & E of three diseases attached with PMT.
Provide evidence in form and substance satisfactory to the Global Fund that the Principal Recipient has standardised formats & guidelines for data collection and reporting through out the country; and |  | Yes | Met | PR has recruited a National TA to review the M & E System and to revise the existing SR data collection and reporting formats and guidelines. The TA has revised and all SRs were provided hands-on-training on the revised reporting format on 17 June 2011 at Paro. However, the new reporting format and guidelines is not been used by most of SRs to report the quarterly report. LFA was informed by SRs that the reporting format is too complicated to be used and most of the focal person in SRs is new who has not been trained. PR need to review the guidelines and report format and again conduct a hands-on training immediately.
Provide evidence, in form and substance satisfactory to the Global Fund, the the Principal Recipient has implemented and M&E training and supervision plan for reporting units |  | Partially | Met | The PR has recruited a National TA to review the M & E training and supervision plan for reporting units including SRs. LFA is yet to receive the report and to see the actual implementation of M & E training and supervision plan for reporting Units. LFA has asked PR to submit the report to LFA and GF.
The disbursement by the GF or use by PR of global funds to finance the procurement of Health products (as defined in Article 19 of the Standard Terms and Condition of this Agreement), is subject to the following conditions: |  | Yes | Met | Updated PSM plan was submitted to GF and was approved on 2 Feb 2011.
(a) The Principal Recipient shall submit to the Global Fund a plan for procurement , use & supply management of Health Products for phase 2 of program (Updated PSM Plan) in accordance with Global Fund guidelines for review and approval by the Global Fund. The Updated PSM shall: |  | Yes
(i) address the deficiencies identified during the Phase 1 review in consultation with the GF, particularly those deficiencies relating to procurement process, quality assurance systems, storage and distribution as well as inventory mangement; and |  | Yes | Met | This has been done. There were several exchanges of comments and revisions on the Phase 2 PSM Plan. The deficiencies were corrected and based on the revision; GF provided the approval for PSM Plan.
(ii) include assumptions on forecasting for ARVs and testing products in order to ensure alignment with the performance framework and work plan and budget, where appropriate; and |  | Yes | Met | PR has submitted forecasting for ARVs and testing products while submitting PSM Plan which is aligned with PF, workplan and budget
(b) The written approval of the Global Fund of the updated PSM plan |  | Yes | Met | The written approval of the GF of the updated PSM Plan was provided on 2 Feb 2011.
The Principal Recipient acknowledges and agrees that Ministry of Health will be responsible for the implementation of the Program |  | Yes | Met | The PCM members during its 14th PCM meeting endorsed that hereafter the Ministry of Health shall be the PR and are responsible for implementation of the program. The Phase 2 documents were also signed both by GNHC and MoH to reflect this arrangement
The Principal Recipient shall maintian, management capacity sufficient for program implementation through the term of Grant, based on the results of periodic assessment of the program by The Global Fund. Such management capacity will ensure adequate staffing including among other things, the position of (1) program officer, (2) M& E Coordinator, (3) Finance Officer/Accoutant (4) Project Manager |  | Yes | Met | The required staffs are in place. Currently, Mr Tandin Dorji is the overall Program Manager for TB and HIV program. Mr. Sonam Wangdi, Program Officer has left for his studies but Mr Namgay Tshering is appointed as the new Program Manager and Mr Leki Khandu as Assistant Program Manager. Mr Ugyen Tshewang is the Finance Officer and Mr Dinash Rai is working as an Accountant. There is one M & E officer (Mr Jigme Thinley) who will be looking after M & E component of all three diseases. Mr Tandin Dorji, Chief Program Officer of DVED is looking after PSM.
No later than 31 October 2010, the Principal Recipient shall deliver to the Global Fund, in form and substance satisfactory to the Global Fund, a detailed, quarterly budget for years 4 and 5, including detailed break downs per cost categories, Service Delivery Areas and per Sub-recipient, as well as assumptions explaining all lump sums. |  | Yes | Met | PR submitted the detailed quarterly budget for Year 4 and 5 including detailed breakdown per cost categories and summary budget to LFA on 17 October 2010. LFA verified the submission and was submitted to GF on 18 October 2010 and GF approved the Year 4 and 5 budget including detailed breakdown on 22 October 2010.
Following each procurement of health products the Principal Recipient shall update the informatin for key health products in the Global Fund's on-line Price and Quality Reporting (PQR) database, in accordance with Global Fund guidelines on Price and Quality Reporting. |  |  | Met | PR has issued purchase order for procurement of ARV drugs and expected to receive the drugs by mid-October through Year 3 budget. Therefore, no health products were received so far and thus there is no update on PQR database.
B. PR & LFA REVIEW OF PROGRESS ON IMPLEMENTATION OF OUTSTANDING MANAGEMENT ACTIONS FROM PREVIOUS DISBURSEMENTS
! This table should contain all issues raised in the last Management Letter from the Global Fund or outstanding from previous Management Letters, and comment on the progress.
Global Fund Management Actions |  | LFA Review of PR Progress on Global Fund Management Actions
The reporting templates have been developed for the SR's to reports on the activties. However, the SR's are not using the templates consistently. The report should be submitted on agreed reporting format. The focal persons from each SR should be trained to report using the new format |  | PR has revised the reporting template and has assured that the SRs will be retrained. This is expected to be conducted in the next quarter.
We noted that the coordination between PMT, NACP & SRs has improved and regular quarterly meeting is taking place. Nevertheless, the SRs continue to underperform and there is delay in submission of preogress reports |  | The PR has not undertaken more oversight activites and this is required for better performance by the SR's. As recommended previously the management of the SR's should come under the NACP rather than the PMT. In addition the NACP should be strengthened with M&E person to undertake supervision and oversight of the SR's.
During the reporting period one indicator “Number of people with advanced HIV infection currently receiving antiretroviral therapy” achieved only 69% of the target. We noted that the program has started using the new criteria for starting treatment as recommended by WI-IO which is to start ART with a CD4 count of 350. We have been informed that the treatment manual has been revised to incorporate this new recommendation and is now ready for printing. Officially the implementation of new treatment criteria has been initiated, but the awareness among the service providers and people living with HIV (PLWHIV) is not optimum. We would like to request NACP to initiate the awareness among the service providers and PLWHIV |  | Awareness for this new criteria for starting ART has been undertaken and it is excpected that more people will be put on ART in the coming quarters.
Targets In reference to the indicator ‘Number of teachers trained on life skill based HIV/AIDS education’ have been overachieved. We have been informed that the result was not correctly reported for this indicator. We would like to request NACP to segregate the training data and report with the Progress Update for the Quarter 15. In addition, we would also like to request to review the results for other training related indicators and conñrm the accuracy of the reported result. No disbursement for training will be made until the correct results are submitted. |  | The PR has chosen to report only on the teachers who attended the Training of Trainers (ToT) on life skills education. This is nor appropriate because the teachers who are trained as trainers are then expected to return to their school and conduct cascade training. The reported results are thus the total number of teachers who are trained in imparting LSE and this is correct. However the PR has included even teachers who teach grade 6 and below in the total and this is not in line with the PF where the target is to reach out to teachers who teach grade 7 and above. Excluding this group of teachers from the total will give more accurate results.
During the reporting period a high number for achievement has been reported for the indicator ‘Number of most at risk individuals reached with education materials (primarily substance users and sex workers)’. We would like to request your good office to share the information with the Global Fund on the mapping of MARP. |  | PR has shared with LFA on the study on Sexual Behaviours and Networks in Thimphu, Bhutan: A Rapid Assessment which is attached with this PU.
The analysis of cumulative variances from Q9 to Q14 shows that there is still a need for strengthening the ñnance management for this grant. There are instances, where expenditure overshoot budget and the NACP is not fully aware of this situation. In case the variances are known, they are not in a position to give proper explanations and justifications. The Global Fund provided training for finance personnel in 2010. We would like to request your good office to look into this and request the PMT for better coordination with finance and program units. |  | This issue is being taken care by PR
Surveillance strategy has not included armed forces personnel as one of the target groups although they are one of the high risk groups. We would like to encourage both NACP and PMT to initiate the discussion of inclusion of armed forces in the surveillance strategy. We would like to request your good to discuss this issue with armed forces. In addition, the technical partners (WHO, UNAIDS) can be also be consulted. |  | The Army has been included in the surveillance strategy
Reporting on most at risk individuals reached with education materials needs to be improved. Data is not segregated according to risk groups. All people who visit the HISC's are reported as most at risk individuals. We would recommend the program to strengthen the reporting system and segregate data accordingly. This would help the program to design an effective implementation |  | PR has started to report correctly on this indicator from this quarter.
Capacity of the PHPM needs to be strengthened. The Program unit (NACP) and the DVED should coordinate on regular basis for procurement. In this case PMT needs to be more proactive for an effective coordination. |  | MoH is in process of strengthening DVED as new people are being recruited to run the division
C. PR & LFA COMMENTS ON ANNUAL GRANT REPORTING REQUIREMENTS
This table should contain the due date for the report due for submission. If a report is overdue, indicate the original due date and explain the reason for delay.
| PR SECTION |  | LFA SECTION
Required Documentation | Due date | Status | Due date | Status | Comments
PR Audit Report | 2012-12-31 | Preparation on track | 2011-12-31 | Preparation on track | RAA is completed the auditing and report will be shared with PR. The 1 Feb 2010-31 Jan 2011 audit report was submitted on 26 March 2011.
Enhanced Financial Reporting (EFR) | 2012-01-31 | Preparation on track | 2011-03-15 | Submitted to GF | EFR for Period 1 Feb 2010-Jan 2011 was submitted to GF on 28 April 2011

## LFA_Total PR Cash Outflow_3A
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter |  | Number: | 19
Progress Update - Period Covered: | Beginning Date: | 2012-08-01 |  | End Date: | 2012-10-31
Progress Update - Number: | 19
Currency: | USD
Section 3A: Total PR Cash Outflow
LFA-VERIFIED TABLES ON TOTAL PR CASH OUTFLOW
! For RCC grants the cumulative section of the table below should contain cumulative amount from the start of the RCC and not from the start of Phase 1 of the program.
| LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance |  | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance | All amounts are in: | LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance
1. Total cash outflow vs. budget | 78545 | 115743.48 | -37198.48 |  |  | 2308713.07 | 2044349.48 | 264363.59 |  | 1. Total cash outflow vs. budget | 78545 | 8833 | 69712 |  | 2844101.07 | 2321650.11 | 522450.96
1a. PR's total expenditures | 78545 | 77400.13 | 1144.87 | The overall budget absorption rate achieved at Q15 end is 107% (USD 115,743.48) of the total corresponding budget of USD 108,107.00. Out of the total budget, the PR is allocated 86% of the budget amounting to USD 93,272.00. During this quarter, the PR implemented 53% (USD 49,088.00) of the total budget allocated either fully or partially, while 47% (USD 44,184.00) remains unimplemented at Q15 end. Analysis of unimplemented budget shows that Training budget (SDA 2.4.1) amounting to USD 7,389.00 was not implemented as the PR has postponed the activity for implementation in Q16. Further, procurement budget related to Test Kits Vacationers (SDA 1.8.3) amounting to USD 21,750.00 and budget for CD4 Reagents (SDA 1.8.4) amounting to USD 15,045.00 was not implemented in Q15. Analysis of expenditure reveals that out of the total expenditure of USD 77,400.13, 62% (USD 48,113.69) pertains to the implementation of current budget and another 24% (USD 18,699.23) is related to the implementation of back log activities while 14% (USD 10,578.40) has been incurred in implementation of budgets of Q17 and Q18 respectively. Detailed analysis of variance is shown in Annexure -C. |  | 1059651 | 983232.13 | 76418.87 | The overall cumulative burn rate achieved at Q15 end is 87% (USD 2,044,349.48) of the corresponding cumulative budget of USD 2,338,275.07 and the cumulative variance is 13% (USD 293,925.59). At Q15 end, the total cumulative budget provided for PR is 46% amounting to USD 1,074,378.00. Out of this, the PR implemented 92% (USD 983,231.99) and 8% (USD 91,146.01) remains unimplemented. The unimplemented budget pertains to Training under SDA 1.7.1 USD 12,117.84, SDA 2.2.2 USD 22,493.01 (Training budget provided for long term study in Epidimeology), and unimplemented procurement related budgets are SDA 1.8.3 USD 11,069.72, SDA 1.8.4 USD 13,735.20, SDA 3.1 USD 11,352.91 and M & E budget under SDA 2.2.1 amounting to USD 12,160.12 respectively. With respect to PR’s financial performance, the cumulative variance of 8% (USD 91,145.87) is not material in the opinion of the LFA. Detailed analysis of cumulative variances is shown in Annexure D. | 1a. PR's total expenditures | 78545 | 8833 | 69712 |  | 1360155 | 1125098.76 | 235056.24
1b. Disbursements to sub-recipients | 0 | 38343.35 | -38343.35 | The SR is allocated 14% (USD 14,835) of the total budget of USD 108,107 in Q15. Out of this, the PR disbursed 57% (USD 8,495.00) while 43% (USD 6,340.00) remains undisbursed at Q15 end. Analysis of disbursement shows that only 19% (USD 7,238.66) is related to Q15 budget while 81% (USD 31,104.69) pertains to the disbursement made related to back log activities. Detailed analysis is shown in Annexure -C. |  | 1249062.07 | 1061117.35 | 187944.72 | The cumulative budget allocated for SRs at Q15 end is 54% amounting to USD 1,263,897.07. Out of this, total disbursement amounted to 84% (USD 1,061,117.35) resulting cumulative variance of 13% (USD 202,779.72). Major variances occurred from not releasing training budgets provided for Department of Youth Services under SDA 1.1.1 USD 65,886.38, SDA 1.1.2 USD 27,522.00 and, budget for supply of equipment amounting to USD 21,517.62 is also remains unimplemented. Detailed analysis is of cumulative variances is given in Annexure D. | 1b. Disbursements to sub-recipients | 0 | 0 | 0 |  | 1483946.07 | 1196551.35 | 287394.72
| LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance |  | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance |  | LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance
2. Pharmaceuticals & health product expenditures vs. budget | 0 | 0 | 0 |  |  | 339919 | 177480.46 | 162438.54 |  | 2. Pharmaceuticals & health product expenditures vs. budget | 0 | 0 | 0 |  | 317474 | 169585.37 | 147888.63
2a. Medicines and pharmaceutical products | 0 | 0 | 0 | In Q15, the PR paid for procurement of ARVs (SDA 3.1) amounting to USD 15,425.70. |  | 89919 | 30567 | 59352 | Budget is not utilised in Phase II as the PSM plan was delayed in approving for purchase of Health products and equipments since PR took longer time to address the issues in PSM Plan | 2a. Medicines and pharmaceutical products | 0 | 0 | 0 |  | 66179 | 32352.7 | 33826.3
2b. Health products and health equipment | 0 | 0 | 0 | The PR did not implement budget in Q15. |  | 250000 | 146913.46 | 103086.54 | Budget is not utilised in Phase II as the PSM plan was delayed in approving for purchase of Health products and equipments since PR took longer time to address the issues in PSM Plan | 2b. Health products and health equipment | 0 | 0 | 0 |  | 251295 | 137232.67 | 114062.33
* If LFA-entered data differs from PR's figures, the respective cells will change colour automatically
3. Indicate any expenditures (incurred or forecasted) that should not be financed by the Global Fund
LFA verification of expenditures reported in Q15 revealed that all expenditures incurred and reported are in line with GFATM approved budget.

## LFA_EFR Review_3B
LFA review of Enhanced Financial Reporting template
LFA Organization / Responsible office: |  |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | Ministry of Health
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
Section 3B: ENHANCED FINANCIAL REPORTING PERIOD
Current Period |  |  | Beginning Date: | End Date:
Cumulative Period |  |  | Beginning Date: | End Date:
1. CHECKLIST
The following information provided by the Principal Recipient in its EFR has been checked. |  |  |  |  | Comments if any:
| Select | The template has been fully completed.
1
| Select | The total figures in Tables A, B and C are equal.
2
| Select | The reporting dates are correct for both current period and cumulative period.
3
| Select | The total budget figure is accurate based on existing approved budgets.
4
| Select | The PR expenditure in Table C is consistent with PR expenditure for the same period as provided in the Progress Updates/Disbursements Request (PU/DR).
5
| Select | The total expenditure is supported by appropriate documentation ( PR expenditure reports, bank reconciliations, SR expenditure reports to PR etc.) or reasonable assumptions.
6
2. COMPLETION OF THE TEMPLATE
Comments on the process, assumptions and supporting documentation used by the PR to complete the template. (If space is insufficient, please provide comments in an addendum)
3. VARIANCE ANALYSIS
Comments on the explanations for variances provided by the PR (LFA can also provide comment directly on the EFR template completed by the PR)
Signed on behalf of the LFA:
Name:
Title:
Date and Place:

## LFA_Procurement Info_4
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter |  | Number: |  | 19
Progress Update - Period Covered: | Beginning Date: | 2012-08-01 |  | End Date: |  | 2012-10-31
Progress Update - Number: | 19
Section 4: LFA-verified Procurement and Supply Management Information
| PR's response | LFA's response | LFA Comments/Analysis
1a. Has the PR updated the Price Quality Reporting (PQR) with the required information on the pharmaceuticals and health products received during the period covered by this PU/DR’ (if applicable)? (If health products procurement information has not been entered into the PQR, please explain why in comments box) | No | No | PR has procured ARV drugs but has not been updated in the PQR and LFA is unable to compare the prices
1b. Value of Pharmaceuticals and Health Products in the PQR (6 categories only)
(!) This table is included in the PU/DR form with the aim to improve completeness of information in the PQR system and not for comparing PQR amounts vis-à-vis expenditure per se. NB: PQR and expenditure amounts on health products may not be equal due to a timelag between payments and delivery of pharmaceuticals/health products. (!) For further guidance on PQR data entry, please refer to the guidelines.
Reporting Currency
PQR Product Categories | Value of products received during reporting period | Value of products entered by the PR and verified as correct by the LFA in the PQR during reporting period | Variance | Reason for Variance | Cumulative value of products received since Jan 2011 | Cumulative value of products verified as correct by the LFA in the PQR since Jan 2011 | Variance | Reason for Variance
1. Anti-malaria medicines
2. Bed nets
3. Rapid Diagnostic Tests
4. Condoms
5. Anti-retrovirals
6. Anti-TB Medicines
Total | 0 | 0 | 0 |  | 0 | 0 | 0
2. Based on best information available to the LFA, are there any risks of drug stockout at the central level in the next period of implementation? (If yes, please explain in comments box) ! This section should be completed by the LFA based on best information on stock levels at the central level available to the LFA and should not require dedicated visits for on-site checks of stocks. | No | N/A | PR has informed that enough drugs has been procured. However, LFA is not in position to verify since PR has not updated the PQR.
3. PR comments on issues related to the procurement and supply management of pharmaceuticals and health products |  |  |  | LFA analysis on issues related to the procurement and supply management of pharmaceuticals and health products
As indicated by PR, the capacity of DVED is weak and there had been delay in procuring most of the drugs but essential drugs such as ARV drugs will not get out-of -stock since they had procured enough. The PSM plan for all three grants was delayed in getting approval from GF due to weak capacity of the DVED. There is need to strengthen the capacity of DVED.

## LFA_Findings&Recommendations
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | BTN-607-G03-H
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: | 19
LFA-specific section: LFA Findings & Recommendations
! Based on the information provided in the previous sections and your understanding of the grant, please summarise any important management issues, proposing a recommendation for each. NB: an issue is considered as 'important' if it impacts or is likely to impact program implementation and results. ! Instead of repeating detailed descriptions of issues covered in other sections, it is acceptable to state the issue and reference the section containing the details.
Functional Areas | Description of Identified Issues (in order of importance) |  |  | LFA Recommendations (in order of importance) | FPM Comments (to be completed upon receipt of the LFA-verified form)
Program management (including SR management) | number of people reached in out of school setting must be conducted more activiely by SR |  |  | SR should actively reach out of school people with HIV education especially by the Ministry of Labour and Human Resources. Trainees in the vocational training institutes and job seekers coming to the Ministry seeking employement should be reached and reported. Time: Q16
Program management (including SR management) | Number of monks and nuns reached with HIV awareness must be accelerated |  |  | SR should ensure that this activity is conducted and the targets are reached. Since this activity can be conducted in the monasteries, the PR should ensure that SR carries out this acitivyt in time and that it is reported in a timely manner. There must be better oversight by the PR on SR management. Timeline: Q16
Select
LFA_Findings & Recommendations
Select
Yes
No
Select
Program management (including SR management)
Financial management and systems
Monitoring and evaluation
Pharmaceutical & health product management
Other management issues, including: PR capacity to develop quality programmatic and financial reports

## LFA_Cash Reconciliation_5A
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 1
Disbursement Request - Period Covered: |  | Beginning Date: | 2013-02-01 | End Date: | 2014-01-31
Disbursement Request - Number: |  | 1st under TFM
Section 5: LFA-verified Cash Reconciliation & Disbursement Recommendation
A. LFA-VERIFIED CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
|  |  |  | PR-reported amounts | LFA-verified amounts | LFA Comments on verified amounts (if they are different from those reported by the PR) and PR's explanation of reconciliation adjustments (line 9)
1. Cash Balance: Beginning of period covered by Progress Update (line 10 from Cash Reconciliation section of the period covered by the previous Progress Update): |  |  |  | 6738.12 | 130297 | The opening cash balance has been verified with reference to the closing cash balance reported in Q14 PUDR.
Add: |  |  |  | 0 | 0
2. Cash received by the PR from the Global Fund during the period covered by this progress update: (1)
| 3. Cash disbursed to third parties by the Global Fund on behalf of the PR during the period covered by this progress update: (1) |  |  | 0 | 0
| 4. Interest received on bank account |  |  | 0 | 0
| 5. Revenue from income-generating activities (if applicable) |  |  | 0 | 0
| 6. Other income, if applicable (e.g. income from disposal of fixed assets, tax refunds) |  |  | 0 | 0
Less: | 7. Total PR cash outflow during period covered by Progress Update (value entered in Section 3A "Total cash outflow"): |  |  | 8833 | 115743 | The expenditures incurred in Q15 has been verified against payment vouchers which are reocrded in PR's cash book and also verified with reference to monthly trial balances prepared by the PR.
| 8. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign) |  |  | 0 | 0
| 9. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) |  |  | 0 | 0
10. Cash Balance: End of period covered by Progress Update: |  |  |  | -2094.88 | 14554 | Cash balance is correctly reflected as shown in the Cash Flow Statement. The LFA verified this balance with reference to PR's cash book and the bank reconciliation statement.

## Annexure_B_Cashflow
Cash Flow Statement | ANNEXURE B: SOURCES AND APPLICATION OF FUND (Q15_ASO_2011)
| Details | Ex. Rate | Nu | USD
Cash Inflow (Sources of Fund)
| Opening Balance at DPA | 45.37 | 5785803.16 | 127524.8658
| Opening Bank MOH | 45.37 | 125382.2 | 2772.3686
| Total Inflow - A |  | 5911185.36 | 130297.2344
Cash Outflow (Application of Fund)
| Actual expenditure for the period (PR) | 45.37 | 3511243.94 | 77400.1345
| Actual expenditure for the period (SR) | 45.37 | 1739638 | 38343.3546
| Total Outflow - B |  | 5250881.94 | 115743.4892
| Balance (A-B) |  | 660303.42 | 14553.7452
Represented by:
| Bank Balance of PR | 45.37 | 660303.26 | 14553.75
| Total Fund available at the end of reporting period |  | 660303.26 | 14553.75

## LFA_Disbursement Recommend_5B
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: |  | BTN-607-G03-H
Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 1
Disbursement Request - Period Covered: |  | Beginning Date: | 2013-02-01 | End Date: | 2014-01-31
Disbursement Request - Number: |  | 1st under TFM
Currency: |  | USD
Section 5: LFA-verified Cash Reconciliation & Disbursement Recommendation
B. LFA-RECOMMENDED DISBURSEMENT AMOUNT AND EXPLANATIONS
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update:
1. Period beginning date: |  | 2013-02-01 | end date: | 2014-01-31 |  | Approved budget amount (reported by PR): |  | 333177.17 | Forecasted amount (reported by PR): | 333177.17
[6 empty] | LFA-verified approved budget amount: |  | 0 | LFA-adjusted forecasted amount: | 0
2a. Cash buffer period (by default)
(cash "buffer") beginning date: |  | 2014-02-01 | end date: | 2014-04-30 |  | Approved budget amount (reported by PR): |  | 0 | Forecasted amount (reported by PR): | 0
PR Total Forecast
[6 empty] | LFA-verified approved budget amount: |  | 0 | LFA-adjusted forecasted amount: | 0 | 333177.17
2b. Additional "buffer" (discretionary, select only if there is a prior agreement with the FPM) (1) | [10 empty] | LFA Total Forecast
0
(cash "buffer") beginning date |  | 2014-05-01 | end date: |  |  | approved budget amount: |  | 0 | forecasted amount: | 0
[6 empty] | LFA-verified approved budget amount: |  | 0 | LFA-adjusted forecasted amount: | 0
(1) Upon agreement with the FPM, additional Cash buffer can be requested if the PU/DR report contains a completed EFR report or a completed Annex on SR financials, requested by the Secretariat, or if there are any additional GF-specific requirements that cannot be delivered within 45 days. However such requests may or may not be satisfied based on the review of the current PUDR
(2) When the additional (cash "buffer" ) period is 1 or 2months, the approved budget and forecasted amounts should be calculated as prorated values for the period following the regular buffer period.
PR's explanation of any significant variance between forecasted amounts and amounts as originally budgeted.
LFA's explanation of any significant variance between forecasted amounts and amounts as originally budgeted. Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. NB. Consider the following items when providing the analysis. - Expected timing of payments for any significant budgetary items, - Impact of existing cash balance at SR levels - Current confirmed commitments to be paid during disbursement request period - Current/expected unit prices compared to those in the budget - Change in quantities compared to budget - Exchange rates and inflation - Linkage between budget absorption and programmatic performance to-date. ! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the disbursement period
Less: | 3. Cash Balance: End of period covered by Progress Update (number 10 from LFA or PR Cash Reconciliation sheet): |  |  |  | PR-reported amounts | LFA-verified amounts | LFA Comments
[5 empty] | -2094.88 | 14554 | Cash balance is correctly reflected as shown in the Cash Flow Statement. The LFA verified this balance with reference to the PR's cash book and bank reconciliation statement.
| 4. Cash "in transit" disbursed to the PR: |  |  |  | 0 | 0
| 5. Cash "in transit" disbursed to third parties by the Global Fund on behalf of the PR : |  |  |  | 0 | 0
[5 empty] | PR-requested amount | LFA-recommended amount
6. Disbursement Request to the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): |  |  |  |  | 335272.05 | 0
7. Does the PR's Disbursement Request include funds for health product procurement? |  |  |  |  | Select
8. Exchange Rate (used to translate local currency into grant currency)
|  | Rates used by the PR | LFA-verified rates |  | Name of local currency and LFA comments on the exchange rates used by the PR
| - used to convert Opening Cash Balance | 45.7 | 45.37 |  | Local currency is called NGULTRUM, in short Nu. Exchange rate is determined by the Royal Monetary Authority of Bhutan (RMA) on the date when GF disbursement hits RMA account. The RMA transfers an equivalent local currency into the Royal Government Budget Fund Account.
| - used to convert Closing Cash Balance | 45.7 | 45.37
| - used to convert Total PR Cash Outflow for the Progress Update Period | 45.7 | 45.37

## LFA_Overall Performance_6
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | BTN-607-G03-H
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 19
Progress Update - Period Covered: |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31
Progress Update - Number: |  | 19
Section 6: LFA EVALUATION AND COMMENTS ON OVERALL PERFORMANCE
A. Overall Evaluation and Rating of Grant Performance (including a summary of how financial performance is linked to programmatic achievements)
! The evaluation should be undertaken by taking into account programmatic achievements, financial performance and program issues in various functional areas (M&E, Finance, Procurement, and Program Management, including management of sub-recipients). See Guidelines for more detailed guidance on the completion of this section. ! For RCC grants, this section should cover the period from the RCC start date through the end date of the current Progress Update period. ! For guidance on the methodology for rating overall performance, refer to Annex 2 of Guidelines.
Indicator rating | B1 |  | Any major management issues resulting in downgrade? | Select |  | Overall Grant Rating | B1
Program achievement: The average percentage achievement for the seven top ten indicators is 93% which is A2 rating but two TOP indicators are in B1 (indicator 1.1 is 74 % and indicator 1.9 is 86%). The average for all the indicators is 93 percent which is A2 rating. Out of seven top indicators for this quarter, the achievement for four indicators is above 100 percent and none are below 70 percent. Only two Indicators are in B2 rating. The final Quantitative rating is B1 (see annexure A). Financial Achievement: The overall budget absorption rate of Q15 end is 107 % (USD 115,743.48) of the corresponding budget of USD 108,107.00. Out of the total budget, the PR is allocated 86% of the budget amounting to USD 93,272.00. PR implemented 53% (USD 49,088.00) of the total budget allocated either fully or partially, while 47% (USD 44,184.00) remains unimplemented at Q15 end.The budget implemented (partially or fully) in Q15 amounts to 60% (USD 147,455) and 40 % (USD 97,117.00) of the Q15 budget remains un-implemented. Analysis of expenditure reveals that out of the total expenditure of USD 77,400.13, 62% (USD 48,113.69) pertains to the implementation of current budget and another 24% (USD 18,699.23) is related to the implementation of back log activities while 14% (USD 10,578.40) has been incurred in implementation of budgets of Q17 and Q18 respectively. Detailed analysis of variance is shown in Annexure -C.With such a burnt-rate, the financial achievement in this quarter is rated "A1". Overall Rating: Based on the program and financial performance, LFA provided a rating of "B1" for this quarter.
B. LFA comments on PR planned changes in the program, if any
LFA do not see any major plan changes except DYS has reprogram the training of school teachers during the winter holiday (Dec-Jan) so that teachers are not disturbed during the academic session.
C. LFA Comments on External Factors Beyond Control of the Principal Recipients that have impacted or may impact program
As indicated in Q14, due to 18 September 2011 earthquake with magnitude of 6.9, there had been major damages to houses, cultural monuments, roads and public infrastructures (Health centers, schools etc) in the country. Thus, LFA foresees that all public servants will be engaged in rebuilding these infrastructures and may hamper the implementation of the program in certain areas especially in hard-hit districts in western Bhutan.

## LFA_DisbursementRecommendation7
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office: |  |  | UNOPS/LFA-BHUTAN
GENERAL GRANT INFORMATION
Country: |  |  | Bhutan
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | BTN-607-G03-H
Principal Recipient: |  |  | Ministry of Health
Program Start Date: |  |  | 2008-02-01
Currency: |  |  | USD
PROGRESS UPDATE PERIOD | [7 empty] | DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 19 |  | Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 1
Progress Update - Period Covered: |  |  | Beginning Date: | 2012-08-01 | End Date: | 2012-10-31 |  | Disbursement Request - Period Covered: |  | Beginning Date: | 2013-02-01 | End Date: | 2014-01-31
Progress Update - Number: |  |  | 19 |  |  |  |  | Disbursement Request - Number: |  | 1st under TFM
Section 7: Disbursement Recommendation
A. DISBURSEMENT RECOMMENDATION
| Overall Rating | B1
Indicative disbursement ranges by performance rating (included as a reference)
Performance rating |  |  | Range for cumulative disbursement amount (after the currently recommended disbursement)
A1 | Exceeding expectations |  | Above 95% of cumulative budget through the next reporting period
A2 | Meeting expectations |  | Between 85-105% of cumulative budget through the next reporting period
B1 | Adequate |  | Between 55-95% of cumulative budget through the next reporting period
B2 | Inadequate but potential demonstrated |  | Between 25-65% of cumulative budget through the next reporting period
C | Unacceptable |  | Below 35% of cumulative budget through the next reporting period
1. Cash amount requested by the Principal Recipient from the Global Fund for next disbursement period plus one additional quarter (amount in: USD): | [6 empty] | 335272.05 |  | 0
2. LFA disbursement recommendation (amount in: USD): | [6 empty] | 0 |  | N/A
State the amount in words
Cumulative budget through the next period of implementation (including the buffer) |  |  | Cumulative disbursed amount to date (*) |  | Cumulative disbursed after recommended disbursement (including the buffer) |  | % range |  | Is the recommended disbursement within the range?
| 2308713.07 |  |  |  | 0 |  | 0% |  | Select
(*)This data can be obtained from the "Disbursements in detail report (PDF)" (http://www.theglobalfund.org/documents/disbursementdetails.pdf)
3. Rationale for the LFA's disbursement recommendation (if resulting in cumulative disbursement outside the indicative ranges):
B. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [8 empty] | Comments regarding verifications, if any:
| Yes | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request | [6 empty] | Verified and found to be correct
| Yes | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable). | [6 empty] | All CPs for this disbursement has been met
| Yes | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement). | [6 empty] | Verified and found to be correct
| Yes | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress. | [6 empty] | Verified and found to be correct
| Yes | Exchange rate stated by Principal Recipient has been verified and is correct. | [6 empty] | The exchange rates are: First disbursement= 1 USD= BTN 39.25; Second disbursement =1 USD = BTN 47.841; third disbursement 1 USD= BTN 46.04; Fourth Disbursement 1 USD= BTN 46.74; Fifth disbursement 1 USD=BTN.45.37; sixth disbursement 1 USD =BTN 52.09
| Yes | PR Bank details verified/corrected by LFA | [6 empty] | Correct
| Select | Current budget forecasts of the Principal Recipient for the next disbursement period plus buffer period have been reviewed for reasonableness | [6 empty] | There is no budget forecast in Q15.
| Yes | LFA has debriefed the Principal Recipient on the key findings (comment on the format of this debriefing) | [6 empty] | LFA met with Chief Program Officer, PMT, Program Officers of GNHC and NACP and Accountant and discuss on key findings included in this report.
NB: Please ensure that section 7C Bank Details on the following page is completed if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.
D. Summary of the LFA's approach used for verification of financial, programmatic and procurement data and Quality Assurance undertaken by the LFA
In this section the LFA should indicate, as applicable, what percentage of expenditures was verified at PR level, if any expenditures were verified at SR level, how many site visits were made, what tender documentation was verified, and any other material parts of verification procedures in line with the verification approach agreed upfront between the LFA and GF Secretariat based on country/grant risks. As a good practice, the verification approach needs to be reviewed jointly by the LFA and the Secretariat annually.
LFA carried out vouching exercise with random selection of payment vouchers for the month of October 2011. The expenditure incurred in October 2011 amounted to USD 71,277 accounting to 62 percent of the total expenditure in Q15 (USD 115,743.48). The objective of vouching exercise has been to check the accuracy and genuineness of all recorded transactions, check all recorded transactions are properly authorized and supported with bills and money recipts, and all expenditures have been incurred in line with GFATM approved budget line. In opinion of LFA, all expenditures are supported by documentary evidences and are in line with GFATM approved work plan and budget.
NB: The LFA should sign a printed version of the verified PU/DR and send it to the Secretariat as a pdf file by email, or include an electronic signature in the Excel file to be submitted to the Global Fund.
Signed on behalf of the LFA:
Name: |  |  | Yeshey Dorji
Title: |  |  | Team Leader
Date and Place: |  |  | 15 Jan 2012, Thimphu-BHUTAN

## LFA_Bank Details_7C
LFA On-going Progress Review and Disbursement Recommendation
Note for LFAs: This page should be completed by the PR if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement. The amounts and bank details below are displayed as entered by the PR. If any of this information is incorrect, please correct them by overwriting with correct information.
7C: LFA-verified Bank Account Details
| Disbursement Request Period | 0
| Summary |  |  |  |  | Summary
|  | Beneficiary Name | Amount in grant currency |  |  |  | Beneficiary Name | Amount in grant currency
| Payee 1 - Principal Recipient: | Ministry of Health |  |  |  | Payee 1 - Principal Recipient: | Ministry of Health
| Payee 2: |  |  |  |  | Payee 2:
| Payee 3: |  |  |  |  | Payee 3:
| Payee 4: |  |  |  |  | Payee 4:
| Total |  | 0 | The total does not match requested amount on PR signature page |  | Total |  | 0
| Payee 1: |  |  |  |  | Payee 1:
| Beneficiary Name: | Ministry of Health |  | Owner of Bank Account: | Royal Government of Bhutan | Beneficiary Name: | Ministry of Health |  | Owner of Bank Account: | Royal Government of Bhutan
| Currency in which beneficiary should receive the funds | USD |  | Owner of Bank Account: | Federal Reserve Bank of New York | Currency in which beneficiary should receive the funds | USD |  | Owner of Bank Account: | Federal Reserve Bank of New York
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | 2108337 | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | 2108337
| Amount in Words: |  |  | Bank Address | 33 Liberty Street , NY 1004 ,USA | Amount in Words: |  |  | Bank Address | 33 Liberty Street , NY 1004 ,USA
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | FRNYUS33 | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | FRNYUS33
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): |  | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  |  | Routing Instructions:
| Payee 2: |  |  |  |  | Payee 2:
| Beneficiary Name: |  |  | Owner of Bank Account: |  | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: |  | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: |  | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address |  | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: |  | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): |  | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  |  | Routing Instructions:
| Payee 3: |  |  |  |  | Payee 3:
| Beneficiary Name: |  |  | Owner of Bank Account: |  | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: |  | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: |  | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address |  | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: |  | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): |  | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  |  | Routing Instructions:
| Payee 4: |  |  |  |  | Payee 4:
| Beneficiary Name: |  |  | Owner of Bank Account: |  | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: |  | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: |  | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address |  | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: |  | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): |  | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  |  | Routing Instructions:

## LFA_Annex-SR Financials
LFA On-going Progress Review and Disbursement Recommendation
Annex to PU/DR - LFA-reviewed Sub-recipient financial information ! Completion of this table by the PR and verification by the LFA are discretionary, and should be done upon the Secretariat's request.
Grant number: |  |  |  | BTN-607-G03-H
Progress Update - Reporting Period: |  |  |  | Cycle: | Quarter |  | Number: | 19
Progress Update - Period Covered: |  |  |  | Beginning Date: | 2012-08-01 |  | End Date: | 2012-10-31
Progress Update - Number: |  |  |  | 19
Currency: |  |  |  | USD
Note for LFAs: The information below is displayed as entered by the PR. If any of this information is incorrect, please correct them by overwriting with correct information.
Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR | Budget for Reporting Period* | Disbursed during Reporting Period* |  | Cumulative Budget through period of Progress Update* | Cumulative Disbursed through period of Progress Update* | Cumulative Actual Expenditure through period covered by this Progress Update | Cash balance at the end of the period covered by this Progress Update | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (1) between cumulative budget and cumulative expenditure and (2) between cumulative disbursement and cumulative expenditure (mandatory for amounts above $50,000 or equivalent and with more than 10% variance) | LFA Comments on the PR's overall verification efforts of SR expenditure and the explanations of variance provided | Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR | Budget for Reporting Period* | Disbursed during Reporting Period* | Cumulative Budget through period of Progress Update* | Cumulative Disbursed through period of Progress Update* | Latest Cumulative Actual Expenditure (as per most recent SR reports available at PR level) | End date of period covered in most recent SR report | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (mandatory for amounts above $50,000 and with more than 10% variance)
Department of Youth & Sports, MoE | 0 |  | 0 |  |  | 318609 | 0 | 225097.78 |  | 93511.22 | 0 |  | The PR has not provided any analysis of SR expenditure and also explanations of variances. | Department of Youth & Sports, MoE | 0 |  | 0 |  | 318609 | 0 | 225097.78 |  | 93511.22
Department of Adult & Higher Learning, MoE | 0 |  | 0 | 0 |  | 303430 | 0 | 218135.01 |  | 85294.99 | 0 |  | The PR has not provided any analysis of SR expenditure and also explanations of variances. | Department of Adult & Higher Learning, MoE | 0 |  | 0 | 0 | 303430 | 0 | 218135.01 |  | 85294.99
Ministry of Labour & Human Resource | 0 |  | 0 | 0 |  | 35465 | 0 | 37040.91 |  | -1575.91 | 0 |  | The PR has not provided any analysis of SR expenditure and also explanations of variances. | Ministry of Labour & Human Resource | 0 |  | 0 | 0 | 35465 | 0 | 37040.91 |  | -1575.91
Bhutan Chamber of Commerce & Industries | 0 |  |  | 0 |  | 97975 | 0 | 78440.98 |  | 19534.02 | 0 |  | The PR has not provided any analysis of SR expenditure and also explanations of variances. | Bhutan Chamber of Commerce & Industries | 0 |  |  | 0 | 97975 | 0 | 78440.98 |  | 19534.02
Armed Forces | 0 |  |  |  |  | 140815 | 0 | 85801.71 |  | 55013.29 | 0 |  | The PR has not provided any analysis of SR expenditure and also explanations of variances. | Armed Forces | 0 |  |  |  | 140815 | 0 | 85801.71 |  | 55013.29
Dratshang Lhengtshog | 0 |  |  |  |  | 66945 | 0 | 58142.86 |  | 8802.14 | 0 |  | The PR has not provided any analysis of SR expenditure and also explanations of variances. | Dratshang Lhengtshog | 0 |  |  |  | 66945 | 0 | 58142.86 |  | 8802.14
Royal Institute of Health Sciences | 0 |  | 0 | 0 |  | 61250 | 0 | 51109.6 |  | 10140.4 | 0 |  | The PR has not provided any analysis of SR expenditure and also explanations of variances. | Royal Institute of Health Sciences | 0 |  | 0 | 0 | 61250 | 0 | 51109.6 |  | 10140.4
TOTAL |  |  | 0 | 0 |  | 1024489 | 0 | 753768.85 |  | 270720.15 |  |  |  | TOTAL |  |  | 0 | 0 | 1024489 | 0 | 753768.85 |  | 270720.15
*TOTAL amount for these columns should reconcile with relevant amounts under "1b Disbursed to Sub Recipients" in Section 3A"
** Where the number of SRs is significant (over 10), SRs with small budgets (less than $50,000 or EUR equivalent cumulative each) do not need to be reported separately and the figures can be aggregated in a group called "Other Minor SRs"

## Annexure_D_CuuVAR
Annexure D: Analysis of Cumulative Variances by Line Items from Q9-Q15
SDA | Objectives / Service Delivery Areas (SDAs) |  | FMA (Q9) |  |  | MJJ (Q10) |  |  | ASO (Q11) |  |  | NDJ (Q12) |  |  | FMA (Q13) |  |  | MJJ (Q14) |  |  | ASO (Q15) |  |  | Analysis of Cu variance up to Q15 end
|  | PR/SR | BUDGET | EXP. | Variance | BUDGET | EXP. | Variance | BUDGET | EXP. | Variance | BUDGET | EXP. | Variance | Budget | EXP. | Variance | Budget | Expenditure | Variance | Budget | Expenditure | Variance | CU. Budget | CU. Exp. | Cu. Variance | % Variance | LFA Comments
1.1.1 | TOT on Life Skill Education in 3 regions (Western, Central,Southern ) - 5 days training program each for region | DYS | 10085 | 3806.69 | 6278.31 |  |  | 0 | 10085 |  | 10085 | 10085 | 30254.0009 | -20169.0009 | 69692.07 |  | 69692.07 |  |  | 0 | 0 | 0 | 0 | 99947.07 | 34060.6909 | 65886.3791 | 65.92% | The SR, Deaprtment of Youth Services has postponed this activity to be implemented in Q16.
| i. PA wirless meeting amplifier to be sent to schools | DYS | [15 empty] | 28160 | 0 | 28160 | 0 | 6642.3848 | -6642.3848 | 28160 | 6642.3848 | 21517.6152 | 76.41% | Procurement of Audio visual equipment has been delayed by DYS SR) in Q14. However, it is now reprogrammed for implementation in Q16.
| ii. Audio visual materials on HIV/AIDs for Schools | DYS | [15 empty] | 2800 | 0 | 2800 | 0 | 0 | 0 | 2800 | 0 | 2800 | 100%
| iii. TV for schools | DYS | [15 empty] | 13500 | 0 | 13500 | 0 | 13500 | -13500 | 13500 | 13500 | 0 | 0%
| iv. DVD player for school | DYS | [15 empty] | 3000 | 0 | 3000 | 0 | 3000 | -3000 | 3000 | 3000 | 0 | 0%
| v. Digital camera for CSHP | DYS | [15 empty] | 450 | 0 | 450 | 0 | 0 | 0 | 450 | 0 | 450 | 100%
1.1.2 | Support to TOT in the implementation of further training of teachers in their communities/districts (5-day training). | DYS |  |  | 0 | 21495 |  | 21495 | 21495 |  | 21495 |  | 42988.8746 | -42988.8746 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 42990 | 42988.8746 | 1.1254 | 0.002618% | The variance is immaterial
| Support to ToT in the implementation of further training of teachers in their communities/districts | DYS | [15 empty] | 27522 |  | 27522 | 0 | 0 | 0 | 27522 | 0 | 27522 | 100% | This activity has been deferred to Q16 coinciding with the winter vacation as per the policy of the ministry of education
| Attend regional GFATM meetings | DYS | [15 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Training of Focal person in Project management | DYS | [15 empty] | 4950 | 4948.2 | 1.8 | 0 | 0 | 0 | 4950 | 4948.2 | 1.8 | 0.03636%
1.1.3 | Purchase of Television & DVD for the schools. - 30 sets required | DYS | 12000 |  | 12000 |  | 3627.28 | -3627.28 |  |  | 0 |  | 12000 | -12000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 12000 | 15627.28 | -3627.28 | -30.23% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.1.4 | Purchase of sound syetem (Ahuja) | DYS | 5850 |  | 5850 |  |  | 0 |  |  | 0 |  | 5850 | -5850 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 5850 | 5850 | 0 | 0%
1.1.5 | Purchase of LCD Projector with desktop computer | DYS | 4500 |  | 4500 |  |  | 0 |  |  | 0 |  | 4500 | -4500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 4500 | 4500 | 0 | 0%
1.1.6 | Sound proofing of the Auditorium | DYS | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1.1.7 | Purchase of wall mounted projector scerr 119" | DYS | 450 |  | 450 |  |  | 0 |  |  | 0 |  | 450 | -450 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 450 | 450 | 0 | 0%
1.1.8 | Purchase of Plasma TV | DYS | 3150 |  | 3150 |  |  | 0 |  |  | 0 |  | 3150 | -3150 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3150 | 3150 | 0 | 0%
1.1.9 | Attend regional GFATM meetings | DYS | 2250 |  | 2250 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2076.97 | -2076.97 |  |  | 0 | 0 | 0 | 0 | 2250 | 2076.97 | 173.03 | 7.69% | The variance is immaterial
1.1.10 | Monitoring and evaluation | DYS |  | 11500 | -11500 | 860 |  | 860 |  |  | 0 | 860 |  | 860 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 1720 | 11500 | -9780 | -568.6% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
SDA 1.2: Providing life-skills-based HIV/AIDS education | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1.2.1 | Development & Printing of educational materials(TLM- teaching learning materials) | NFE | 5000 |  | 5000 |  |  | 0 |  | 5003.24 | -5003.24 |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 5000 | 5003.24 | -3.24 | -0.0648% | The variance is immaterial
1.2.2 | Training of Teachers/Principals | NFE | 18580 |  | 18580 | 18580 |  | 18580 |  | 37159.99 | -37159.99 |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 37160 | 37159.99 | 0.01 | 2.691e-05% | The variance is immaterial
1.2.3 | Training employees of MOLHR | [16 empty] | 4255 | 4253.91 | 1.09 | 0 | 0 | 0 | 4255 | 4253.91 | 1.09 | 0.02562%
1.2.3 | Community activities by youth NFE learners | NFE |  | 2048.54 | -2048.54 |  |  | 0 |  | 68800 | -68800 | 68800 | 0 | 68800 | [5 empty] | 0 | 0 | 0 | 0 | 68800 | 70848.54 | -2048.54 | -2.978% | The variance is immaterial
1.2.4 | Attend regional GFATM meetings | NFE | 2250 |  | 2250 |  |  | 0 |  |  | 0 |  | 2250 | -2250 | [5 empty] | 0 | 0 | 0 | 0 | 2250 | 2250 | 0 | 0% | GFATM meeting not yet attended
1.2.5 | Refresher ToT for Vocational Centre teachers | NFE | 5660 |  | 5660 |  |  | 0 |  | 5659.99 | -5659.99 |  | 0 | 0 |  |  |  | 66978 | 66977.96 | 0.04 | 0 | 0 | 0 | 72638 | 72637.95 | 0.05 | 6.883e-05% | The variance is im-material
1.2.6 | Sensitization of unemployed youths and job seekers during the job fairs and NGOP | NFE |  |  | 0 |  |  | 0 | 6960 | 6956.69 | 3.31 |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 6960 | 6956.69 | 3.31 | 0.04756% | The variance is im-material
1.2.7 | Attend regional GFATM meetings | NFE | 2250 |  | 2250 |  |  | 0 |  |  | 0 |  | 2250 | -2250 | [5 empty] | 0 | 0 | 0 | 0 | 2250 | 2250 | 0 | 0% | GFATM meeting not yet attended
1.2.8 | M & E | NFE |  | 8598.33 | -8598.33 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 8598.33 | -8598.33 | 0% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
SDA 1.3: Reaching youth through the private sector |  |  |  |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1.3.1 | Sensitization of private sectors in 5 towns | BCCI |  | 4535.19 | -4535.19 | 3450 | 345.81 | 3104.19 |  |  | 0 |  | 3450 | -3450 | 1500 |  | 1500 | 4790 |  | 4790 | 0 | 0 | 0 | 9740 | 8331 | 1409 | 14.47% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.3.2 | Printing of education materials and products | BCCI | 5000 |  | 5000 |  |  | 0 |  | 3438.94 | -3438.94 |  | 0 | 0 |  |  | 0 | 5000 | 1139.98 | 3860.02 | 0 | 0 | 0 | 10000 | 4578.92 | 5421.08 | 54.21% | Activity is on-going
1.3.3 | Ex-country training for the focal person on HIV programming | BCCI | 3610 |  | 3610 |  |  | 0 |  | 3487.38 | -3487.38 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3610 | 3487.38 | 122.62 | 3.397% | The variance not material
1.3.4 | Ex-change of experience among private sectors | BCCI |  | 7993.05 | -7993.05 | 2225 |  | 2225 |  |  | 0 |  | 2225 | -2225 | 6340 |  | 6340 |  |  | 0 | 0 | 0 | 0 | 8565 | 10218.05 | -1653.05 | -19.3% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
| Quarterly Exchange of experience | [19 empty] | 6340 | 0 | 6340 | 6340 | 0 | 6340
SDA 1.4: Establishing youth-friendly health services in 30 hospitals | [19 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
1.4.1 | Training/refresher of staff about youth-issues | NACP |  | 153.56 | -153.56 |  | 144.77 | -144.77 | 6780 | 5283.74 | 1496.26 |  | 1824.4223 | -1824.4223 |  |  |  | 7389 | 7493.94 | -104.94 | 7389 | 0 | 7389 | 21558 | 14900.4323 | 6657.5677 | 30.88% | The balance activities are planned to be implementedin Q16.
1.4.2 | Telephone line charges | NACP | 474 | 1247.73 | -773.73 | 474 | 1554.76 | -1080.76 | 474 | 966.04 | -492.04 | 474 | 328.006 | 145.994 | 474 | 652.4 | -178.4 | 474 | 612.96 | -138.96 | 474 | 848.6886 | -374.6886 | 3318 | 6210.5846 | -2892.5846 | -87.18% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.4.3 | Ex-country training for Youth-hotline staff | NACP |  |  | 0 |  |  | 0 | 8680 |  | 8680 |  | 8680 | -8680 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 8680 | 8680 | 0 | 0%
1.4.2 | WHO Guidelines | NACP |  | 1240.42 | -1240.42 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 1240.42 | -1240.42 | 0% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.4.7 | Training HIV core Team at JDWNRH | NACP |  | 5495.74 | -5495.74 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 5495.74 | -5495.74 | 0% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
SDA 1.5: Intensifying HIV prevention among 10,000 uniformed personnel and their families | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1.5.1 | Development and Printing of HIV information package | RBG/RBP | 3000 | 819.85 | 2180.15 |  |  | 0 |  |  | 0 |  | 1000 | -1000 |  | 2703.29 | -2703.29 |  |  | 0 | 0 | 490.9191 | -490.9191 | 3000 | 5014.0591 | -2014.0591 | -67.14% | Excess budget utilized from other printing budget (SDA 1.3.2)
1.5.2 | Capacity building of women police volunteers | RBG/RBP | 4820 |  | 4820 |  |  | 0 |  |  | 0 |  | 4818.1429 | -4818.1429 | 4820 |  | 4820 |  | 7590.92 | -7590.92 | 0 | 0 | 0 | 9640 | 12409.0629 | -2769.0629 | -28.72% | Q16budget implemented.
1.5.3 | Sensitization of staff at different levels by RBP | RBG/RBP |  |  | 0 | 2517.5 |  | 2517.5 | 2518 |  | 2518 |  | 5358.3654 | -5358.3654 | 3085 |  | 3085 | 3085 |  | 3085 | 6170 | 4408.1993 | 1761.8007 | 17375.5 | 9766.5647 | 7608.9353 | 43.79% | Activity is on-going- SR activity
1.5.4 | Sensitization program for RBA & RBG | RBG/RBP | 2517.5 |  | 2517.5 | 2517.5 |  | 2517.5 |  |  | 0 |  | 2503.2092 | -2503.2092 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 5035 | 2503.2092 | 2531.7908 | 50.28% | Activity is on-going- SR activity
1.5.5 | Awareness program in prisons | RBG/RBP |  |  | 0 |  |  | 0 | 3600 |  | 3600 |  | 3598.6307 | -3598.6307 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3600 | 3598.6307 | 1.3693 | 0.03804%
1.5.6 | Training of instructors from the Military training institutes (RBP, RBG, RBA) | RBG/RBP |  |  | 0 | 5095 |  | 5095 |  |  | 0 |  | 5990.5862 | -5990.5862 |  |  | 0 | 11500 | 8309.85 | 3190.15 | 0 | 2522.3275 | -2522.3275 | 16595 | 16822.7638 | -227.7638 | -1.372% | The activity completed but 14% budget overspent due to new training programs included.
1.5.7 | Attend regional GFATM meetings (for focal persons) | RBG/RBP | 5000 |  | 5000 |  |  | 0 | 5000 |  | 5000 |  | 8634.3603 | -8634.3603 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 10000 | 8634.3603 | 1365.6397 | 13.66% | PR plans to utilize this budget in subsequent qtrs.
1.5.8 | M & E Survey | RBG/RBP |  | 787.26 | -787.26 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 787.26 | -787.26 | 0%
SDA 1.6: Increasing HIV awareness among members of faith-based organizations | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1.6.1 | Cascade Training for Shedras/Lobdras/ community religious practitioners | DRATSHANG |  |  | 0 | 9235 |  | 9235 |  |  | 0 |  | 9092.8541 | -9092.8541 | 1000 |  | 1000 |  | 998.46 | -998.46 | 0 | 1000 | -1000 | 10235 | 11091.3141 | -856.3141 | -8.367% | The variance not material
1.6.2 | Purchase of 1 laptop and 1 projector | DRATSHANG | 2669 |  | 2669 |  |  | 0 |  |  | 0 |  | 2625.1605 | -2625.1605 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2669 | 2625.1605 | 43.8395 | 1.643% | The variance not material
1.6.2 | Attend regional meetings/training program | [16 empty] | 6160 |  | 6160 | 0 | 4439.9824 | -4439.9824 | 6160 | 4439.9824 | 1720.0176 | 27.92% | PR plans to utilize this budget in subsequent qtrs.
1.6.3 | Exchange programme | DRATSHANG |  | 1132.93 | -1132.93 |  |  | 0 | 10900 |  | 10900 |  | 10727.4283 | -10727.4283 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 10900 | 11860.3583 | -960.3583 | -8.811% | The variance not material
1.6.4 | Annual review meeting | DRATSHANG |  |  | 0 |  |  | 0 |  |  | 0 | 1860 | 1829.2683 | 30.7317 |  |  | 0 |  |  | 0 | 2325 | 2339.5415 | -14.5415 | 4185 | 4168.8098 | 16.1902 | 0.3869% | The variance not material
SDA 1.7: Providing services for CSWs, IDUs, and MSMs through NGOs |  |  |  |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1.7.1 | IDU outreach services through sub grantee community organization | NACP | 2000 | 1020.81 | 979.19 | 6000 | 127.85 | 5872.15 |  | 106.97 | -106.97 |  | 5546.4484 | -5546.4484 |  | 113.41 | -113.41 | 22500 | 888.27 | 21611.73 | 0 | 10578.3998 | -10578.3998 | 30500 | 18382.1583 | 12117.8417 | 39.73% | Activity is on-going
1.7.2 | SW outreach services through sub grantee community | NACP | 8000 |  | 8000 |  |  | 0 |  |  | 0 |  | 5372 | -5372 |  | 1103.51 | -1103.51 |  | 1421.6 | -1421.6 | 0 | 0 | 0 | 8000 | 7897.11 | 102.89 | 1.286% | The variance not material
SDA 1.8: Expanding prevention packages to the BHU and the community level with CT services to two additional VCT centers, 176 BHUs and 16 army health units |  |  |  |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1.8.1 | Rent two VCT centres | NACP | 999 |  | 999 | 999 | 2624.13 | -1625.13 | 999 |  | 999 | 999 | 1775 | -776 | 999 | 390.84 | 608.16 | 999 | 297.55 | 701.45 | 999 | 859.5989 | 139.4011 | 6993 | 5947.1189 | 1045.8811 | 14.96% | On-going activity
| Training refresher training of two Health worker from each facility | NACP | [18 empty] | 17166 | 18800.9257 | -1634.9257 | 17166 | 18800.9257 | -1634.9257 | -9.524%
1.8.2 | Procurement of computers & printers for the two VCT centers | NACP | 3982 |  | 3982 |  |  | 0 |  |  | 0 |  | 639.2811 | -639.2811 |  | 46.66 | -46.66 |  | 3914.66 | -3914.66 | 0 | 0 | 0 | 3982 | 4600.6011 | -618.6011 | -15.53% | Expenditure exceeded budget du to price escalation.
1.8.3 | Test kits and vacutainers | NACP |  | 21810.6 | -21810.6 |  | 1973.98 | -1973.98 | 21750 |  | 21750 |  | 8645.6996 | -8645.6996 |  |  | 0 |  |  | 0 | 21750 | 0 | 21750 | 43500 | 32430.2796 | 11069.7204 | 25.45% | The excess expenditure resulted from implementing Phase I spill over activities in Q9.
1.8.4 | Procurement of CD4 reagenst | NACP |  |  | 0 | 13750 |  | 13750 |  |  | 0 |  |  | 0 |  |  | 0 |  | 15059.8 | -15059.8 | 15045 | 0 | 15045 | 28795 | 15059.8 | 13735.2 | 47.7% | Expenditure exceeded budget due to price escalation.
1.8.6 | Printing of IEC materials on HIV and VCT | [16 empty] | 10000 | 853.38 | 9146.62 | 0 | 0 | 0 | 10000 | 853.38 | 9146.62 | 91.47% | The activity is planned for implamentation in Q16 & Q17.
1.8.6 | Purchase of Elisa Readers | NACP |  | 1710.84 | -1710.84 |  | 21840.59 | -21840.59 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 23551.43 | -23551.43 | 0% | The excess expenditure resulted from implementing Phase I spill over activities.
| Refresher training for village health workers | NACP | [12 empty] | 25980 |  | 25980 |  | 19935.33 | -19935.33 | 0 | 16817.2801 | -16817.2801 | 25980 | 36752.6101 | -10772.6101 | -41.47% | The activity is on-going at the time of review
| Refurbishment of VCT Centres | NACP | [12 empty] | 4900 |  | 4900 |  |  | 0 | 0 | 0 | 0 | 4900 | 0 | 4900 | 100% | The activity is planned for implamentation in Q18.
1.8.10 | Ex-country training of councilors | NACP |  |  | 0 |  | 5159.92 | -5159.92 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 5159.92 | -5159.92 | 0% | The excess expenditure resulted from implementing Phase I spill over activities.
SDA 1.9 IEC activities |  |  |  |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1.9.1 | Consultative meeting to develop IEC materials for vulnerable groups | NACP | 984 | 0 | 984 |  | 899.04 | -899.04 |  |  | 0 |  | 718.1857 | -718.1857 |  |  | 0 |  | 24.25 | -24.25 | 0 | 0 | 0 | 984 | 1641.4757 | -657.4757 | -66.82% | The excess expenditure resulted from implementing Phase I spill over activities in Q9, However, the absolute amount is not substantial.
1.9.2 | Field testing of the materials | NACP | 338 | 3207.97 | -2869.97 |  |  | 0 |  |  | 0 |  | 64.3132 | -64.3132 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 338 | 3272.2832 | -2934.2832 | -868.1% | The excess expenditure resulted from implementing Phase I spill over activities in Q9 & Q13
1.9.3 | Printing of materials for vulnerable groups | NACP |  | 1736.25 | -1736.25 | 10000 |  | 10000 |  | 2620.88 | -2620.88 |  | 3415.7681 | -3415.7681 |  | 582.59 | -582.59 |  | 2226.48 | -2226.48 | 0 | 0 | 0 | 10000 | 10581.9681 | -581.9681 | -5.82% | Pending bills to clear at the time of LFA review.
1.9.4 | Sensitization and Breifing to the Media personnel on HIV/AIDS issues | NACP |  | 18718.72 | -18718.72 | 3680 | 433.97 | 3246.03 |  |  | 0 |  | 1245.4472 | -1245.4472 |  | 334.36 | -334.36 |  |  | 0 | 0 | 0 | 0 | 3680 | 20732.4972 | -17052.4972 | -463.4% | The excess expenditure resulted from implementing Phase I spill over activities.
1.9.5 | Undertake supervision and monitoring visits | NACP | 450 | 2985.27 | -2535.27 |  | 251.87 | -251.87 |  |  | 0 | 450 |  | 450 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 900 | 3237.14 | -2337.14 | -259.7% | PR need to provide reason for excess expenditure
1.9.6 | M & E | NACP |  | 24302.99 | -24302.99 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 24302.99 | -24302.99 | 0%
SDA 2.1: Strengthening STI/HIV/AIDS pre-service training and continuous education at the Royal Institute of Health Sciences. |  |  |  |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 | Build up library resources | RIHS | 4000 |  | 4000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 100% | Budget reappropriated for activity 2.1.4 .
2.1.2 | Faculty development - continuning education for lecturers on STI & HIV/AIDS | RIHS |  |  | 0 | 9000 |  | 9000 |  | 9000 | -9000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 9000 | 9000 | 0 | 0%
2.1.3 | Attend Global Fund meeting | RIHS | 2700 |  | 2700 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2738.03 | -2738.03 |  |  | 0 | 0 | 0 | 0 | 2700 | 2738.03 | -38.03 | -1.409%
2.1.4 | Refurbishment of classrooms | RIHS |  |  | 0 | 4500 |  | 4500 |  | 4500 | -4500 |  |  | 0 |  | 2668.08 | -2668.08 |  |  | 0 | 0 | 0 | 0 | 4500 | 7168.08 | -2668.08 | -59.29% | The excess expenditure met from SDA 2.1.1.
SDA 2.2: Strengthening national capacity for programme monitoring and evaluation |  |  |  |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Hire M&E consultant in MOH | NACP | 1950 | 868.81 | 1081.19 | 1950 |  | 1950 | 1950 |  | 1950 | 1950 | 0 | 1950 | 6000 | 632.77 | 5367.23 | 6000 | 10125.43 | -4125.43 | 6000 | 2012.8719 | 3987.1281 | 25800 | 13639.8819 | 12160.1181 | 47.13% | Budget reappropriated for activity 1.9.6.
2.2.2 | Master in epidemiology | NACP | 25000 |  | 25000 | 25000 |  | 25000 |  |  | 0 |  | 758.344 | -758.344 |  |  | 0 |  | 25532.34 | -25532.34 |  | 1215.8254 | -1215.8254 | 50000 | 27506.5095 | 22493.4905 | 44.99% | The activity is on-going at the time of review
2.2.3 | Undertake supervision and monitoring visits | NACP | 1251 | 6010.32 | -4759.32 | 1251 | 32.19 | 1218.81 | 1251 | 946.73 | 304.27 | 1251 | 408.9431 | 842.0569 | 2460 | 751.67 | 1708.33 | 2460 | 1933.22 | 526.78 | 2460 | 1881.4635 | 578.5365 | 12384 | 11964.5366 | 419.4634 | 3.387%
2.2.4 | Send program staff to international forum for information exchange and attend regional meetings of GFATM | NACP | 8100 | 3587.12 | 4512.88 |  |  | 0 | 8100 |  | 8100 |  | 7544.0843 | -7544.0843 | 5310 | 4160.16 | 1149.84 | 4950 | 1064.44 | 3885.56 | 5310 | 8284.4391 | -2974.4391 | 31770 | 24640.2434 | 7129.7566 | 22.44% | PR plans to utilize this budget in subsequent qtrs.
2.2.5 | Training one support staff from NACP on data punching, record keeping | NACP |  |  | 0 | 4580 | 133.58 | 4446.42 |  |  | 0 |  | 4711.4089 | -4711.4089 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 4580 | 4844.9889 | -264.9889 | -5.786% | Variance not material.
2.2.6 | Quarterly meeting of stakeholders | NACP | 270 |  | 270 | 270 |  | 270 | 270 | 928.06 | -658.06 | 270 | 84.0822 | 185.9178 |  | 54.5 | -54.5 |  |  | 0 | 0 | 0 | 0 | 1080 | 1066.6422 | 13.3578 | 1.237% | Variance not material.
2.2.10 | PCM meeting | NACP |  | 1282.97 | -1282.97 |  | 2467.62 | -2467.62 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3750.59 | -3750.59 | 0%
2.2.13 | KAP Survey | NACP |  | 16661.6 | -16661.6 |  | 29070.62 | -29070.62 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 45732.22 | -45732.22 | 0% | The excess expenditure resulted from implementing Phase I spill over activities.
SDA 2.3: Strengthening the management and technical capacity of the NACP | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.3.1 | Diploma in finance management of HIV/AIDS project | NACP | 11210 |  | 11210 |  |  | 0 |  | 14302.44 | -14302.44 |  | 1350.5777 | -1350.5777 | [5 empty] | 0 | 0 | 0 | 0 | 11210 | 15653.0177 | -4443.0177 | -39.63% | PR is required to explain for excess expenditure.
2.3.2 | Building a local pool of expertise in key technical areas | NACP |  | 17625.95 | -17625.95 | 15000 | 3880.63 | 11119.37 |  |  | 0 |  | 15000 | -15000 | [5 empty] | 0 | 0 | 0 | 0 | 15000 | 36506.58 | -21506.58 | -143.4% | PR is required to explain for excess expenditure.
SDA 2.4: Building the capacity of non-govermental sectors as partner in the national HIV/AIDS response |  |  |  |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.4.1 | Exchange programme for PLHA | NACP |  | 8489.25 | -8489.25 |  | 3653.89 | -3653.89 | 7930 |  | 7930 |  | 7930 | -7930 |  |  |  | 7650 |  | 7650 | 0 | 0 | 0 | 15580 | 20073.14 | -4493.14 | -28.84% | PR is required to explain for excess expenditure.
2.4.2 | Training people living with HIVAIDS | [19 empty] | 16679 | 666.123 | 16012.877 | 16679 | 666.123 | 16012.877
2.4.4 | Workshop | NACP |  | 27508.1 | -27508.1 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 27508.1 | -27508.1 | 0% | The excess expenditure resulted from implementing Phase I spill over activities.
SDA 3. Ensuring care & treatment |  |  |  |  | 0 | [14 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
3.1 | Procurement of ARVs | NACP |  |  | 0 |  | 13640.39 | -13640.39 | 40419 |  | 40419 |  |  | 0 | [5 empty] | 0 | 0 | 15425.6985 | -15425.6985 | 40419 | 29066.0885 | 11352.9115 | 28.09% | Complete payments for procurement of ARV is not released at the time of this review.
| TOTAL PROGRAM COSTS |  | 170349.5 | 206886.86 | -36537.36 | 162429 | 91862.89 | 70566.11 | 159161 | 169161.09 | -10000.09 | 86999 | 241587.8932 | -154588.8932 | 132560.07 | 19009.24 | 113550.83 | 244572 | 185602.93 | 58969.07 | 108107 | 115734.6692 | -7627.6692 | 1064177.57 | 1029845.5724 | 34331.9976 | 3.226%
Analysis of Cumulative Variance (Phase I and II)
| Phase 1 (Q1-8) | PR | SR | Total
| Cumulative budget at end of Q8 (Phase 1) | 620602 | 653496 | 1274098
| Cumulative expenditure at end of Q8 (Phase 1) | 504317.2 | 510178.13 | 1014495.33
| Cumulative variance at end of Q8 (Phase 1) | 116284.8 | 143317.87 | 259602.67
Phase 2 (Q9-15)
| Cumulative budget for Q9-15 | 453776 | 610401.07 | 1064177.07
| Cumulative expenditure for Q9-15 | 478914.79 | 550939.59 | 1029854.38
| Cumulative variance for Q9-15 | -25138.79 | 59461.48 | 34322.69
Cumulative for Phase 1+ (Q9-15) Overall variance
| Cumulative budget at end of Q15 | 1074378 | 1263897.07 | 2338275.07
| Cumulative expenditure at end of Q15 | 983231.99 | 1061117.72 | 2044349.71
| Cumulative varaince at end of Q15 | 91146.01 | 202779.35 | 293925.36
| % Budget allocation at Q15 end | 45.95% | 54.05%
| Burn rate at Q15 end | 91.52% | 83.96% | 87.43%
| % Cumulative variance at end of Q15 | 8.484% | 16.04% | 12.57%

## Annexure_C_CurVAR
Annexure C: Line item analysis variance for Q15 (ASO_ 2011)
| Objectives / Service Delivery Areas (SDAs) |  | ASO (Q15)
SDA |  | PR/SR | Budget | Expenditure | Variance | % Variance | LFA Comments
| i. PA wirless meeting amplifier to be sent to schools | DYS | 0 | 6642.3848 | -6642.3848 | 0% | Q14 budget implemented in Q15.
| iii. TV for schools | DYS | 0 | 13500 | -13500 | 0%
| iv. DVD player for school | DYS | 0 | 3000 | -3000 | 0%
| Quarterly Exchange of experience | DYS | 6340 | 0 | 6340 | 100% | Budget Implemented in Q14.
1.4.1 | Training/refresher of staff about youth-issues | NACP | 7389 | 0 | 7389 | 100% | Implementation of this budget is planned in Q16.
1.4.2 | Telephone line charges | NACP | 474 | 848.6886 | -374.6886 | -79.05% | This activity is quarterly budget. The excess expenditure is met from Q16 budget provision.
1.5.3 | Sensitization of staff at different levels by RBP | RBG/RBP | 6170 | 4899.1193 | 1270.8807 | 20.6% | Activity is on-going by the SR.
1.5.6 | Training of instructors from the Military training institutes (RBP, RBG, RBA) | RBG/RBP | 0 | 2522.3275 | -2522.3275 | 0% | Q14 budget implemented in Q15.
1.6.1 | Cascade Training for Shedras/Lobdras/ community religious practitioners | DRATSHANG | 0 | 1000 | -1000 | 0% | Q14 budget implemented in Q15.
1.6.2 | Purchase of 1 laptop and 1 projector | DRATSHANG | 0 | 0 | 0 | 0%
1.6.2 | Attend regional meetings/training program | DRATSHANG | 0 | 4439.9824 | -4439.9824 | 0% | Q14 budget implemented in Q15.
1.6.4 | Annual review meeting | DRATSHANG | 2325 | 2339.5415 | -14.5415 | -0.6254% | The variance not material
1.7.1 | IDU outreach services through sub grantee community organization | NACP | 0 | 10578.3998 | -10578.3998 | 0% | Year 5 budget (Q17 & Q18) implemented in Q15.
1.8.1 | Rent two VCT centres | NACP | 999 | 859.5989 | 139.4011 | 13.95% | On-going activity
| Training refresher training of two Health worker from each facility | NACP | 17166 | 18800.9257 | -1634.9257 | -9.524% | Expenditure exceeded budget by 10%. The amount is not materially significant in the opinion of the LFA.
1.8.3 | Test kits and vacutainers | NACP | 21750 | 0 | 21750 | 100% | Unimplemented due to delay in finalization of PSM plan.
1.8.4 | Procurement of CD4 reagenst | NACP | 15045 | 0 | 15045 | 100% | Unimplemented due to delay in finalization of PSM plan.
| Refresher training for village health workers | NACP | 0 | 16817.2801 | -16817.2801 | 0% | Q14 budget implemented in Q15.
2.2.1 | Hire M&E consultant in MOH | NACP | 6000 | 2012.8719 | 3987.1281 | 66.45% | The activity is on-going at the time of this reciew. Only part payment to the consultant is recorded.
2.2.2 | Master in epidemiology | NACP |  | 1215.8254 | -1215.8254 | 0% | Long term training budget provided in previous quarters.
2.2.3 | Undertake supervision and monitoring visits | NACP | 2460 | 1881.4635 | 578.5365 | 23.52% | The activity is on-going at the time of this reciew. Only part payment is recorded in this quarter..
2.2.4 | Send program staff to international forum for information exchange and attend regional meetings of GFATM | NACP | 5310 | 8284.4391 | -2974.4391 | -56.02% | Excess expenditure met from the budget provided in the previous quarters (refer cumulative variance analysis in Annexure D).
2.4.2 | Training people living with HIVAIDS | NACP | 0 | 666.123 | -666.123 | 0% | The activity was on-going at the time of this review. Only part payment is captured in this review report.
3.1 | Procurement of ARVs | NACP | 16679 | 15425.6985 | 1253.3015 | 7.514% | Variance is not material.
| TOTAL PROGRAM COSTS |  | 108107 | 115734.6701 | -7627.6701 | -7.056%
Analysis of current vairnace (Q15)
| Analysis of Budget | PR | SR | Total
| Total Budget for Q15 | 93272 | 14835 | 108107
| Current budget fully or partially implemented for Q15 | 49088 | 8495 | 57583
| Q15 budget not implemented | 44184 | 6340 | 50524
| % Budget allocation | 86.28% | 13.72% | 100%
| % Q15 budget fully or partially implemented | 52.63% | 57.26% | 53.26%
| % Q15 budget not implemented | 47.37% | 42.74% | 46.74%
Expenditure Analysis
| Total Expenditure | 77391.31 | 38343.36 | 115734.67
| Budgeted Expenditure- Q15 | 48113.6861 | 7238.6608 | 55352.3469
| Back log Activities | 18699.2286 | 31104.6947 | 49803.9233
| Q17 and Q18 budget implemented in Q15 | 10578.3998 | 0 | 10578.3998
| % Budgeted expenditure | 62.17% | 18.88% | 47.83%
| % Expenditure related to back log activities | 24.16% | 81.12% | 43.03%
| % Year 5 budget (Q17 and Q18) implemented in Q15 | 13.67% |  | 9.14%
| Variance | 15880.69 | -23508.36 | -7627.67
| % Varianace | 17.03% | -158.5% | -7.056%
| Budget absorption rate in Q15 | 82.97% | 258.5% | 107.1%

## Memo HIV (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
Please select… | Please select… | Please select… | Please select… | Please select… |  | Please select…
Prevention: Behavioral Change Communication - Mass media | % of young women and men aged 15-24 who are HIV infected | impact | % of young people aged 15-24 who had sex with more than one partner in the last year | National Health Accounts | Please enter a corresponding indicator here… | Please select disease and Impact/Outcome first
Prevention: Behavioral Change Communication - community outreach | % of adults aged 15-49 who are HIV infected | outcome | % of young people aged 15-19 who have never had sex | DHS/DHS+ (Demographic and Health Survey) | Please enter a data source here…
Prevention: Condom distribution | % of adults and children with HIV still alive 12 months after initiation of antiretroviral therapy (extend to 2, 3, 5 years as program matures) |  | % of young people aged 15-24 who never had sex in the last year of those who ever had sex | MICS (Multiple Indicator Cluster Survey) | Please enter a SDA here…
Prevention: Counseling and Testing | % of infants born to HIV infected mothers who are infected |  | % of young people aged 15-24 reporting the consistent use of a condom with non-regular sexual partners in the last year | AIS (AIDS Indicator Survey)
Prevention: PMTCT | % of most-at-risk population(s) (sex workers, clients of sex workers, men who have sex with men, injecting drug users) who are HIV infected |  | % of young women and men who had sex before the age of 15 | SAMS (Service Availibility Mapping Survey)
Prevention: Post-exposure prophylaxis (PEP) | % of HIV seroprevalence among all newly registered TB patients |  | % of adults and children who are still on treatment after 6 months, 1, 2, 3, 5 years from the initiation of treatment | BSS (Behavioral and Surveillance Survey)
Prevention: STI diagnosis and treatment |  |  | % of injecting drug users who have adopted behaviors that reduce transmission of HIV. | Sentinel surveillance
Prevention: Blood safety and universal precaution |  |  | % of orphaned children compared to non-orphaned children aged 10-14 who are currently attending school | Serological surveys
Treatment: Antiretroviral treatment (ARV) and monitoring |  |  | % of young people aged 15-24 reporting the use of a condom the last time they had sex with a non-regular sexual partner | Prevalence surveys
Treatment: Prophylaxis and treatment for opportunistic infections |  |  | % of people expressing accepting attitudes towards PLWHA, of all people surveyed aged 15-49 | Facility-based survey
Care and support: Care and support for the chronically ill |  |  | % of female sex workers reporting the use of a condom with every client in the last month | Key informant survey
Care and support: Support for orphans and vulnerable children |  |  | % of men who have had sex with a female sex worker in the last year | Specific surveys (to be defined)
TB/HIV collaborative activities: HIV care and support for HIV-positive TB patients | TB/HIV collaborative activities: Intensified case-finding among PLWHA |  | % of men reporting the use of condom the last time they had anal sex with a male partner in the last 6 months | Civil registration systems (vital/disease specific registration)
Supportive environment: Policy development including workplace policy | TB/HIV collaborative activities: Prevention of TB disease in PLWHA |  |  | Census
Supportive environment: Strengthening of civil society and institutional capacity building | TB/HIV collaborative activities: Prevention of HIV in TB patients |  |  | Health service statistics
Supportive environment: Stigma reduction in all settings | TB/HIV collaborative activities: Prevention of opportunistic infections in PLWHA with TB |  |  | Patient register
Supportive environment: Program management and administration |  |  |  | Clinical cohort follow-up studies
HSS: Service delivery | TB/HIV collaborative activities: Provision of antiretroviral treatment for TB patients during TB treatment |  |  | Community services assessment
HSS: Human resources | HSS: PAL (Practical Approach to Lung Health) |  |  | Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
HSS: Community Systems Strengthening |  |  |  | Operational research
HSS: Information system & Operational research
HSS: Infrastructure
HSS: Procurement and Supply management
HSS: Other, specify

## Memo TB (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
please select… | please select… | please select… | please select… | please select…
Improving diagnosis | TB prevalence rate | impact | Case detection | National Health Accounts
Standardized treatment, patient support and patient charter | TB incidence rate | outcome | Treatment success rate | DHS/DHS+ (Demographic and Health Survey)
Procurement and supply management | TB mortality rate |  | Smear conversion rate | MICS (Multiple Indicator Cluster Survey)
M&E |  |  |  | AIS (AIDS Indicator Survey)
TB/HIV |  |  |  | SAMS (Service Availibility Mapping Survey)
MDR-TB |  |  |  | BSS (Behavioral and Surveillance Survey)
High-risk groups |  |  |  | Sentinel surveillance
HSS (beyond TB) |  |  |  | Serological surveys
PAL (Practical Approach to Lung Health) |  |  |  | Prevalence surveys
PPM / ISTC (Public-Public, Public-Private Mix (PPM) approaches and International standards for TB care) |  |  |  | Facility-based survey
ACSM (Advocacy, communication and social mobilization) |  |  |  | Key informant survey
Community TB care |  |  |  | Specific surveys (to be defined)
Programme-based operational research
Other:Specify
Supportive environment: Program management and administration |  |  |  | Civil registration systems (vital/disease specific registration)
Census
Health service statistics
Patient register
Clinical cohort follow-up studies
Community services assessment
Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
Operational research
R&R TB system, quarterly report
R&R TB system, yearly management report
Other Surveillance reports, specify

## Memo Malaria (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
please select… | please select… | please select… | please select… | please select…
Prevention: Behavioral Change Communication - Mass media | Death rates associated with Malaria: all-cause under-5 mortality rate in highly endemic areas | impact | % of U5 children (and other target groups) with malaria/fever receiving appropriate treatment within 24 hours (community/health facility) | National Health Accounts
Prevention: Behavioral Change Communication - community outreach | Incidence of clinical malaria cases (estimated and/or reported) | outcome | % of U5 children (and other target group) with uncomplicated malaria correctly managed at health facilities | DHS/DHS+ (Demographic and Health Survey)
Prevention: Insecticide-treated nets (ITNs) | Anaemia prevalence in children under 5 years of age |  | % of U5 children (and other target groups) admitted with severe malaria and correctly managed at health facilities | MICS (Multiple Indicator Cluster Survey)
Prevention: Malaria prevention during pregnancy | Prevalence of malaria parasite infection |  | % of children U5 sleeping under an ITN the previous night | MIS (Malaria Indicator Survey)
Prevention: Vector control (other than ITNs) | Laboratory-confirmed malaria cases seen in heath facilities |  | % of households with at least one ITN | SAMS (Service Availibility Mapping Survey)
Prevention: other - specify | Laboratory-confirmed malaria deaths seen in health facilities |  | % of pregnant women (and other target groups) sleeping under an ITN the previous night | BSS (Behavioral and Surveillance Survey)
Treatment: Prompt, effective anti-malarial treatment | Malaria-attributed deaths in sentinel demographic surveillance sites |  | % of pregnant women on Intermittent preventive treatment (IPT) according to national policy (specific to Sub-Saharian Africa) | Sentinel surveillance
Treatment: Home based management of malaria | API (Annual Parasite Index) (specific to Latin America and Asia) |  | % of households in malaria areas protected by IRS | MOH (routine HIS or HMIS)
Treatment: Diagnosis |  |  |  | RBM (Roll Back Malaria)
Treatment: other - specify |  |  |  | Serological surveys
Supportive environment: Monitoring drug resistance |  |  |  | Prevalence surveys
Supportive environment: Monitoring insecticide resistance |  |  |  | Facility-based survey
Supportive environment: Coordination and partnership development (national, community, public-private) |  |  |  | Key informant survey
Supportive environment: other - specify |  |  |  | Specific surveys (to be defined)
Supportive environment: Program management and administration |  |  |  | Civil registration systems (vital/disease specific registration)
HSS: Service delivery |  |  |  | Census
HSS: Human resources |  |  |  | Health service statistics
HSS: Community Systems Strengthening |  |  |  | Patient register
HSS: Information system & Operational research |  |  |  | Clinical cohort follow-up studies
HSS: Infrastructure |  |  |  | Community services assessment
HSS: Procurement and Supply management |  |  |  | Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
HSS: other - specify |  |  |  | Operational research
Questionnaire

## Definitions-lists-EFR (hidden)
Please Select…
Prevention
Treatment
Care and Support
TB/HIV Collaborative Activities
Supportive Environment
Health System Strengthening (HSS)
Please Select…
Prevention
Treatment
Supportive Environment
Health System Strengthening (HSS)
Please Select…
Prevention: Behavioral Change Communication - Mass Media
Prevention: Behavioral Change Communication - Community Outreach
Prevention: Insecticite-treated nets (ITNs)
Prevention: Malaria in pregnancy
Prevention: Vector control (other than ITNs)
Prevention: Other - specify
Treatment: Prompt, effective antimalatial treatment
Please Select…
TB Detection
TB Treatment
TB/HIV Collaborative Activities
Supportive Environment
Health System Strengthening
Please Select…
Improving diagnosis
Standardized treatment, pation support and patient charter
Procurement and Supply management
M&E
TB/HIV
MDR-TB
High-risk groups
Please Select…
FBO
NGO/CBO/Academic
Private Sector
Ministry Health (MoH)
Other Government
UNDP
Other Multilateral Organization