## Slide 1
Debrief – Global Fund CT mission Bhutan 9-12 June 2015 Debrief with CCM Chair, Director and Chief Program Officer DoPH, CCM members
12 June 2015
Thimphu, Bhutan

## Slide 2: Content Overview
Framework Agreement
Program updates and next steps
TB
Malaria
HIV
“Closures” existing TFM grants
Financial Issues
Cross-cutting issues
CCM Secretariat
Questions

## Slide 3: Framework agreement (FA)
    Signature of NFM grants and disbursement of funds thereunder can only happen after signature of the FA
    Clarification on section 12.2 of the grant regulations (privileges & immunities): “…the Grantee confirms that the ‘Agreement on Privileges and Immunities of the Global Fund to Fight AIDS, Tuberculosis and Malaria’, adopted by the Global Fund Board, is under review of the relevant authorities of the Kingdom of Bhutan.”
     Next steps:
      Relevant ministries/GNHC to discuss revised wording on privileges & immunities
      Provide timeline on Framework Agreement signature to Global Fund

## Slide 4: TB
GF will prepare grant confirmation (grant agreement) – can only be signed once the FA is signed
Updates:
      Activities conducted as planned (except TB/HIV coordination meeting)
      Discussion on direct payment from GF to IDA Foundation for SLD
    Challenges:
      DOTS to be strengthened
      Increased MDR-TB (mostly due to weakness in DOTS and cross-border issues)
      Electronic reporting systems not being used
      Monitor better how DOTS is implemented at health centers
      Engage with partner/NGO to support DOTS implementation
      Strengthen the three regional reference hospitals for MDR-TB treatment
NFM grant was approved by the Board:
US$ 2,083,173 for the period 1 July 2015 – 30 June 2018

## Slide 5: TB
Next steps:
      Update MDR-TB expansion plan
      Provide communication strategy (draft communication is in place already) and explain how main risk population is targeted (MA)
      Provide indicator reference sheet by 1 Aug 2015 (MA)
      Submit GeneXpert implementation plan validated by WHO by 1 Aug 2015 (MA)
      Submit all necessary documents for TFM grant end (see separate slide)

## Slide 6: Malaria
 GF will prepare grant confirmation (grant agreement) – can only be signed once the FA is signed
Updates:
      Update of M&E plan as per the NSP has already started
      Discussions among stakeholders to be done
      Submit final M&E plan by 30 Sep 2015
    Challenges:
      Insecticide resistance: needs to be better monitored
       Plan for insecticide resistance monitoring to be submitted to GF (MA), including expansion of sentinel sites to 2 other districts
NFM grant was approved by the Board on 9 June 2015:
US$ 1,942,261 for the period 1 July 2015 – 30 June 2018

## Slide 7: Malaria
Next steps:
      LLIN distribution list to be provided (outstanding MA from previous period)
      Case investigation report to be provided (together with the PU) (outstanding MA)
      Indicator reference sheet to be provided to GF by 20 June 2015 (MA)
      Submit policy of DSA payment for village health workers and community action group to GF by end June
      Submit all necessary documents for TFM grant end (see separate slide)

## Slide 8: HIV
Updates:
ART guidelines were updated
Meetings with Lhaksam and LGBTI community
Meeting with UNDP on collaboration for removal of legal barriers
Challenges:
MSM/TG network strengthening  decide on human resource position representing MSM/TG (HISC, Lhaksam...?)
Viral load test  discuss the use of GeneXpert for viral load testing for the future (more cost effective and easy to use) – start with in-country evaluation and coordinate with TB team
IBBS  make sure that key populations are included in the planning stage. Share ToR with the GF
NFM grant was approved by the GAC on 27 May 2015 and sent to the Board for approval (outcome expected in early July)
US$ 2,001,227 for the period 1 July 2015 – 30 June 2018

## Slide 9: HIV
Next steps:
      Submit revised NFM budget to GF
      Stock status to be provided with expiry dates, specifications walk-in cold room
      Decide on procurement through PPM or to be done by country
      Provide indicator reference sheet by 1 July 2015 (MA)
      Provide updated costed M&E work plan by 1 July 2015 (MA)
      Submit all necessary documents for TFM grant end (see separate slide)

## Slide 10: “Closures” existing TFM grants
    Steps to be completed by all three disease programs:
      Submit (estimated) uncommitted cash balance until 30 June 2015
      Submit PU until end June by mid-Aug 2015 together with EFR and update on outstanding MA
      Submit audit ToR for the NFM period 2015-2016
      Submit audit report until end June by 30 Sep 2015
      Submit inventory list of non-cash assets that will be transferred to new grant by 30 Sep 2015
      All other non-cash assets (health consumables, drugs and similar) need to be added to the fixed assets list
      TFM grants to be fully closed by end Dec 2015
      First disbursement under the new grants will be processed «automatically» once the grant is signed based on approved budget (no need for disbursement request)

## Slide 11: Financial issues
    Audits
    “New” timeline for submission of audit reports: 3-month after period end date
    Audit ToR for TB for 2014-2015 and 2015-2016 approved by GF
     Audit ToR for HIV for 2014-2015 and 2015-2016 approved by GF on 15 June
    Audit ToR for M for 2014-2015 approved by GF on 15 June and 2015-2016 to be submitted
    10K were set aside in the new grants: only as a safety measure in case it is needed, if not needed, these funds can be reprogrammed
    Taxes
    Tax exemption table to be submitted to GF by 20 June 2015 (if any taxes paid, provide amount of taxes paid and amount of taxes recovered – for both PR and SRs)

## Slide 12: Cross-cutting issues
    Procurement
    Move to Department of Medical Supplies
    Possibility of using PPM for HIV (to be decided by the country)
    E-LMIS
    Electronic stock management system to be implemented (TA funding included in TB NFM grant – other disease grants to collaborate in development and deployment)
    Sustainability
    CCM/country needs to establish a sustainability plan/transition plan
    Regular updates
    Bhutan will now report on annual basis (PUDR), however, it is important to have regular communication to update on progress made on the programs, including financial information

## Slide 13: CCM Secretariat
Deliverable | Update/Agreed action
Y1 Expenditure report (1 Mar – 30 Jun 2014) | CCM has submitted Y1 expenditure report online  Official cash balance bank statement to be provided by 15 June 2015
Y2 Expenditure report (1 Jul 2014 – 30 June 2015) | Y2 expenditure report to be submitted to GF through online system once Y1 is closed Official cash balance bank statement as of end May 2015 to be provided to the GF by 15 June plus expected expenditures for June
CCM funding (Jul 2015 – June 2017) | CCM has submitted draft funding request GF will review and provide formal feedback (initial feedback provided during mission) Needs to be endorsed by entire CCM before agreement signature
Improvement Plan | Update needs to be provided by CCM on a monthly basis CCM to provide supporting documentation for the change of ratings
Oversight visits | This was identified as major weakness in the EPA  CCM to take action: undertake oversight activities and share and discuss challenges/findings with PR; seek feedback from non-CCM members and PLWD

## Slide 14: Questions?
    Next visit by Global Fund planned end October 2015: participation in the pre-Board meeting in Paro (26-27 Oct) and visit of the malaria program
    TASHI DELEK