## Sheet1
| 2016 | 2017 | [11 empty] | 2018
| December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | Comments
New Grant Applications
Allocation letters sent | 2016 December: 2016-12-15
CCM Determination of Program Split | 2017 March: TBD -- pre grant making
BTN-H-MOH: Program Continuation Request
First draft of program continuation request form | 2017 February: 2016-02-28
Application due | 2017 March: 2020-03-01
Expected feedback from TRP | 2017 May: early May
Grant making (assuming TRP gives go ahead) | bar: 2017 June; 2017 September to 2017 November; 2018 January
GAC review of grant documents | bar: 2018 February
Board approval of grant documents | bar: 2018 March
Grant signing | bar: 2018 April
New grant start date | 2018 July: 2001-07-01
TLS-T-MOH: Program Continuation Request
First draft of program continuation request form | 2017 February: 2016-02-21
Application due | 2017 March: 2020-03-01
Expected feedback from TRP | 2017 May: early May
Grant making (assuming TRP gives go ahead) | bar: 2017 June; 2017 September to 2017 November
GAC review of grant documents | bar: 2018 February
Board approval of grant documents | bar: 2018 March
Grant signing | bar: 2018 April
New grant start date | 2018 July: 2001-07-01
TLS-M-MOH: Program Continuation Request
First draft of program continuation request form | 2017 February: 2016-02-14
Application due | 2017 March: 2020-03-01
Expected feedback from TRP | 2017 May: early May
Grant making (assuming TRP gives go ahead) | bar: 2017 June; 2017 September to 2017 October
GAC review of grant documents | bar: 2018 February
Board approval of grant documents | bar: 2018 March
Grant signing | bar: 2018 April
New grant start date | 2018 July: 2001-07-01
Global Fund Reporting Requirements for Existing Grants
PU/DR and AFR
BTN-H-MOH | 2017 September: 2016-09-01 | Need to determine staggered reporting schedule for three disease programs
LFA Review | 2017 October: TBC
TLS-T-MOH | 2017 September: 2016-09-01
LFA Review | 2017 October: TBC
TLS-M-MOH | 2017 September: 2016-09-01
LFA Review | 2017 October: TBC
2016 Tax Reporting | 2017 July: TBD
Additional Key Grant Activities
Global Fund Missions | 2017 June: TBC | Need to determine best time for sustainability discussions